## Sheet1
| Project Phase | Project Meetings (All) | Solution Planning | Plan & Design | Build & Test | Implement
| Project Activities | Attend internal project team meetings, Attend customer project team meetings, Attend executive steering meetings | Review SoW, Setup Project code, Internal Project Kickoff, Customer Project Kickoff, Validate customer H/W & S/W requirements, Deliver application licenses | Participate in a business assessment workshop to gather detailed requirements, Document Solution Detail Document (SDD), Develop Project Plan, Review Customer Test Plan, Develop Internal Test Plan, Obtain Sign off of SDD & Test Plans | Setup internal server, Install & configure application in an internal environment, Build Configuration, Unit Test the application setup & Configuration, end-to-end test the setup & configuration, Fix cases, Re-test, Compile software package, Deliver package, Update SDD | Support Customer Installation & Configuration in up to 4 environments (Test, Cert, Prod, HA) for x weeks, Support Customer Testing in up to 4 environments (Test, Cert, Prod, HA) for x weeks, Review Customer go-live / roll-back plan, Support on-the-night-go-live, Support post-prod stabilization, Prepare HELP24 handover document, Handover to HELP24, Close project code
| Enter Number of weeks | 0 | 0 | 0 | 0 | 0
| Hours/Week | 40 | 40 | 40 | 40 | 40
Enter Allocations | Infrastructure Technical Consultant | 0% | 0% | 0% | 0% | 0%
| Business Analyst | 0% | 0% | 0% | 0% | 0%
| Solution Architect | 0% | 0% | 25% | 0% | 0%
| Technical Consultant (MTS) | 0% | 0% | 0% | 0% | 0%
| Technical Consultant (UPF) | 0% | 0% | 0% | 0% | 0%
| Application Configuration (MTS) | 0% | 0% | 0% | 0% | 0%
| Quality Analyst | 0% | 0% | 0% | 0% | 0%
| Project Manager | 25% | 25% | 25% | 25% | 25%
| Infrastructure Technical Consultant | 0 | 0 | 0 | 0 | 0
| Business Analyst | 0 | 0 | 0 | 0 | 0
| Solution Architect | 0 | 0 | 0 | 0 | 0
| Technical Consultant (MTS) | 0 | 0 | 0 | 0 | 0
| Technical Consultant (UPF) | 0 | 0 | 0 | 0 | 0
| Application Configuration (MTS) | 0 | 0 | 0 | 0 | 0
| Quality Analyst | 0 | 0 | 0 | 0 | 0
| Project Manager | 0 | 0 | 0 | 0 | 0
| SUB TOTAL | 0 | 0 | 0 | 0 | 0
| TOTAL (LOW) | 0
| Enter Contingency (Confidence level) | 25%
| TOTAL (HIGH) | 0
Enter Assumptions:
1
2
3
4
5
6
7
8
9
10