## Intercompany
ABA
| Project Phase | Project Meetings (All) | Solution Planning | Plan & Design | Build & Test | Implement
| Project Activities | Attend internal project team meetings, Attend customer project team meetings, Attend executive steering meetings | Review SoW, Setup Project code, Internal Project Kickoff, Customer Project Kickoff, Validate customer H/W & S/W requirements, Deliver application licenses | Participate in a business assessment workshop to gather detailed requirements, Document Solution Detail Document (SDD), Develop Project Plan, Review Customer Test Plan, Develop Internal Test Plan, Obtain Sign off of SDD & Test Plans | Setup internal server, Install & configure application in an internal environment, Build Configuration, Unit Test the application setup & Configuration, end-to-end test the setup & configuration, Fix cases, Re-test, Compile software package, Deliver package, Update SDD | Support Customer Installation & Configuration in up to 4 environments (Test, Cert, Prod, HA) for x weeks, Support Customer Testing in up to 4 environments (Test, Cert, Prod, HA) for x weeks, Review Customer go-live / roll-back plan, Support on-the-night-go-live, Support post-prod stabilization, Prepare HELP24 handover document, Handover to HELP24, Close project code
| Enter Number of weeks | 1 | 1 | 2 | 4 | 2
| Hours/Week | 40 | 40 | 40 | 40 | 40
Enter Allocations | Infrastructure Technical Consultant | 0% | 0% | 0% | 0% | 0%
| Business Analyst | 0% | 0% | 0% | 0% | 0%
| Solution Architect | 80% | 80% | 50% | 0% | 0%
| Technical Consultant (MTS) | 10% | 20% | 20% | 0% | 0%
| Technical Consultant (UPF) | 0% | 0% | 0% | 0% | 0%
| Application Configuration (MTS) | 0% | 0% | 0% | 0% | 0%
| Quality Analyst | 0% | 0% | 0% | 0% | 25%
| Project Manager | 25% | 25% | 25% | 25% | 25%
| Infrastructure Technical Consultant | 0 | 0 | 0 | 0 | 0
| Business Analyst | 0 | 0 | 0 | 0 | 0
| Solution Architect | 32 | 32 | 40 | 0 | 0
| Technical Consultant (MTS) | 4 | 8 | 16 | 0 | 0
| Technical Consultant (UPF) | 0 | 0 | 0 | 0 | 0
| Application Configuration (MTS) | 0 | 0 | 0 | 0 | 0
| Quality Analyst | 0 | 0 | 0 | 0 | 20
| Project Manager | 10 | 10 | 20 | 40 | 20
| SUB TOTAL | 46 | 50 | 76 | 40 | 40
| TOTAL (LOW) | 252
| Enter Contingency (Confidence level) | 25%
| TOTAL (HIGH) | 315
Enter Assumptions:
1
2
3
4
5
6
7
8
9
10

## New SSB
New SSB Transact lines & New Tran Codes
| Project Phase | Project Meetings (All) | Solution Planning | Plan & Design | Build & Test | Implement
| Project Activities | Attend internal project team meetings, Attend customer project team meetings, Attend executive steering meetings | Review SoW, Setup Project code, Internal Project Kickoff, Customer Project Kickoff, Validate customer H/W & S/W requirements, Deliver application licenses | Participate in a business assessment workshop to gather detailed requirements, Document Solution Detail Document (SDD), Develop Project Plan, Review Customer Test Plan, Develop Internal Test Plan, Obtain Sign off of SDD & Test Plans | Setup internal server, Install & configure application in an internal environment, Build Configuration, Unit Test the application setup & Configuration, end-to-end test the setup & configuration, Fix cases, Re-test, Compile software package, Deliver package, Update SDD | Support Customer Installation & Configuration in up to 4 environments (Test, Cert, Prod, HA) for x weeks, Support Customer Testing in up to 4 environments (Test, Cert, Prod, HA) for x weeks, Review Customer go-live / roll-back plan, Support on-the-night-go-live, Support post-prod stabilization, Prepare HELP24 handover document, Handover to HELP24, Close project code
| Enter Number of weeks | 1 | 1 | 2 | 4 | 2
| Hours/Week | 40 | 40 | 40 | 40 | 40
Enter Allocations | Infrastructure Technical Consultant | 0% | 0% | 0% | 0% | 0%
| Business Analyst | 0% | 0% | 0% | 0% | 0%
| Solution Architect | 80% | 80% | 50% | 0% | 0%
| Technical Consultant (MTS) | 10% | 20% | 20% | 0% | 0%
| Technical Consultant (UPF) | 0% | 0% | 0% | 0% | 0%
| Application Configuration (MTS) | 0% | 0% | 0% | 50% | 0%
| Quality Analyst | 0% | 0% | 50% | 50% | 25%
| Project Manager | 25% | 25% | 25% | 25% | 25%
| Infrastructure Technical Consultant | 0 | 0 | 0 | 0 | 0
| Business Analyst | 0 | 0 | 0 | 0 | 0
| Solution Architect | 32 | 32 | 40 | 0 | 0
| Technical Consultant (MTS) | 4 | 8 | 16 | 0 | 0
| Technical Consultant (UPF) | 0 | 0 | 0 | 0 | 0
| Application Configuration (MTS) | 0 | 0 | 0 | 80 | 0
| Quality Analyst | 0 | 0 | 40 | 80 | 20
| Project Manager | 10 | 10 | 20 | 40 | 20
| SUB TOTAL | 46 | 50 | 116 | 200 | 40
| TOTAL (LOW) | 452
| Enter Contingency (Confidence level) | 25%
| TOTAL (HIGH) | 565
Enter Assumptions:
1
2
3
4
5
6
7
8
9
10

## Sheet3
SPRINT 9 | 11
SPRINT10 | 4
SPRINT 11 | 7
SPRINT 12 | 8
SPRINT 13 | 13
8.6

## Sheet4
|  | sep1-sep 5 | sep8-sep 12 | sep 15-sep 19 | Sep22-sep 26 | sep 29- Oct 3
Task Name
deliver internal code MTS | 2025-09-08
ACI Configurations (UPF/APP)
ACI Internal UPF Config
Milestone:- Configuration Completed
Testing
Configure MTS QA Environment
Connectivity Testing (E2E)
Create test scripts
Review Test Scripts
QA Testing
Delivery
Delivery of MTS Configuration (Config Express) | 2025-09-29
Deploy at TFC
Milestone:- TFC Build Completed