## Sheet1
State Street Bank Sprint 23 Jan 28 - Feb 11
| Case Number | Project | H24 Case Number | RTPS | Defect Title | Severity/Priority | ACI Status | Planned Delivery Date | Comments | Assignee
x | 03711383 | MPA new Lines | H24-658385 | RTPS-107058 | Reverse Posting for Functional cancel doesn't happen for Bank Adapter/Manual Create messages for Transact accounts | Major | In Progres | 2026-02-10 | Feb 09 Sai confirmed that finalized pending update the ticket. Feb06 ready for test Feb 05 Tejas confirm still pending to start testing(jean need to confirm on this) Feb 04 Sail will ask jean code to start this test today Jean Harty added a comment - jan 26 analyzing these cancels. | Tejas
x | 03711383 | MPA new Lines | H24-658385 | RTPS-107299 | Functional cancellations trapping for all Book To Book Transfer transactions in State Street Domestic | Major | Wating Input RTPS-107058 | 2026-02-10 | Feb 09 Sail will cover on this to Tejas Feb06 ready for test Feb 05 (need to be tested together with RTPS-107058) Feb 04 Sail will ask jean code to start this test today Jean Harty added a comment - jan 28 Saikumar Vemasani this was fixed under RTPS-107058. This should be retested when RTPS-107058 is built and ready for QA, then can be closed if the test results are satisfactory. | Sai
x | 03711383 | MPA new Lines | H24-658385 | RTPS-106894/RTPS-106409 | SSB Cancellations -> Reverse bookings is not happening for upon cancellations | Major | Closed |  | Tested - | Sai
x | 03711383 | MPA multiple lines | H24-658385 | RTPS-106764/RTPS-107967 | SSC - US Boston (SSB) : Bank request for multiple parallel AUT/POST lines for Transact | Minor | Ready for testing | 2026-02-10 | Feb09 Line 21 (21/ 25) will completed today, start line 22 (21/25) Feb06 Line 21 (/ 25) will completed today, start line 22 (8/25) Feb 05 Line 21 (50% completed) will start line 22 Feb 04 Neethu advancing but still with issues ( Jan 29 advace (4/50) cases , create file also update in the share point | Neethu/ Katheeja
x | 03777412 | UPF | H24-716063 |  | ISO 20022: UPF Control Center - Super1 Login - "null" | High | Waiting customer answer |  | Feb 06 still waiting from bank comments in the ticket Feb 05 meetig discuss on Dynatrace again - Bank need to update the ticket and Pausti will review it and update the ticket after that Feb 04 Bank confirmed that is working, (without Dynatrace system). Update the ticket Jan 28 Paul escalte to UPF enginneer | Paul
x |  | New Requirement for RISK Queue |  |  | New Requirement |  |  |  | Feb 09 After POC RTPS doesn't support this feature. need Amit to comunicate to bank ( this specific Action item in the minutes) Feb 06 we will discuss on this today Feb 05 Philp will explore the option .(Review feasibility of routing based on string criteria (non-STP, non-risk)) Feb 04 Bank need to advance in requirement to ACI Jan 29 After jan 27 meeting it's require to create POC, also will have feb 3th new meeting to continue the Analysis on this. | Amit
x | 03749089 | New Requirement[ Direct Cover Scenario] | H24-692138 | RTPS-108203 | RPH-US instance RTPS : New Requirement for Intercompany Bank Settlement DDA | High |  |  | Feb 09 Awaiting bank for test cases; Pending Sai comment advanced on this Feb 06 Phill need to check with Jean on this (SDD alredy had Oscar will share with Jean / Philp) Feb05 same status Feb 04 Feb 04 POC sai is advancing on this jan 29 Amit will advance in Solution Document, pending from bank requirement sign off | Amit
x | 03749089 | Bank Settlement DDA | H24-692138 | RTPS-106276 | Test 100 Cases | Low | Open | 2026-02-15 | Feb 09 ready for test will be get for new sprint Feb 06 same status feb 05 Feb 05 Jean update ticket as resolved .. Need to know next steps Feb 04 in progress by jean Include release end March | Neethu
x | 03748411 | Target Cases | H24-691549 | RTPS-85173 | Ent ISO - Target2 - Inbound CAMT025 Receipt not mapping with Outbound CAMT050 Liquidity Credit Transfer message | High | Ready for Dev | 2026-03-30 | Feb 05 same status feb 04 Feb 04 release for march Develope Prod assgned | Mamatha Govindaraju | sai
x | 03757439/'03757445 | Target Cases | H24-699371/H24-699374 | RTPS-106930 | Outbound CAMT050 MX Message - SAA Header Section populated with incorrect values under certain data elements. | High | In Progres |  | Feb 09 in turn 10 Jason H Feb 06 in turn 11 Jason H Feb 04 already scalate with Stephanie Jan 29 Jason H assign 16 site in development | Padmasri Mudugonda | sai
x | 03757391 | Target Cases | H24-699334 | RTPS-107894 | ACK TRN's are not received in MTS and matched with original outbound transaction | Major | Open |  | Feb 06 Tejas sent mail to bank check swift, now banking is asking ACI (Tejas will update the ticket) Feb05 Tejas review info from bank , it's not recreate yet. Need discuss with Philp. Feb 04 Tejas received data from bank will update and review with Paul on this Jan 29 recreate to review with Philp | Tejas
x | 03757393 | Target Cases | H24-699336 | RTPS-107959 | Outbound PACS009 with Receiver/Cdtr Agt - BCITITMMXXX is routed to EXCQ due to TGT Channel Derivation issue. | Major | Open |  | Feb 06 Tejas confirm that work find, will send bank asking what bank is using this data Feb 05 Tejas partially recreate Amit suggest change the account to test it. Feb 04 Tejas will recreate, with the information received by bank Jan 29 recreate to review with Philp | Tejas
|  |  | H24-711312 | RTPS-107184 | 2026 Mandates (March Release) |  | Open |  | Feb 06 Amit wil review on this Feb 05 Amit will review the RTPS-107074 Amy H. request follow this | Amit
| 03771976 | CHIPS Cases | H24-711312 | RTPS-105098 | CHIPS ISO Inbound - Field 72 OBI/BBI long characters | Minor | Open |  | As per bank's request we will be keeping this on hold till Feb 13. | Katheeja
| 03771976 | CHIPS Cases | H24-711312 | RTPS-106826 | Field 72 - Need sequencing changes in the data shown in Field Tag 72 of the MT910 Credit Confirmation sent out by MTS | Minor | Open |  | As per bank's request we will be keeping this on hold till Feb 13. | Katheeja
x | 03775326 | Other cases | H24-714233 | RTPS-106921 | CHAPS-LEI is not retained in the credit payment text where its mandatory for the regulations | Major | In Progress |  | Feb 09 Oscar Will answer Charayna (PCS) need review more internally before product call. Feb 06 After today meeting with Saumya, next steps call to Joe C and send mail to bank on this (sai) Feb 05 Sail will update the ticket H24, and will check with developer. Oscar arrange the call tomorrow 8 am Feb 04 After feb 03 meeting with the bank the bank comment that with june 25 is working . | Anindya Ganguly | sai
x | 03781262 | Other cases | H24-719521 | RTPS-107539 | MTS routing issue: Payment flagged for TRS still routed to Hogan queue (DDA_AUTQ) | Major | Awaiting Customer Action |  | Feb 04 will update the ticket to closed ACI configuration team have reviewed this concern, and this is confirmed to be ‘Working as Designed’. Please find the response from the team below. | Katheeja
x | 03781260 | Other cases | H24-719519 | RTPS-107540 | Transact MPA lines Login request contains junk characters for Transact Accounts | Major | Open |  | Feb 06 this was de-pririozited by bank Feb 05 Tejas will update messages in RTPS / H24 Feb 04 Tejas will update the ticket Develope Prod assgned | Jitendra Gupta | Tejas
x | 03754982 | Other cases | H24-697226 |  | Wait-Posting event not sent for messages with source BTR from MTS to UPF(Domestic) |  | Awaiting Customer Action |  | Jan 29 bank confirmed be closed Tejas will closed and send mail bank to bank | Tejas
[5 empty] | HKICL RTGS Dual Network Channel Requirement |  |  |  | Feb 04 we received mail from bank related to analyze the implementation on this Jan 19 Mayjane replayed that bank is analyzing on this will confirm at the end of jan | Amit
| '03640399 |  | H24-595902 |  | Payments Canada / Lynx mandatesmail sent by Scott to Bank request (jan27) | Minor | Open |  | jan 29 Mayjane answer mail to Scott with the info, Scott resent to Amy H product | Scott
[5 empty] | Venkata - Can BankAdapter consume FedWire format message as is for Non-Pass Through/Pass Through Model | Minor | Awaiting Customer Action |  | jan 26 Amit will send mail on this today | Amit
x | 03785212 | Inquiry | H24-722986 |  | Inquiry - MPA post interface changes | Minor | Open |  | Feb 09 Amit need to answer to bank / we need to wait for ACI product annoucment Feb 06 we try to recreate issue here to discuss with Philp today Feb 05 to discuss with Philp today meeting Feb 04 Amit will document on this before review with Philp Jan 30 Oscar sent mail to Scott | Oscar
|  |  | H24-709214 |  | SSG ¦ MTS ¦ Processes getting TRAPPED | Minor | Open
x | 03785216 | Inquiry | H24-722988 |  | Inquiry - Charges information configuration based on Source | Minor | Open |  | Feb 09 waiting bank answer Feb 06 already sent to bank waiting bank response Feb 04 Amit need to response to bank on the question | Amit
x | 03785363 | Inquiry | H24-723118 |  | Inquiry - Need sample of CBPR+ PAIN.001 message with multiple CdtTrfTxInf and corresponding PAIN.002 responses (Batch Adaptor) | Minor | Open |  | Feb 09 we need to wait for ACI product annoucment Feb 06 we need to wait for ACI product annoucment Feb 05 SME agenda / after that call with joe (prod) Feb 04 Amit already sent the response | Amit
x | 03785698 | Other Cases | H24-723416 |  | SSC¦ MTS¦ FED Payments incorrectly routing through CHP | Minor | Open |  | Feb 09 Katheeja, not possible to check in sept- service pack. Need tos comment to SME meeting. Feb 06 Philp will change in the rules. Feb 05 Katheeja already recreate the issue. (SSI) create RTPS Feb 04 Katheeja start recreation found TRAPs | Katheeja
x |  |  |  |  | Code Delivery Feb 13 | High | Open |  | Feb 05 need discuss with Jean to send the ticket for snapshoot to bank | Oscar
x | 03779477 | UPF | H24-717875 |  | Control Center December Service Pack Installation Errors | High | Open |  | Feb 09 Siva will review on this and support to bank on this Feb 06 Bank will test it , next steps wait for Bank comments on this. Feb 05 Bank insist they have version mq-client different that ACI recommend, Paul will escalate this | Paul
x | 03785698 |  | H24-723416 | RTPS-67069 | SSG - modify NON_BUSINESS_DAY_EDIT to allow for Sunday processing | Minor | Open |  | Feb 09 Sai will check with Jean Feb 06 open by jean to test by PCS | sai