## Sheet1
State Street Bank Sprint 25 Feb 12 - Feb 25
| Case Number | Project | H24 Case Number | RTPS | Defect Title | Severity/Priority | ACI Status | Planned Delivery Date | Comments | Assignee
x | 03711383 | MPA new Lines | H24-658385 | RTPS-107058 | Reverse Posting for Functional cancel doesn't happen for Bank Adapter/Manual Create messages for Transact accounts | Major | Closed | 2026-02-10 | Feb 12 Tejas update ticket and add the comments Feb 10 Same status finalized Feb 09 Sai confirmed that finalized pending update the ticket. Feb06 ready for test Feb 05 Tejas confirm still pending to start testing(jean need to confirm on this) Feb 04 Sail will ask jean code to start this test today Jean Harty added a comment - jan 26 analyzing these cancels. | Tejas
x |  |  |  |  | Feb 13 Code delivery [ Fix for Multiple lines + cancellation] | High | Closed |  | Feb 12 Madhavi confirmed is done. Oscar need to ask about the code Feb 11 Oscar will review on this with Sri. Feb 05 need discuss with Jean to send the ticket for snapshoot to bank | Oscar
x | 03786990 | New Requirement[ Direct Cover Scenario] | H24-692138 | RTPS-108203 | New Requirement[ Direct Cover Scenario] | High | In Progres |  | Feb 26 Oscar Sent the plan on this Feb 25 Oscar will comunicate to bank for April release Feb 24 today Sizing committe Feb 23 Oscar Sent mail to Jean on this waiting for Sizing Committe Feb 20 jean already advancing on this Feb 19 next step sizing committe due date. Feb 18 bank already sent the authorization next steps get time line for this Feb16 discuss on sizing comitte the hours to present to bank Feb 13 Oscar request help to Alex to get answer from Jean Feb 12 today meeting with jean to finalize budget on the hours to send mail to bank Feb 11 Oscar request hour to jean to get the bank authorization Feb 10 Bank already share the test case Amit update the RTPS next step sizing committe Feb 09 Awaiting bank for test cases; Pending Sai comment advanced on this Feb 06 Phill need to check with Jean on this (SDD alredy had Oscar will share with Jean / Philp) Feb05 same status Feb 04 Feb 04 POC sai is advancing on this jan 29 Amit will advance in Solution Document, pending from bank requirement sign off
x | 03749089 | Interbank Settlement Requirement | H24-692138 | RTPS-106276 | Interbank Settlement Requirement-(Test 100 Cases) | Low | In Progres | 2026-02-15 | Feb 26 Tejas completed (11) , Sai outbound are blocked.(Siva is working on this) Feb 25 Tejas completed 9 / Sai (5) start today. Katheeja (2) Feb 24 require to split only 2 tester Feb 23 Tejas (7) Sai (5) Katheeja(2) Feb 20 Tejas can continue (siva confirmed) / Katheeja same as tejas / Sai (5) Feb 19 Tejas issue duplicate / Katheeja similar issue tejas / Sai need align with UP Feb 18 Tejas confirm 5/ 14, Sai base cases (need complete flow); katheeja need prepare messages to start (posting and revertion) Feb 17 Sai credit-payment - start issue need check with Philp,/ Tejas started 2/14 cases // Katheeja will start today. Feb 16 Sai already update the cases, check the env. Feb 13 Sai review 56 functional cases will split between team Feb 12 initial assigned to Katheeja, but need to split in the team Feb 11 we will start the testing but this will be deliver to bank on march release Feb 09 ready for test will be get for new sprint Feb 06 same status feb 05 Feb 05 Jean update ticket as resolved .. Need to know next steps Feb 04 in progress by jean Include release end March | Sai / Tejas
x | 03785698 | Other Cases | H24-723416 | RTPS-108880 | SSC¦ MTS¦ FED Payments incorrectly routing through CHP | Minor | In Progres |  | Feb 26 Tejas will work on this on Domestic Area Feb 24 Request a Call with bank an Philp to explain on this Feb 23 Dec-Spack new fuctionality. PCS need to inform to bank on this (configuration) Feb 20 Katheeja will send mail to bank (additional functionality dec -service pack) Feb 19 Katheeja today will discuss today SME Feb 18 Katheeja sent mail to bank / (need to discuss with PhilP) today based on tbank answer Feb 17 recreated and will discuss on this with Philp today Feb 16 Katheeja will create RTPS To discuss with Philp tomorrow Feb 13 Bank provide addtional information, Katheeja need to send mail to clarify before next steps Feb 12 Bank will test in his enviroment.Katheeja will update the ticket Feb 11 Katheeja , sent mail and update the ticket. issue is base on the source not the release version. Feb 09 Katheeja, not possible to check in sept- service pack. Need tos comment to SME meeting. Feb 06 Philp will change in the rules. Feb 05 Katheeja already recreate the issue. (SSI) create RTPS Feb 04 Katheeja start recreation found TRAPs | Tejas
x | 03757393 | Target Cases | H24-699336 | RTPS-107959 | Outbound PACS009 with Receiver/Cdtr Agt - BCITITMMXXX is routed to EXCQ due to TGT Channel Derivation issue. | Major | Closed |  | Feb 24 closed Feb 20 closed pending Tejas Update RTPS Feb 19 same status Feb 18 waiting testing by bank (Tejas update ticket) Feb17 same status feb16 Feb 16 already Tejas suggest 2 changes to bank (waiting bank response) Feb 13 Tejas required to update on this Feb 12 Tejas update H24. will and send mail update RTPS with SME conclusion, (is data issue/ bank need to correct the payment) Feb 11 Tejas recreate, today will be presented to SME. Feb 10 no replay from bank, Tejas will re- send the mail to bank to request this information Feb 06 Tejas confirm that work find, will send bank asking what bank is using this data Feb 05 Tejas partially recreate Amit suggest change the account to test it. Feb 04 Tejas will recreate, with the information received by bank Jan 29 recreate to review with Philp | Tejas
x | 03757391 | Target Cases | H24-699334 | RTPS-107894 | ACK TRN's are not received in MTS and matched with original outbound transaction | Major | Open |  | Feb 26 Siva sent mail to bank / bank request discuss on this today standup ( RISK this is product issue) Feb 25 Today meeting with Joe (Prod) to discuss on this Feb 24 bank bring the documents (swift) Siva will update on this.address mail to Product( Joe) Feb 23 PCS will present to Triage today / addtional Siva is looking how to recreate with Swift messages Feb 20 Bank already reply on this Feb 19 Tejas will update Feb 18 invite today to discuss on this Feb 17 wait Ashutosh answer on this Feb 16 Tejas will send mail to ashutosh to request the epic/storie (product) number of this change Feb 13 pending Tejas action on this Feb 12 Tejas require live env for swift to test it.(target swift epic/story number where) Feb 11 tejas send mail to clarify that the system work as is designed. bank require a meeting to discuss on this today at end of standup Feb 10 invite sent to 10 am with Joe / Tejas will update ticket and send mail to bank Feb 06 Tejas sent mail to bank check swift, now banking is asking ACI (Tejas will update the ticket) Feb05 Tejas review info from bank , it's not recreate yet. Need discuss with Philp. Feb 04 Tejas received data from bank will update and review with Paul on this Jan 29 recreate to review with Philp | Tejas
x | 03787561 | Inquiry | H24-725111 |  | handling of drawdown messages for Fedwire(looking for ISO messages) | Minor | Awaiting Customer action |  | Feb 25 bank request more time to review it internally Feb 24 Will ask bank to close Feb 23 Amit will answer today to Matt Feb 20 Matt from bank reply .. Amit will review it for next steps Feb 19 Amit sent mail . Bank is checking on this to close Feb 18 Amit will update the ticket Feb 17 same status feb 13 Feb 13 Amit is working on this Feb 11 Amit will review today on this | Amit
x | 03775326 | Other cases | H24-714233 | RTPS-106921 | CHAPS-LEI is not retained in the credit payment text where its mandatory for the regulations | Major | Closed |  | Feb 18 RTPS was created will RTPS-109003 Feb 16 not testing is requiring from PCS Feb 13 Nancy comment to Sai they testing in Services Area. waiting for env for PCS to do this testing (15 cases) Feb 12 Sai check with Nancy on this Feb 11 the bank is agree on the solution proposed by Amit, sail update the ticket ( this maintaint open until internal testing) Feb 10 Amit will send mail to bank on this its better to sen Feb 09 Oscar Will answer Charayna (PCS) need review more internally before product call. Feb 06 After today meeting with Saumya, next steps call to Joe C and send mail to bank on this (sai) Feb 05 Sail will update the ticket H24, and will check with developer. Oscar arrange the call tomorrow 8 am Feb 04 After feb 03 meeting with the bank the bank comment that with june 25 is working . | Sai
x | 03779477 | UPF | H24-717875 |  | Control Center December Service Pack Installation Errors | High | Awaiting Customer action |  | Feb 26 Paul request close the ticket - open a new one Feb 25 request confirm bank status on today standup Feb 24 Oscar Sent mail to Mayjane request close this cases Feb Paul will request close this Feb 20 pending bank answer on this Feb 19 CC is not working , still in progress. Feb 18 Aci in progress Feb 17 Aci internal review on this Feb 16 Bank update ticket (Manjula) Paul will review on it Feb 13 Paul will request close this next Feb 11 the same status Feb 10 Feb 10 Siva will update the ticket and send request to bank Feb 09 Siva will review on this and support to bank on this Feb 06 Bank will test it , next steps wait for Bank comments on this. Feb 05 Bank insist they have version mq-client different that ACI recommend, Paul will escalate this | Paul
x | 03785698 |  | H24-723416 | RTPS-67069 | SSG - modify NON_BUSINESS_DAY_EDIT to allow for Sunday processing | Minor | Closed |  | Feb 18 after LEI continue this Feb 17 Sail will test on this Feb 13 Sai will close Feb 11 Sai review with Jean not testing required, Sail will update the ticket Feb 10 Sail will recreate on it Feb 09 Sai will check with Jean Feb 06 open by jean to test by PCS | sai
x |  |  |  | RTPS-108560 | SSB - FED ISO - Inbound PACS004 routing into Exception Queue | High | Closed |  | Feb 25 tejas will close and update RTPS case Feb 24 Tejas will send mail to bank this work fin Feb 23 Tejas will check on this today Feb 20 Philp suggest load PAC004 correctly. Tejas test internally next step update ticket and send mail Feb 19 today will discuss SME Feb 18 same error-internal issue Feb 17 Neethu will try using Amit instruction. Feb 16 same status Feb 13 Neethu need to complete this PACS004 test Feb 12 Philp update route, still fail,(require test to check is an issue) Feb 11 Neethu create this new ticket to discuss with SME today | Tejas
| 03772878 |  |  |  | RITS Outbound PACS009X |  |  |  | Feb 13 this is in streech
| 03767600 |  |  |  | Lynx outbound PACS |  |  |  | Feb 13 this is in streech
x | 03748411 | Target Cases | H24-691549 | RTPS-85173 | Ent ISO - Target2 - Inbound CAMT025 Receipt not mapping with Outbound CAMT050 Liquidity Credit Transfer message | High | Ready for Dev | 2026-03-30 | Feb 05 same status feb 04 Feb 04 release for march Develope Prod assgned | Mamatha Govindaraju
x | 03757439/'03757445 | Target Cases | H24-699371/H24-699374 | RTPS-106930 | Outbound CAMT050 MX Message - SAA Header Section populated with incorrect values under certain data elements. | High | In Progres |  | Feb 25 Product confirm that this message is pass thru . waiting for bank confirmation Feb 24 Sail send mail to bank comments of ACI (dev) Feb 11 sail comment he will test it in dev area. Feb 10 ticket mark as resolved (Sail will check with dev) Feb 09 in turn 10 Jason H Feb 06 in turn 11 Jason H Feb 04 already scalate with Stephanie Jan 29 Jason H assign 16 site in development | Padmasri Mudugonda
x | 03789209 | raised for AUX LEI addition - Process TRAP issue | H24-726569 | RTPS-109003 | AUX_MAIN process is getting trapped when user tries to add LEI value to BOFAGB22 which is already linked with another different Branch BIC - BOFAUS3N. Related with this '03775326 | High | Open |  | Feb 26 Bank will create new ticket , Feb 25 After yesterday meeting bank resolved cases but still apper new ones Feb 24 Sal will test today (sai comment) Feb 23 Sai will review sai / or Scott proposal Feb 20 the same status feb 19 Feb 19 Sail will review recomendation for other ACI -Sai this is connected with LEI | sai
x | 03787642 | WebUI WebSphere Upgrade Issues | H24-725180 |  | MTS - WebUI WebSphere Upgrade Issues (contact Janet Zirpolo) |  |  |  | Feb 26 we have internal meeting with Bill, Feb 25 Feb 25 today work session with bank (bill p) Feb 24 same status feb 23 Feb 23 request meeting with bank and Bill P Feb 19 Today call with bill P to discuss on this Feb 18 Oscar sent mail to Janet . Se recomed meeting with Bill P | Oscar
x |  | Inquiry |  |  | Compatability of old UPF version with March SP |  |  |  | Feb 25 waiting Amy H answer Feb 24 . Oscar will answer Amy H on Amit mail waiting for her answer Feb 23 Amit sent mail to Amy H waiting her answer on this feb 20 amit sent mail to stephen
x |  | Inquiry |  |  | 2. UPF fix for Duplicate issue should be ported to future releases March SP |  |  |  | Feb 25 will send mail to bank today Feb 24 Amit will answer to Venkata on this Feb 23 will be giving in march sp. Amit will confirm this to bank Feb 20 Oscar sent invite with Peter Lee
x |  | Inquiry |  |  | 3. Mayjane : Camt.050/Camt.025/head.04 version change in March SP |  | Close |  | Feb 24 Feb 23 Amit already sent mail to bank Feb 20 Sail will check onthis
x | 03711383 | MPA bank asking | H24-658385 |  | New Transaction Codes for SSB for Internal Book transfers |  | Open |  | Feb 25 Tejas will Close and update this case Feb 24 Tejas will update Document and ticket Feb 23 Tejas was assign question by bank on this
x | 03776524 |  | H24-715261 | UPF-58751 UPF-58746 |  |  | Open |  | Siva