## Sheet1
State Street Bank Sprint 26 Feb 26 - Mar 12
| Case Number | Project | H24 Case Number | RTPS | Defect Title | Severity/Priority | ACI Status | Planned Delivery Date | Comments | Assignee
x | 03749089 | Interbank Settlement Requirement | H24-692138 | RTPS-106276 / RTPS-109565 | Interbank Settlement Requirement-(Test 100 Cases) | Low | In ProgresS | 2026-02-15 | Mar 12 Jean bring solution for this blocker. Mar 10 Tejas 27 completed. / Sai pending Jean fix inbounce. ( Mar 10 Tejas 2 pending ask to bank also review internally / Sai review with Philp cutoff is working as / the outbound Mar 9 Tejas 2 cases pending, (58) Sai 9 cases / inbound need to test it / review cutoff scenarios Mar06 Tejas (25) 2 pending / Sai still with issues to complete E-E test. Mar 04 Tejas (20) , Sai blocked waiting Siva Mar 03 Sai still payments not reach MTS. Mar 02 Sai will advance today (Siva already solve the oubound issue) Feb 27 Tejas completed(13) , Sai (5) Feb 26 Tejas completed (11) , Sai outbound are blocked.(Siva is working on this) Feb 25 Tejas completed 9 / Sai (5) start today. Katheeja (2) Feb 24 require to split only 2 tester Feb 23 Tejas (7) Sai (5) Katheeja(2) Feb 20 Tejas can continue (siva confirmed) / Katheeja same as tejas / Sai (5) Feb 19 Tejas issue duplicate / Katheeja similar issue tejas / Sai need align with UP Feb 18 Tejas confirm 5/ 14, Sai base cases (need complete flow); katheeja need prepare messages to start (posting and revertion) Feb 17 Sai credit-payment - start issue need check with Philp,/ Tejas started 2/14 cases // Katheeja will start today. Feb 16 Sai already update the cases, check the env. Feb 13 Sai review 56 functional cases will split between team Feb 12 initial assigned to Katheeja, but need to split in the team Feb 11 we will start the testing but this will be deliver to bank on march release Feb 09 ready for test will be get for new sprint Feb 06 same status feb 05 Feb 05 Jean update ticket as resolved .. Need to know next steps Feb 04 in progress by jean Include release end March | Sai / Tejas
x | 03787642 | WebUI WebSphere Upgrade Issues | H24-725180 | RTPS-109499 | MTS - WebUI WebSphere Upgrade Issues (contact Janet Zirpolo) |  | In Progress |  | Mar 12 same status but was scalted to Step Mar 11 Oscar will send mail to Step to push this issue Mar 10 Jason change the RTPS still waiting assign dev Mar 09 the same status Oscar need to send additional comment to Step Mar 06 Oscar will scalate with Stephanie Mar 05 Oscar will send message to Joe C Mar 04 already presented to Joe yesterday . next step Prod assign a dev to review logs on this Oscar insist on this with Joe C in the ticket Mar 03 Amit already recreate Sail will create RTPS tomorrow will present in War room Mar 02 require review Bill P mail (sai) Feb 27 Next steps bill P installation on Monday. Feb 26 we have internal meeting with Bill, Feb 25 Feb 25 today work session with bank (bill p) Feb 24 same status feb 23 Feb 23 request meeting with bank and Bill P Feb 19 Today call with bill P to discuss on this Feb 18 Oscar sent mail to Janet . Se recomed meeting with Bill P | Sai
|  | Inquiry | HKICL RTGS Dual Network Channel Requirement |  |  |  | Jan 19 Mayjane replayed that bank is analyzing on this will confirm at the end of jan | Amit | Mar 02 Oscar will confirm to bank this need to manage directly with Stephanie Feb 27 Ask Dolores next steps on this | Oscar
x | 03791310 | June SP - All CHATS Outbound | H24-728430 | RTPS-109766 | All CHATS Outbound messages routed to BIS_EXCQ due to BANK-INF MUST HAVE /SPRO/NN OR /CATPURP/IFTNN FOR HKL PAYMENT |  | In Progress |  | Mar 12 Tejas already recreate, next steps ask bank what specific test case the need Mar 11 Bank already answer. Tejas require to recreate as bank mail Mar 10 Tejas sent mail to bank / updated H24 Mar 09 received mail from bank / Process issue june service patch. (samples probably the problem) Mar 06 Tejas already sent mail to bank Mar 05 Tejas already create one scenario Mar 04 Tejas will review an recreate on this. 3/2/2026 | Tejas
x | 03791032 | Inquiry - Need info on PRULES throug | H24-728182 |  | Inquiry - Need info on PRULES through which Value date of Outbound payments are handled during US holidays |  | Close |  | Mar 04 Amit will close and update the ticket *resolved Mar 03 Amit already update the ticket pending Bank answer. Mar 02 Amit will send today the mail to bank Feb 27 Amit request bank more info | Amit
x | 03791311 | Inquiry Need suggestion on how to add |  |  | Inquiry - Need suggestion on how to add a new Service Code for Target2 Outbound CAMT050 messages that are meant for CLM service |  | Close |  | Mar 02 Silvia (Bank) request put this on hold (backlog) Feb 27 Amit request bank more info (bank request put in backlog) | Amit
x |  | Inquiry Structured Address & ISO Strategy |  |  |  |  | Out Scope PCS |  | Mar 11 same status Mar 10 same status Mar 06 same status Mar 05 this is Stephanie and Bank is in dicussion on this Mar 04 Discussion bank and ACI sales Mar 03 Oscar will insist on this with Marc Mar Oscar will send mail to Marc J to request information Feb 27 ACI James is working on this | Oscar
x | 03791307 | Incoming CBPR+ PAIN.001 translated to PAIN.013 | H24-728427 |  | Incoming CBPR+ PAIN.001 translated to PAIN.013 Drawdown Fedwire Outbound message - Dbtr Acct mapping issue |  | Close |  | Mar 03 This functionality Drop-down will be on march. This still is implementation.(keep on hold) until is release by product Mar 02 Amit will review this ticket and update Feb 27 Amit will review on this} | Amit
x | 03775326 | CHAPS outbound PACS008/009/009COV MX | H24-714233 | RTPS-109565 | CHAPS Outbound PACS008/009/009COV MX Messages RTPS is not persisting the LEI value in Incoming message text and not adding LEI for few data elements even when we have it in AUX via the Bank Directory Plus upload. |  | Open / Product fixing |  | Mar 12 Sai get issue (Deb-agent)pacs009, need to update ticket Mar 11 Sail is working on this testing. Mar 10 same status yesterday Mar 09 Sail will test it Mar 04 Sai will update the ticket Resolved awaiting customer (bank asking when is ready to test Mar 03 Bank already test it(Silvia ) will confirm and close it. Mar 02 same status Feb 27 Feb 27 banking is reviewing internally | Sai
x | 03789209 | AUX_MAIN process is getting trapped when user tries to add LE | H24-726569 | RTPS-106921 | Ready for Delivery |  | Close |  | Mar 05 Sail will update the ticket Mar 04 Bank ok to close Mar 02 same status Feb 27 Feb 27Banking is testing on this . Waiting bank confirmation | Sai
x | 03791308 | CHAPS outbound PACS008 | H24-728428 |  | CHAPS Outbound PACS.008 payment with Instructed Agent BIC - BOTKGB2LXXX is being replaced by BIC - NWBKGB55XXX |  | Close |  | Mar 03 Bank confirmed they are good to close it Mar 02 Sal will send mail to bank about this and wait bank comments to close | Sai
x | 03767600 | Lynx Tickets | H24-707712 | RTPS-109890 | Lynx outbound PACS (Lynx /Chat / Chaps) Outbound PACS009 omitting Dbtr Agt) |  | In Progress |  | Mar 12 Product agree that is a defect / also Sai said is working was solved dec25 / Sail will ask bank to review on this to close this issue Mar 11 with comments by bank go to Warroom again. to discuss on this Mar 10 Sai sent mail to bank this work as as it. / wating bank answer Mar 09 will present in today WAR room (clear defect) Mar 06 recreate for linx and chaps will create RPTS Mar 05 Sail require to recreate for chap and chat (outbound deb agent is not carry over) Mar 04 Sail will review on this today | Sai
x | 03772878 | Strech |  |  | RITS Outbound PACS009X |  | Strech |  | 2020-03-04 | PCS
x | 03785698 | Other Cases | H24-723416 | RTPS-108880 | SSC¦ MTS¦ FED Payments incorrectly routing through CHP | Minor | Awaiting Customer Comments |  | Mar 12 same status Mar 11 same status Mar 10 same status yesterday (put on hold) Mar 09 Bank still in internal testing /(PCS already did the information) Mar 06 Tejas will send mail to bank on his Mar 05 still same status Mar 04 Mar 04 Bank is testing on this Feb 27 Philp already did changes , waiting bank clarification to schedule call Feb 26 Tejas will work on this on Domestic Area Feb 24 Request a Call with bank an Philp to explain on this Feb 23 Dec-Spack new fuctionality. PCS need to inform to bank on this (configuration) Feb 20 Katheeja will send mail to bank (additional functionality dec -service pack) Feb 19 Katheeja today will discuss today SME Feb 18 Katheeja sent mail to bank / (need to discuss with PhilP) today based on tbank answer Feb 17 recreated and will discuss on this with Philp today Feb 16 Katheeja will create RTPS To discuss with Philp tomorrow Feb 13 Bank provide addtional information, Katheeja need to send mail to clarify before next steps Feb 12 Bank will test in his enviroment.Katheeja will update the ticket Feb 11 Katheeja , sent mail and update the ticket. issue is base on the source not the release version. Feb 09 Katheeja, not possible to check in sept- service pack. Need tos comment to SME meeting. Feb 06 Philp will change in the rules. Feb 05 Katheeja already recreate the issue. (SSI) create RTPS Feb 04 Katheeja start recreation found TRAPs | Tejas
x | 03757391 | Target Cases | H24-699334 | RTPS-107894 | ACK TRN's are not received in MTS and matched with original outbound transaction | Major | Open |  | Mar 12 Waiting for bank SCB answer. Mar 11 after (meeting witH SCB) internal meeting with Stephanie for next steps Mar 10 meeting today with Joe / step/ siva (next steps check others ntc, scb) after go bank answer. Mar 09 meeting today with Step for next steps Mar 06 Siva will response to developer. Mar 05 Siva Update RTPS to clarify (Samuya R) / Update 25 turn. / Tejas Will update ticket today Mar 04 Developer request documentation Mar 03 already scalate to Stephanie, and Joe, waiting next steps and due date on this. Marc 02 Oscar already sent mail to Stephanie to scalation to product (product need to create story) ( Oscar review news by Stephanie today) Feb 27 Feb 26 Siva sent mail to bank / bank request discuss on this today standup ( RISK this is product issue) Feb 25 Today meeting with Joe (Prod) to discuss on this Feb 24 bank bring the documents (swift) Siva will update on this.address mail to Product( Joe) Feb 23 PCS will present to Triage today / addtional Siva is looking how to recreate with Swift messages Feb 20 Bank already reply on this Feb 19 Tejas will update Feb 18 invite today to discuss on this Feb 17 wait Ashutosh answer on this Feb 16 Tejas will send mail to ashutosh to request the epic/storie (product) number of this change Feb 13 pending Tejas action on this Feb 12 Tejas require live env for swift to test it.(target swift epic/story number where) Feb 11 tejas send mail to clarify that the system work as is designed. bank require a meeting to discuss on this today at end of standup Feb 10 invite sent to 10 am with Joe / Tejas will update ticket and send mail to bank Feb 06 Tejas sent mail to bank check swift, now banking is asking ACI (Tejas will update the ticket) Feb05 Tejas review info from bank , it's not recreate yet. Need discuss with Philp. Feb 04 Tejas received data from bank will update and review with Paul on this Jan 29 recreate to review with Philp | Siva / Teja
| '03776524 | Inquiry | H24-715261/ H24-729422 | UPF-58751 UPF-58746 | 2. UPF fix for Duplicate issue should be ported to future releases March SP |  | In Progress |  | Mar 12 siva will review on this Mar10 same status Mar 09 Siva will close it today Mar 06 Siva tracking on this Mar 05-Issue reported in 5.0.4-21 -->Fix is in 5.0.4.34(Isolated patch on top of UPF code base 5.0.4.21) Mar 03 Amit will create H24 ../H24-729422 Mar 02 Amit will create H24 ticket and assign to SIva Feb 27 request tracking by Siva (assure that this will be on march sp) Feb 25 will send mail to bank today Feb 24 Amit will answer to Venkata on this Feb 23 will be giving in march sp. Amit will confirm this to bank Feb 20 Oscar sent invite with Peter Lee | Siva
|  | Inquiry |  |  | Compatability of old UPF version with March SP |  | Close |  | Mar 03 Venkat answer mail on this Mar 02 Amit will send question to Prod for additional question Feb 25 waiting Amy H answer Feb 24 . Oscar will answer Amy H on Amit mail waiting for her answer Feb 23 Amit sent mail to Amy H waiting her answer on this feb 20 amit sent mail to stephen | Amit
| 03791559 | UPF Case | H24-728664 |  | [H24-728664] Exceptions in RFMLSync even after App startup - IT GoJira |  | In Progress |  | Mar 12 waiting Bank for working session. Mar 11Bank sent information Paul is review on it. Mar 10 bank answer but need to share the logs.(waiting from bank) Mar 09 waiting bank answer Mar 06 Paul had meeting with bank (connection issues) request correction to bank. (request answer by bank) Mar 05 Paul sent update and waiting bank answer. Mar 04 Paul will request a meeting to close Mar 03 Paul sent request for the parameter to the bank to review it. Mar 02 Bank Open new ticket on this | Paul / Siva
|  | Inquiry by Bank May (Rundra Rajeshwar) |  |  | It would be helpful for us to understand what changes or features are added as part of UPF / MTS Feb 2026 Config Express Patch deliverables. We won’t be able to see release notes without installation. If you can get it from product or software delivery team then it will help us to understand new changes |  | Close |  | Mar 09 Oscar sent sri comment to bank Mar 06 Oscar sent mail to bank on this Mar 05 Oscar will update tickets created by this release and ask on this | Oscar
| 03792620 | Inquiry | H24-729594 |  | Structured Address & ISO Strategy - ACI availability timeline for the CUSTOM COMPLIANCE SERVICE |  | In Progress |  | Mar 11 pending meeting step / bank also will make update in the documents to request Amit
| 03793933 | Strech - Domestic | H24-730755 |  | RPH-US RTPS : Camt054 DEBIT/CREDIT Notifications generated from MTS component is having InstrID tag incorrect value |  |  |  | Mar 12 Siva will schedule meeting to review this issue
| 03793397 | Target2 CAMT050 - Add Receiver DN in SAA header specific to Target2 Service (RTGS/CLM) based on AppHdr BIC & Dbtr Acct number | H24-730268 |  | Target2 CAMT050 - Add Receiver DN in SAA header specific to Target2 Service (RTGS/CLM) based on AppHdr BIC & Dbtr Acct number |  |  |  | Mar 12 internal meeting we had yesterday/ Tejas update ticket and request the expectation.