## Sheet1
State Street Bank Sprint 27 Mar 12 - Mar 26
| Case Number | Project | H24 Case Number | RTPS | Defect Title | Severity/Priority | ACI Status | Planned Delivery Date | Comments | Assignee
x | 03787642 | WebUI WebSphere Upgrade Issues | H24-725180 | RTPS-109499 | MTS - WebUI WebSphere Upgrade Issues (contact Janet Zirpolo) |  | In Progress |  | Mar 25 Tejas will create war file update ticket RTPS Mar 24 next steps experts Mar 23 Gopa (dev) request H24 create War file to test Mar 20 Oscar Insist with Saumya Mar 19 Oscar will send message to Saumy R to assign dev on this Mar 18 Oscar send message to Saumya R to advance on this (because de devloper cann't recreate it) Mar 17 Developer start the review and Amit clarify the version. Mar 16 in progress turn 27 Mar 12 same status but was scalted to Step Mar 11 Oscar will send mail to Step to push this issue Mar 10 Jason change the RTPS still waiting assign dev Mar 09 the same status Oscar need to send additional comment to Step Mar 06 Oscar will scalate with Stephanie Mar 05 Oscar will send message to Joe C Mar 04 already presented to Joe yesterday . next step Prod assign a dev to review logs on this Oscar insist on this with Joe C in the ticket Mar 03 Amit already recreate Sail will create RTPS tomorrow will present in War room Mar 02 require review Bill P mail (sai) Feb 27 Next steps bill P installation on Monday. Feb 26 we have internal meeting with Bill, Feb 25 Feb 25 today work session with bank (bill p) Feb 24 same status feb 23 Feb 23 request meeting with bank and Bill P Feb 19 Today call with bill P to discuss on this Feb 18 Oscar sent mail to Janet . Se recomed meeting with Bill P | Sai
x | 03749089 | Interbank Settlement Requirement | H24-692138 | RTPS-106276 / RTPS-109565/RTPS-110609 | Interbank Settlement Requirement-(Test 100 Cases) | High priority | In Progress | 2026-02-15 | Mar 25 Mar 24 issue RTPS(110609) we need to priorize this Mar 23 Tejas update the ticket finalized this test Mar 20 Tejas working on 6 cases pending is required finalize today Mar 19 Sai comment pending only (6) cases for inbound. Mar 18 Sai Complete (9/18) Chips ack not receive. Mar 17 Sai complete 6 will advance (3) pending clarity on description with Philp Mar 16 Sai review is working. Mar 12 Jean bring solution for this blocker. Mar 10 Tejas 27 completed. / Sai pending Jean fix inbounce. ( Mar 10 Tejas 2 pending ask to bank also review internally / Sai review with Philp cutoff is working as / the outbound Mar 9 Tejas 2 cases pending, (58) Sai 9 cases / inbound need to test it / review cutoff scenarios Mar06 Tejas (25) 2 pending / Sai still with issues to complete E-E test. Mar 04 Tejas (20) , Sai blocked waiting Siva Mar 03 Sai still payments not reach MTS. Mar 02 Sai will advance today (Siva already solve the oubound issue) Feb 27 Tejas completed(13) , Sai (5) Feb 26 Tejas completed (11) , Sai outbound are blocked.(Siva is working on this) Feb 25 Tejas completed 9 / Sai (5) start today. Katheeja (2) Feb 24 require to split only 2 tester Feb 23 Tejas (7) Sai (5) Katheeja(2) Feb 20 Tejas can continue (siva confirmed) / Katheeja same as tejas / Sai (5) Feb 19 Tejas issue duplicate / Katheeja similar issue tejas / Sai need align with UP Feb 18 Tejas confirm 5/ 14, Sai base cases (need complete flow); katheeja need prepare messages to start (posting and revertion) Feb 17 Sai credit-payment - start issue need check with Philp,/ Tejas started 2/14 cases // Katheeja will start today. Feb 16 Sai already update the cases, check the env. Feb 13 Sai review 56 functional cases will split between team Feb 12 initial assigned to Katheeja, but need to split in the team Feb 11 we will start the testing but this will be deliver to bank on march release Feb 09 ready for test will be get for new sprint Feb 06 same status feb 05 Feb 05 Jean update ticket as resolved .. Need to know next steps Feb 04 in progress by jean Include release end March | Sai / Tejas
x | 03772878 | Strech | H24-712114 |  | RITS Outbound PACS009X |  | Strech |  | 2020-03-04 | PCS
| 03792620 | Inquiry | H24-729594 |  | Structured Address & ISO Strategy - ACI availability timeline for the CUSTOM COMPLIANCE SERVICE |  | ACI Status |  | Mar 19 put on hold by stephanie (March 27) product release on this Mar 18 Amit require confirm with Stephanie before send the answer to the bank Mar 17 Amit will send mail to Stephanie next steps. Mar 16 waiting bank question on this Mar 11 pending meeting step / bank also will make update in the documents to request Amit
x | 03757391 | Target Cases | H24-699334 | RTPS-107894 | ACK TRN's are not received in MTS and matched with original outbound transaction | Major | Awaiting Customer action by bank |  | Mar 20 awaiting bank additional comments Mar 19 Siva sent additional infor required by bank(already tested by Tejas) Mar 18 Oscar sent mail to bank . now waiting bank confirmation to close this Mar 17 the draft is still in internal review to send to bank Mar 16 Oscar will send draft mail to discuss internally Mar 12 Waiting for bank SCB answer. Mar 11 after (meeting witH SCB) internal meeting with Stephanie for next steps Mar 10 meeting today with Joe / step/ siva (next steps check others ntc, scb) after go bank answer. Mar 09 meeting today with Step for next steps Mar 06 Siva will response to developer. Mar 05 Siva Update RTPS to clarify (Samuya R) / Update 25 turn. / Tejas Will update ticket today Mar 04 Developer request documentation Mar 03 already scalate to Stephanie, and Joe, waiting next steps and due date on this. Marc 02 Oscar already sent mail to Stephanie to scalation to product (product need to create story) ( Oscar review news by Stephanie today) Feb 27 Feb 26 Siva sent mail to bank / bank request discuss on this today standup ( RISK this is product issue) Feb 25 Today meeting with Joe (Prod) to discuss on this Feb 24 bank bring the documents (swift) Siva will update on this.address mail to Product( Joe) Feb 23 PCS will present to Triage today / addtional Siva is looking how to recreate with Swift messages Feb 20 Bank already reply on this Feb 19 Tejas will update Feb 18 invite today to discuss on this Feb 17 wait Ashutosh answer on this Feb 16 Tejas will send mail to ashutosh to request the epic/storie (product) number of this change Feb 13 pending Tejas action on this Feb 12 Tejas require live env for swift to test it.(target swift epic/story number where) Feb 11 tejas send mail to clarify that the system work as is designed. bank require a meeting to discuss on this today at end of standup Feb 10 invite sent to 10 am with Joe / Tejas will update ticket and send mail to bank Feb 06 Tejas sent mail to bank check swift, now banking is asking ACI (Tejas will update the ticket) Feb05 Tejas review info from bank , it's not recreate yet. Need discuss with Philp. Feb 04 Tejas received data from bank will update and review with Paul on this Jan 29 recreate to review with Philp | Siva / Teja
x | 03791307 | Incoming CBPR+ PAIN.001 translated to PAIN.013 | H24-728427 |  | Incoming CBPR+ PAIN.001 translated to PAIN.013 Drawdown Fedwire Outbound message - Dbtr Acct mapping issue |  | Awaiting Customer action by bank |  | Mar25 check with the bank this will be moved to backlog 'Mar 24 same status 'Mar 20 same status Mar 19 'Mar 19 Amit sent this mail (waiting bank comments) Mar 18 March SP / Second part Amit will send mail with Ashutosh answer . Mar 17 Domestic Product(Ashutosh) comment March 26 / Amit will respond on this 'Mar 16 Bank ask on this point is possible to include in Jan26- ACI(Ashutosh) not possible.- Amit will answer to bank to this 'Mar 03 This functionality Drop-down will be on march. This still is implementation.(keep on hold) until is release by product Mar 02 Amit will review this ticket and update Feb 27 Amit will review on this} | Amit
x | 03791310 | June SP - All CHATS Outbound | H24-728430 | RTPS-109766 | All CHATS Outbound messages routed to BIS_EXCQ due to BANK-INF MUST HAVE /SPRO/NN OR /CATPURP/IFTNN FOR HKL PAYMENT |  | In Progress |  | Mar 25 Oscar need to replay to Barbara H for who in APEX can be contact for this. / Amit will comment to bank on this. Mar 24 Stephen R comment we need to present to Barbar H probably DM is required. Mar 23 Tejas will present to Product today (again) custom change Mar 20 Tejas send message and Bank(Silvia) replay to discuss something new. Mar 19 Tejas sent comment by Product. them Silvia comments : Mar 18 Bank provide messages to continue the test (to present to Product) Mar 16 waiting mail bank expectation to advance on this (ON HOLD) Mar 12 Tejas already recreate, next steps ask bank what specific test case the need Mar 11 Bank already answer. Tejas require to recreate as bank mail Mar 10 Tejas sent mail to bank / updated H24 Mar 09 received mail from bank / Process issue june service patch. (samples probably the problem) Mar 06 Tejas already sent mail to bank Mar 05 Tejas already create one scenario Mar 04 Tejas will review an recreate on this. 3/2/2026 | Amit
x | 03767600 | Lynx Tickets | H24-707712 | RTPS-109890 | Lynx outbound PACS (Lynx /Chat / Chaps) Outbound PACS009 omitting Dbtr Agt) |  | Resolved awaiting customer acceptance |  | Mar 25 this is not issue in our enviroment. bank / Sai will update H24 ticket Mar 24 Sai will need RTPS To fix this issue (bring to warroom) Mar 23 Sail will explain bank the versions Mar 20 Sai already test on jan SP is working Mar19 Sai will retest today (update ticket) Mar 18 Sai will retest on jan SP. after that next steps Mar 17 Oscar will send scalation with Bank justification Mar 16 Oscar will send the priorization to Stephanie ( pending reason) Sai Mar 12 Product agree that is a defect / also Sai said is working was solved dec25 / Sail will ask bank to review on this to close this issue Mar 11 with comments by bank go to Warroom again. to discuss on this Mar 10 Sai sent mail to bank this work as as it. / wating bank answer Mar 09 will present in today WAR room (clear defect) Mar 06 recreate for linx and chaps will create RPTS Mar 05 Sail require to recreate for chap and chat (outbound deb agent is not carry over) Mar 04 Sail will review on this today | Sai
| 03793397 | UPF | H24-730268 |  | Target2 CAMT050 - Add Receiver DN in SAA header specific to Target2 Service (RTGS/CLM) based on AppHdr BIC & Dbtr Acct number |  | Resolved awaiting customer acceptance |  | Mar 19 Bank is providing solution by themselves on this (backlog) Mar 18Same status Mar 16 waiting bank Mar 17 Same status Mar 16 waiting bank Mar 16 Waiting bank expectation from Silvia (The requirement has been amended, Silviya would be updating the ticket with the new requirement.) Mar 12 internal meeting we had yesterday/ Tejas update ticket and request the expectation. | Tejas
| 03792620 | Inquiry | H24-729594 |  | Structured Address & ISO Strategy - ACI availability timeline for the CUSTOM COMPLIANCE SERVICE |  | In Progress |  | Mar 11 pending meeting step / bank also will make update in the documents to request Amit
| 03793933 | Domestic | H24-730755 | RTPS-110282 | RPH-US RTPS : Camt054 /CREDIT Notifications generated from MTS component is having InstrID tag incorrect value |  | Slotting |  | Mar 19 product Slotting Mar 18 today will present in War room Mar 17 Discuss credit | Tejas
| 03793933 | Domestic | H24-730755 | RTPS-110270 | RPH-US RTPS : Camt054 DEBITNotifications generated from MTS component is having InstrID tag incorrect value |  | Slotting |  | Mar 19 product slotting Mar 18 this slotty Mar 17 Separate the deb / Cred Mar 16 Tejas sent mail to bank request information on this (created RTPS) Mar 12 Siva will schedule meeting to review this issue | Tejas
x | 03775326 | CHAPS outbound PACS008/009/009COV MX | H24-714233 | RTPS-106921 /RTPS-110269 | CHAPS Outbound PACS008/009/009COV MX Messages RTPS is not persisting the LEI value in Incoming message text and not adding LEI for few data elements even when we have it in AUX via the Bank Directory Plus upload. |  | Open / Product fixing |  | Mar 25 still is in development (waiting for release ) Mar 24 in devep are pending receiving in our area Mar 23 Saumya R will be ready March29 PCS will test. Mar 20 Oscar need to check with Soumya on this Mar 19 Oscar sent this mail to step Mar 18 request to scalate with Step Mar 17send mail to Stephany for support Mar 16 Oscar need to contact dev (Saumya R) how is the process on this to get his attention Mar 12 Sai get issue (Deb-agent)pacs009, need to update ticket Mar 11 Sail is working on this testing. Mar 10 same status yesterday Mar 09 Sail will test it Mar 04 Sai will update the ticket Resolved awaiting customer (bank asking when is ready to test Mar 03 Bank already test it(Silvia ) will confirm and close it. Mar 02 same status Feb 27 Feb 27 banking is reviewing internally | Sai
x | 03789209 | AUX_MAIN process is getting trapped when user tries to add LE | H24-726569 |  | AUX_MAIN process is getting trapped when user tries to add LE |  | Close |  | Mar 16 Bank Silva agree to close Mar 05 Sail will update the ticket Mar 04 Bank ok to close Mar 02 same status Feb 27 Feb 27Banking is testing on this . Waiting bank confirmation | Sai
x |  | Target Mandates March | H24- | RTPS-107184 - Target Market Mandates | RTPS-107074 Support new Target2 Message Versions for March Service Pack (June Go Live) |  | Progress |  | Mar 25 Amit will communicate to bank today (send mail) Mar 24 Request support by Stephanie on this Mar 23 Same Status Mar 20 same status waiting comments by Product (Amy H) Mar 19 Amit already sent mail to Amy H waiting her comment Mar 18 bank request this ported to Jan SP question to Amy H Mar16 Amit follow on this
x | 03791559 | UPF | H24-728664 |  | Exceptions in RFMLSync even after App startup |  | Awaiting Customer comment on this |  | Mar 25 Paul update the ticket with solution proposed / awaiting bank confirmation Mar 24 Mcast issue request to UPF SMEs Mar 23 Paul is working Mar 20 today Paul send invitation work session Mar 19 Paul found different error RFML waiting bank . Mar 18 Paul comment that is working
x | 03792406 | UPF Inquiry | H24-729422 | New | Duplication records on Dec issue(Fix inclusion in future UPF patches for SSC¦UPF¦Duplicate transaction processing in US Production |  | Awaiting Customer comment on this |  | Mar 25 Amit will send mail to bank / await bank response after that mail Mar 23 Siva will review on this Mar 20 waiting product Answer on this Mar 19 Amit will update the ticket
x | 03791559 | UPF | H24-728664 |  | Exceptions in RFMLSync even after App startup |  | Progress |  | Mar 20 Paul request working session bank
x |  |  |  | RTPS-110609 | Functional Return to Sender not working for SSI FED Inbound pacs009 and pacs009COV |  | Progress |  | Mar 25 Osca sent mail to Stephanie requiring Priorization / also will be present today in War room requesting assign developer Mar 24 request priorization by Stephanie also Tejas will update on this. | Tejas