## Handover Checklist
Customer Name: | State Street Bank |  | This spreadsheet will be used to document and track the handover process of projects for ALL PRODUCTS. | Standard (BAU) support
Customer Acronym: | SSB |  |  | CSM support
Support Model: | PCS support |  |  | PCS support
Project Name: | SSB Bank Adapter Global |  | 1. Make a copy of this spreadsheet and save it as "PRODUCT_NAME handover - CustomerName - ProjectName" | Solution Support
Product and Version: | MTS 6 /UPF |  |  | Managed Services
Project Manager Name: | Oscar Herrera Lizcano |  | 2. Complete all the yellow fields.
JIRA Project Link: | https://gojira.am.tsacorp.com/browse/SVCS-29201
Handover case number: |  |  | Right click on any tab and select UNHIDE, then select the Product this handover is for.
Sheet created on: | 2025-10-21
Handover Date:
Handover Checklist - To be validated and filled by HELP24 |  |  | Link to: Steps to Complete a Project Handover
The completion of the following steps will ensure a successful handover |  | STATUS | Link to: Project Handover Case Quick Reference Guide
Creation of the Project Handover Case |  | Completed | Link to: Handover Procedure site
Complete Internal Checkpoint One (Project Kickoff) |  | Pending
Complete Internal Checkpoint Two (Pre Go-live) |  | Pending | Pending
Complete task checklist (As appropriate, all tasks may not be required) |  | Pending | Completed
Complete Internal Checkpoint Three (Post Go-live) |  | Pending | Not required
Complete Customer Checkpoint Four (Customer handover) |  | Pending
Complete Closure of the Project Handover Case |  | Pending

## Checkpoints
Internal Checkpoint One (Project Kickoff) | Pending | ~ 7 days* from Project Start |  | *The length of time between the steps are variable and should be agreed upon by Matrix Team | Pending
Completed
This step requires completion of the following: |  | STATUS | Owner |  | Not required
Introduction to HELP24 on the complexities and components of the project |  | Not required | PM
HELP24 introduces the handover process and criteria |  | Completed | HELP24
PM to confirm Latest Service Pack or Current SP-1 will be used for Go-live |  | Pending | PM
Coordinate a meet and greet with the customer (depending on the project, not necessary for existing customers) |  | Not required | PM/HELP24
Internal Checkpoint Two (Pre Go Live) | Pending | ~ 14 days* Pre Go-live
This step requires completion of the following: |  | STATUS | Owner
Overview of the project and current status with an online review in Salesforce * Risks and outstanding issues * Review open cases |  | Completed | PM
Ensure Customer is going live with the Latest Service Pack or Current SP-1 |  | Completed | PM
Review status of checklists |  | Pending | HELP24
Review status of handover criteria |  | Pending | HELP24
Review Golive process (depending on the project, not necessary for existing customers) |  | Completed | PM
Review P1 processing and Rapid Response procedure (depending on the project, not necessary for existing customers) |  | Pending | PM
Review of customizations, CSMs etc or any other unique quality for a given project |  | Pending | PM/HELP24/AD
Set a target date for the Internal and Customer turnover |  | Pending | PM
Internal Checkpoint Three (Post Go Live) | Pending | ~ 14 days* Post Go-live
This step requires completion of the following: |  | STATUS | Owner
Review current status of the project with an online review * Validate all outstanding issues have been resolved * The system has been running stable. |  | Pending | PM
Review handover criteria |  | Pending | PM
Review all open cases and determine next steps |  | Pending | PM
Production Readiness review with customer was completed |  | Pending | PM
Discuss customer communication of any outstanding issues (including cases such a P3’s or P4’s.) |  | Pending | PM
Review account details in Salesforce for accuracy. * Validate a contact for the implementation survey. |  | Pending | PM
Schedule and confirm customer handover meeting. |  | Pending | PM
Customer Checkpoint Four (Customer Handover) | Pending | ~ 21 days* Post Go-live
This step requires completion of the following: |  | STATUS | Owner
Receive customers validation and acceptance of any outstanding issues. |  | Pending | PM
Introduction to the HELP24 team |  | Pending | PM/HELP24
Review of the HELP24 Overview presentation to assure understanding of processes, roles, responsibilities and implementation survey. May not be necessary for existing customers. |  | Pending | HELP24

## TaskChecklist
Task Checklist | Pending |  |  |  | Pending
Completed
The following tasks need to be completed by the project team and/or project manager prior to handover. All tasks may not be necessary for existing customers. |  |  |  |  | Not required
Standard tasks |  | STATUS | Owner | Timeline
Create a project case in Salesforce to track and document the completion of the HELP24 Handover process. |  | Completed | PM | Checkpoint 1
Create a new Handover sheet and add the link to the case comment. |  | Pending | PM | Checkpoint 1
Verify and update the customer Account in Salesforce. Review all information listed in the Salesforce account update section. For example, deactivate any contacts that have left the project and create new contacts as necessary. If there is an area you cannot update notify your the customer manager to assist. |  | Completed | PM | Checkpoint 3
Confirm that All Analysts have access to the Project Site defined under "Document Storage Link" under the SF Project Page. |  | Pending | PM | Checkpoint 2
Test WebEx between ACI and the customer. Is the customer able to join Webex meetings and sharing screens (without granting direct control) to work on P1, P2 and/or P3 cases? |  | Pending | PM | Checkpoint 2
Train customers on the use of eSupport portal to use for tracking and remaining current with fixes. Validate they have access and review how to determine if a fix is critical to their environment, the impacts of not taking a fix, etc. May not be necessary for existing customers. |  | Pending | PM | Checkpoint 2
Confirm customer is compliant with all Mandates (e.g. Interface, Regulatory, Network). |  | Pending | PM | Checkpoint 2
As the customer’s go-live approaches, confirm steps been taken to restrict remote access to their production environment, including the removal of all unnecessary remote login capabilities provided to ACI engineers, including all non-WebEx points of access? |  | Pending | PM | Checkpoint 2
Deliver and review the following customer communication guides prior to handover. HELP24 staff will participate should any questions arise. May not be necessary for existing customers * Delivery of the current ACI Customer Support Guide. |  | Pending | PM | Checkpoint 2
Review of P1 processing procedure. May not be necessary for existing customers |  | Pending | PM | Checkpoint 2
Review the eSupport Portal and all cases should be opened using this tool. P1 issues should be followed up with a call to the Priority 1 hotline. * The eSupport portal provides the customer the ability to search for existing solutions to known problems, view documentation and add notes and/or attachments to the case. Gives them access to all of the hotlines, documentation and critical fix notifications. |  | Pending | PM | Checkpoint 2
Create users to access eSupport and should be able to attach files and if they need to have permission to download deliveries. |  | Pending | PM | Checkpoint 2
The following information is required when opening a case: Customer name, contact name, phone, email address, product, module, release, version, priority and business impact. Please provide full international dialing instructions with the customer’s phone number. |  | Pending | PM | Checkpoint 2
Hours outside of normal business hours are for Priority 1 issues only. Issues that do not meet P1 criteria will be addressed the next business day. |  | Pending | PM | Checkpoint 2
Emphasize the importance of WebEx access for assistance in case resolution. |  | Pending | PM | Checkpoint 2
Inform the customer once live, the ability of ACI personnel to work directly in their production environment will be severely limited due to customer and ACI liabilities. |  | Pending | PM | Checkpoint 2
Review the project specifications and any customizations, warranties or other special processing. |  | Pending | PM | Checkpoint 2
Review cases and validate proper priority levels are used during the project. |  | Pending | PM | Checkpoint 3
Set customer expectations based on priority. Emphasize some differences with HELP24 and project for example, turnaround of cases in HELP24 may not be as timely as during the project phase. During the project, the customer has a full-time team dedicated to their support, while HELP24 must balance other high-priority customer cases. |  | Pending | PM | Checkpoint 3
If customer has contracted for ACI’s Enhanced Support Program (ESP), ensure the customer is aware of the parameters under which their time will be billed when the ESP resource is involved in case resolution. Typically, if HELP24 contacts the ESP for help (for example, questions regarding specifics of the customer’s system), that time will be billed to HELP24, but if the customer chooses to involve the ESP in case resolution directly, their time will be billed to their ESP hours. |  | Pending | PM | Checkpoint 3
If available document the Customer Escalation process. Provide the customer's internal escalation process and/or procedures with regard to high severity incident management so that HELP24 leadership and account teams can anticipate and be better prepared for potential customer escalation to ACI senior leaders. |  | Pending | PM | Checkpoint 3
For all handovers of new customers to HELP24, if they’re in a country ACI hasn’t previously served, please do the following: 1. Open a GSD ticket to ensure that IT-Voice adds support for a toll-free hotline number for that country, if available. This process can take several months to complete, so it’s important that it’s begun early in the project phase. 2. Contact Robert (Bobby) Mercer to have the new number added to the country-specific drop-down at https://www.aciworldwide.com/support . |  | Pending | PM | Checkpoint 3
Review support assumptions with customers. Support Assumptions: * When reporting incidents, the customer should review the problem and gather as much information as possible prior to opening a case. Customer representatives opening cases should be capable of gathering and transmitting the information necessary for HELP24 to research the issue (such as event messages, log files, UI screen captures, etc.). If they are not, they should contact qualified internal technical personnel who possess that ability to assess the issue. These technical personnel should then contact HELP24 if they are unable to resolve the problem themselves. * When a problem is reported to HELP24, support staff will often require the continued involvement of the customer’s technical contact(s) in order to resolve the issue. Our analysts and engineers will do everything within their power to research the issue from a product standpoint, but will not have the specific knowledge of the customer’s system. The customer is expected to give HELP24 access to an internal resource with that knowledge. * While VPN may sometimes be used by the project teams for remote access to the customer’s test system, it is never to be used in a production environment due to customer and ACI liabilities. If remote access to a customer’s production system is necessary, only WebEx is to be used. |  | Pending | PM | Checkpoint 3
Production Readiness review with customer was completed: * Customer has purchased the hardware ACI recommended based on the hardware sizing document provided during the initial implementation or most recent upgrade project * Customer has configured system in Production environment based on the recommendations from ACI as documented in the hardware sizing document * Customer has done an appropriate like for like test of Production volume and performance testing in a Non-Production environment * Customer has configured and enabled housekeeping procedure according to ACI product documentations. * Customer education and\or knowledge sharing about the project being implemented has occurred. |  | Pending | PM | Checkpoint 3
After successful customer handover, the HELP24 Manager or Lead will close out the project case and notify the Implementation survey team. |  | Pending | HELP24 | Checkpoint 3

## HandoverCriteria
Handover Criteria | Pending |  |  | Pending
Completed
This criteria was determined to be necessary to allow a handover of a stable system for ongoing support. A customer is considered ready for handover to HELP24 once their production system is live, their system has stabilized, reporting of new issues is infrequent, and the customer can be used as a reference. This criteria should be reviewed at the beginning of the project, at and all checkpoints leading to the handover to HELP24. It should be agreed upon by the project team, HELP24, AD and the customer. |  |  |  | Not required
Standard tasks |  | STATUS | Owner
No open P1 Cases |  | Pending | PM
Recommend no open P2 cases. Final disposition of P2 cases will be agreed upon with the vested team |  | Pending | PM
Recommend < 8 P3/4 cases. All other cases must be reviewed to determine who is responsible for working to completion. Final disposition of P3/4 cases will be agreed upon with the vested team |  | Pending | PM/HELP24
PM works with the customer to validate their understanding and agreement with the resolution of the cases and other outstanding issues |  | Pending | PM
All required tasks have been completed on the checklists |  | Pending | PM/HELP24
Other criteria |  | STATUS | Owner
Other criteria can exist as agreed by PM, AD & H24 Manager; recommend a review and discussion concerning reasonable number of open cases based on unique complexity of the project |  | Pending | PM/HELP24
PM responsible for minimizing open cases w/ customer prior to Handover to HELP24 |  | Pending | PM
Additional criteria & discussion required if customer has licensed SDK for own use or other process that require additional documentation or knowledge transfer to HELP24 |  | Pending | PM/HELP24

## OutstandingCases
Outstanding Cases - To be completed by PM
Case # | Contact | Priority | Create Date | Description | Status | Handover Comments
HELP24 Management approval required if the below thresholds are exceeded
Standard tasks
No open P1 Cases
Recommend no open P2 cases. Final disposition of P2 cases will be agreed upon with the vested team
Recommend < 8 P3/4 cases. All other cases must be reviewed to determine who is responsible for working to completion. Final disposition of P3/4 cases will be agreed upon with the vested team

## ProjectTeam
ACI Project Contact Details - To be completed by PM
Document the various ACI personnel involved in the project – include names, titles, project job roles, email addresses & telephone numbers where available. Confirm that the Clarity allocations for all active team members are up to date.
Contact Name | Contact Email | Contact Telephone | Team Role
Oscar Herrera Lizcano | oscar.herrera@aciworldwide.com | 573214838862 | Project Manager
Ajay, Amit | amit.ajay@aciworldwide.com |  | Architect
Contreras, Paul | paul.contreras@aciworldwide.com |  | Sr Technical UPF
Vemasani, Sai Kumar | saikumar.vemasani@aciworldwide.com |  | Technical Consultant
Parveen, Katheeja | katheeja.parveen@aciworldwide.com |  | Technical Consultant
Tarawade, Tejas | tejas.tarawade@aciworldwide.com |  | Technical Consultant
ACI Customer Success Manager / Client Services Director details / Software Delivery Manager - To be completed by PM
Contact Name | Contact Email | Contact Telephone | Team Role
Hegarty, Philip | philip.hegarty@aciworldwide.com | 13527201039 | Principal Solution Architect
Cox, Stephanie | stephanie.cox@aciworldwide.com |  | Dir Services
Customer Project Contact Details - To be completed by PM
Document the various customer personnel involved in the project – include names, titles, project job roles, email addresses & telephone numbers where available.
Contact Name | Contact Email | Contact Telephone | Team Role
Koppavolu, Venkata Kumar | vkoppavolu@statestreet.com |  | IT Delivery Manager
Yelgulwar, Tarun Balraj | tyelgulwar@statestreet.com |  | Technical

## BASE24-eps Specific Info (hidden)
ACI Test Environment Details - To be completed by PM
Please provide details on the following. Please note that not all fields may be relevant based on the project/product. |  |  |  |  | Please attach to Project or provide the location of a current copy of the customer’s system diagram and technical documentation regarding new functionality added during project phase.
ACI Product and Version |  |  |  |  | System Diagram
ACI Test network machine and location (include ESP networks):
ACI Logins and Passwords (Network and UI)
Simulator Test script location
Simulator Test script names
Synergy Baseline and Code thread
Jenkins Runstreams
Please provide the location of the following documents:
Test Validation Document (TVD): | Enter Link Here
Test master report | Enter Link Here
Maintenance and Support Plan | Enter Link Here
Additional Information about the Project - to be completed by PM
CSMed Interfaces require retrofit
[5 empty] | Channel | Customer Contact Name | BASE24-eps release | Full Service Pack | Interface | Module Id | IPF Refresh | Platform | Synergy Code Stream | Issuer/Acquirer/Both | Comments
Additional Information about the Project - to be completed by PM
ACI Product | Platform Name | Machine Type | Remote Access
BASE24-eps Tasks | [6 empty] | STATUS |  | Owner | Timeline
Configure CSM source code into the Pull Program. Check all project-modified code and scripts - both CSM and product – into Synergy if they're to be supported by HELP24. | [6 empty] | Pending |  | PM | Checkpoint 3 |  | Pending
All CSM and product cases from the project phase must be closed prior to handover. | [6 empty] | Pending |  | PM | Checkpoint 3 |  | Completed
CSMs must be not only resident in the production executable, but actively functioning for 30 days prior to handover. | [6 empty] | Pending |  | PM | Checkpoint 3 |  | Not required
Does this customer require Mandate retrofit or receive standard Mandate? If yes, please update the Mandate Retrofit List. https://aciww.sharepoint.com/sites/Global/team/gb24eps/SitePages/Mandate%20Retrofit%20Customers.aspx | [6 empty] | Pending |  | HELP24 | Checkpoint 3
Did the project involved CSMs developed by ACI on SDK? If yes, complete the SDK section below | [6 empty] | Pending |  | PM | Checkpoint 3
Pull configurations to be added to fetch the fix report for any CSM fix deliveries, if Project involves CSM code changes. A Sample FixReport is available on the location \\oma2swm01\shared_work_areas_writable\ccm_wa\shrd\UIcsm,sqa_2.0_MBB_3A_2\Uicsm | [6 empty] | Pending |  | PM | Checkpoint 3
CSMs development adhered to secure coding practices - Security Scanning Policy. If not, the handover cannot be accepted. | [6 empty] | Pending |  | PM | Checkpoint 3
Project Team need to provide the Pull ID details of the Product, CSM initial deliveries to confirm if those were done with Group of "swm_prod" user through "Delivery Request" option of Pull program. If these deliveries done correctly, the Pull's show as user "name" and Group "swm_prod". | [6 empty] | Pending |  | PM | Checkpoint 3
Perform a patch pull using the Stream name of the above Product Pull ID and review if patch CR's for that specific Service Pack are visible. If not, coordinate with Project team to either raise a SDRS official delivery or raise a GDM request to do an internal(Non-Distributed) pull through swm_prod user ID for that stream, version, and Service Pack. | [6 empty] | Pending |  | PM | Checkpoint 3
HELP24 Handover Lead to add the Product and CSM Pull stream names along with Pull ID Acryo from the above Pull(s) to customer info sheet under "Pull Configs" field. Acronym : HDFC Product: HDFC_RPS CSM: HDFC_3 | [6 empty] | Pending |  | PM | Checkpoint 3
Is the customer contracted to report capacity and pay capacity fees? | [6 empty] | Pending |  | PM | Checkpoint 2 | [5 empty] | Pending
If above is YES Ensure TBP process is configured and running successfully in Production before Go-Live | [6 empty] | Pending |  | PM | Checkpoint 2 | [5 empty] | YES
If the customer is contracted to report capacity: Ensure TBP report is running successfully and last month TBP report is provided. We’ll NOT take any exceptions approach to this in order to ensure there is no revenue gaps. | [6 empty] | Pending |  | PM | Checkpoint 3 | [5 empty] | No
If above is YES Update BSO Operations Team that the handover is completed by sending email to the following emails to insure customer is uploading TBP report to eSupport on time. mbox-aci-cash-operations-transaction-volume-reporting@aciworldwide.com | [6 empty] | Pending |  | HELP24 | Checkpoint 3 | [5 empty] | Not Applicable
System Growth and Capacity
Detail current and future planned transaction volumes being processed by the system and the upgrade path of the software version including forecasted dates. Any Performance review conducted or planned for future?
Custom Software Modifications (CSMs) - To be completed by PM
ACI-supplied customizations:
CSM # (Dev/CSM Narrative) | CSM Name (Deliverable Description) | CSM Size (Project Profile) | Owner | Sub-Type | CSM Status | CSM Phase
SDK customizations:
CSM # (Dev/CSM Narrative) | CSM Name (Deliverable Description) | CSM Size (Project Profile) | Owner | Sub-Type | CSM Status | CSM Phase

## CGW Specific Info (hidden)
ACI Test Environment Details - To be completed by PM
Please provide details on the following. Please note that not all fields may be relevant based on the project/product. |  |  |  |  | Please attach to Project or provide the location of a current copy of the customer’s system diagram and technical documentation regarding new functionality added during project phase.
ACI Product and Version |  |  |  |  | System Diagram
ACI Test network machine and location (include ESP networks):
ACI Logins and Passwords (Network and UI)
Simulator Test script location
Simulator Test script names
Synergy Baseline and Code thread
Jenkins Runstreams
Please provide the location of the following documents:
Test Validation Document (TVD): | Enter Link Here
Test master report | Enter Link Here
Maintenance and Support Plan | Enter Link Here
Additional Information about the Project - to be completed by PM
Installed Third Party Components used with Commerce Gateway
[5 empty] | Third Party Product |  | Release / Version / Fix Level | Vendor |  | HW Platform | Category
i.e. Backup System
Platform Information - to be completed by PM
ACI Product | Platform Name | Machine Type | Remote Access
Installed ACI Products
ACI Product | Release # Version # Service Pack # | System Name | Operation System
Commerce Gateway Tasks | [6 empty] | STATUS | Owner | Timeline |  |  | Pending
[12 empty] | Completed | Pending
Are CSMs developed by Services or AD? Who will be supporting the customer CSMs? Does the customer Pay CSM Support? Does the customer planning to make their own CSMs? | [6 empty] | Pending | PM | Checkpoint 3 |  |  | Not required | YES
CSMs development adhered to secure coding practices - Security Scanning Policy. If not, the handover cannot be accepted. | [6 empty] | Pending | PM | Checkpoint 3 |  |  |  | NO
Is the customer contracted to report capacity and pay capacity fees? | [6 empty] | Pending | PM | Checkpoint 2 |  |  |  | Not Applicable
If above is YES Ensure Capacity (TBP) process is configured and running successfully in Production before Go-Live | [6 empty] | Pending | PM | Checkpoint 2
If the customer is contracted to report capacity: Ensure Capacity report is running successfully and last month Capacity report is provided. We’ll NOT take any exceptions approach to this in order to ensure there is no revenue gaps. | [6 empty] | Pending | PM | Checkpoint 3
If above is YES Update BSO Operations Team that the handover is completed by sending email to the following email to insure customer is uploading Capacity report to eSupport on time. mbox-aci-cash-operations-transaction-volume-reporting@aciworldwide.com | [6 empty] | Pending | HELP24 | Checkpoint 3
System Growth and Capacity
Detail current and future planned transaction volumes being processed by the system and the upgrade path of the software version including forecasted dates. What is the current TPS and future TPS expected? Any Performance review conducted or planned for future? Database Retention period?
ACI Product ACI PRM - Enterprise Risk | Transaction Volumes (est. per month) |  | System Capacity
Current
Future – next 6 months
Future – after 6 months
Custom Software Modifications (CSMs) - To be completed by PM
ACI-supplied customizations:
CSM # (Dev/CSM Narrative) | CSM Name (Deliverable Description) | CSM Size (Project Profile) | Owner | Sub-Type | CSM Status | CSM Phase

## MTS Specific info (hidden)
MTS Specific info
Project/H24 Handover - Project Checklist
1. Fill out this custom handover check list. For not applicable items mention N/A.
2. Save the file using the following naming convention:
BBB_Vxx_Description.YYYYMMDD
SCB_V50_Uprgrade.20130313
3. Please upload document under the customer account in Salesforce.
4. Send the completed document check list via email to: GRP-hp24-MTS
Cut-Over/Go-live Details
Customer Name
Go-live date
Billable code for the project
Case(s)/Demand Management numbers
Release/CRs for the project
Primary ACI contacts during cutover weekend
Primary ACI contacts until project is turned over to H24
Project Manager
Customer Manager
Product /Technical Consultant
AD Manager
Customer contacts
New Customer | Yes | No | Comments
Is release area created and configured?
Any specific training required?
If yes please list training date(s)
Has the production/test VPN login tested successfully?
Has the MINFO file been updated with this information?
If the bank only allows webex support please note this.
Has a discussion been held with H24 to determine the outstanding project cases and who will be responsible for them going forward?
What are the test area name(s) and its server(s)
List of functionality that bank will use (i.e. FED, MPA, etc.)
Please provide go live support action plan, will H24 or project be first line of support? Will project be onsite for cutover?
Patch/stream the bank will go live with.
Availability of Bank’s Go-Live configuration files.
Any product customizations unique to this customer?
What are the versions being used for the following:
Java
Oracle
Impromptu
Are any of these products applicable? | Yes | No
Comments
ACE
SRGW
WEB_UI
ETW
Trail
Sterci
RPI
WFM
Prognosis
If WEB_UI, SUI or RPI have the necessary configurations and installations been done for support i.e. Oracle database, Websphere instance, WAR file, access permissions, etc?
Where - server/area_name/ usernames and passwords if applicable?
What date is scheduled for project to H24 support handover?
Where are the project/CSMs documentation located for reference?
Please indicate Area configuration | Yes | No | Comments
Phased
Multi-bank
Project/Enhancement
Upgrade | Yes | No | Comments
Is release area created and configured?
What is the server and area name?
Provide RPI/Oracle specifics
Are there any custom enhancements added in the new version? if so provide release notes
Any specific training required? If so please provide date training will take place on.
Patch/stream the bank will go live
with.
Availability of Bank’s Go-Live configuration files.
Please provide go live support action plan. Will there be onsite support from project?
Has a meeting taken place to review the outstanding project cases to determine who will be responsible for them after go live?
What are the versions being used for the following:
Java
Oracle
Impromptu
Are any of these products applicable? | Yes
|  | No | Comments
ACE
SRGW
WEB_UI
ETW
Trail
Sterci
RPI
WFM
Prognosis
If WEB_UI, SUI or RPI have the necessary configurations and installations been done for support i.e. Oracle database, Websphere instance, WAR file, access permissions, etc?
Where - server/area_name/ usernames and passwords if applicable?
What date is scheduled for project to H24 support handover?
Where are the project/CSMs documentation located for reference?
Please indicate Area configuration | Yes | No | Comments
Phased
Multi-bank
Project/Enhancement
Project/Enhancement | Yes | No | Comments
What is the server and area name?
Patch/stream the bank will go live with.
What will be the outstanding project cases and who will be responsible for them?
Instructions
5. Fill out this custom handover check list. For not applicable items mention N/A.
6. Save the file using the following naming convention:
BBB_Vxx_Description.YYYYMMDD
SCB_V50_Uprgrade.20130313
7. Please upload document under the customer account in Salesforce
8. Send the completed document check list via email to: GRP-hp24-MTS

## CMM Specific Information (hidden)
Additional CMM/Back Office Information - To be completed by PM
Please provide details on the following. Please note that not all fields may be relevant based on the project/product. |  |  |  |  | Please attach to Project or provide the location of a current copy of the customer’s system diagram and technical documentation regarding new functionality added during project phase.
ACI Product(s) and Version(s) | See table "CMM Products Affected by Project" below |  |  |  | System Diagram
New CSMs included in Project | See table"Custom Software Modifications (CSMs) Included in Project" below
ACI Test System (for HELP24 support)
~ WebUI Address (if applicable)
~ Port Address
~ ACI Logins and Passwords
Any Additional HELP24 Training Requirements?
Phased Go Live?
Go Live Date(s)
for future use
Please provide the location for the following:
Project Sharepoint Site: | Enter Link Here
Requirements Documents: | Enter Link Here
Detailed Design Documents: | Enter Link Here
Additional Information about the Project (including overview of how the customer uses the system and any future plans) - to be completed by PM
How many days per week is the BATCH run: |  |  |  |  | Installed Third Party Components used with CMM Product(s)
What time (approx) does the BATCH Start:
[5 empty] | Third Party Product |  | Release / Version / Fix Level |  | Vendor |  | HW Platform |  | Category
e.g. UNIX third party products
e.g. Websphere
CMM Products Affected by Project - to be completed by PM |  |  |  |  | Card Schemes Supported - to be completed by PM
ACI Product | Release / Version / Fix Level | Platform |  |  | Card Scheme |  | As an Acquirer / Issuer / Both
e.g. UNIX/Linux
Support Contacts at Customer - to be completed by PM
Name | Email Address | Telephone Number |  | Role / Specialist Area |  |  | Notes
CMM/Back Office Tasks | [6 empty] | STATUS |  | Owner | Timeline
Initial Update / Advice for CMM Call out Team | [6 empty] | Pending |  | HELP24 | Checkpoint 2 |  | Pending
If the project involves new CSMs, confirmation should be provided on whether the customer will be paying ongoing CSM Support Fees (CSF). | [6 empty] | Pending |  | PM | Checkpoint 3 |  | Completed
Upgrade Projects: if existing CSMs are retrofitted to the new version of the Product, confirmation should be provided on whether the customer will be paying ongoing CSM Support Fees (CSF). | [6 empty] | Pending |  | PM | Checkpoint 3 |  | Not required
All CSM and product cases from the project phase (i.e. prior to go live) must be closed prior to handover. | [6 empty] | Pending |  | PM | Checkpoint 3
Final Update for CMM Call Out Team | [6 empty] | Pending |  | HELP24 | Checkpoint 3
CSMs development adhered to secure coding practices - Security Scanning Policy. If not, the handover cannot be accepted. | [6 empty] | Pending |  | HELP24 | Checkpoint 3 |  |  |  | Pending
Is the customer contracted to report capacity and pay capacity fees? | [6 empty] | Pending |  | PM | Checkpoint 2 |  |  |  | YES
If above is YES Ensure Capacity (TBP) process is configured and running successfully in Production before Go-Live | [6 empty] | Pending |  | PM | Checkpoint 2 |  |  |  | NO
If the customer is contracted to report capacity: Ensure Capacity report is running successfully and last month Capacity report is provided. We’ll NOT take any exceptions approach to this in order to ensure there is no revenue gaps. | [6 empty] | Pending |  | PM | Checkpoint 3 |  |  |  | Not Applicable
If the customer is contracted to report capacity: Update BSO Operations Team that the handover is completed by sending email to the following email to insure customer is uploading Capacity report to eSupport on time. mbox-aci-cash-operations-transaction-volume-reporting@aciworldwide.com | [6 empty] | Pending |  | HELP24 | Checkpoint 3
for future use | [6 empty] | Pending |  | tba | tba
for future use | [6 empty] | Pending |  | tba | tba
System Growth and Capacity
Detail the current card * / merchant * / transaction * volumes being processed by the system. (* depending on products)
Detail future planned card * / merchant * / transaction * volumes being processed by the system and the upgrade path of the software version including forecasted dates. Any Performance review conducted or planned for future? (* depending on products)
Does the customer run, or plan to run, Housekeeping? If so what is the frequency?
Custom Software Modifications (CSMs) Included in Project To be completed by PM (if the handover is for a CSM then this section can be ignored)
ACI-supplied CSMs: | Yes / No (delete as appropriate)
CSM # or Reference | CSM Name | CSM Size (effort/cost) | Owner |  | CSM Status | Tested by Customer? |  | Go Live Plans (if go live is in the future, a separate handover may be required)

## PRM Specific Info (hidden)
PRM Specific Information
Please attach to Project or provide the location of a current copy of the customer’s system diagram and technical documentation regarding new functionality added during project phase. |  |  |  | Installed Third Party Components used with PRM
System Diagram |  |  |  | Third Party Product |  | Release / Version / Fix Level | Vendor |  | HW Platform | Category
i.e. Backup System
Server Java Version
Client Java Version
PRM Specific Components
|  |  |  | Component |  |  | Description |  |  | Comments
Action Levels Installed
No of AG Processes and PSEs
Database
PRM interface
PRM Scoring Engine (PSE)
Web Application Server
Additional Information about the Project - to be completed by PM |  |  |  | PRM Client
Production and DR Servers
|  |  |  | Server Name |  |  | Function
|  |  |  | example. PRM123456 |  |  | Windows Server running SQL-Server 2012– the Primary SQL server
|  |  |  | example. PRM123457 |  |  | Windows Server 2012 running Tomcat 8.0.30
Scheduled Jobs
Platform Information - to be completed by PM
ACI Product | Platform Name | Machine Type | Remote Access
Configuration and Store Procedure Changes
If there were any configuration changes made, Please list them below Were there any changes to standard stored procedure or new fields added? Please add them below
Installed ACI Products
ACI Product | Release # Version # Service Pack # | System Name | Operation System
PRM Tasks | [5 empty] | STATUS | Owner | Timeline |  |  | Pending
Completed
Did Project Team provided Product Training to the Customer? | [5 empty] | Pending | PM | Checkpoint 3 |  |  | Not required
Is customer pay license for DR Site? | [5 empty] | Pending | PM | Checkpoint 3
Provide System Sizing document to HELP24. | [5 empty] | Pending | PM | Checkpoint 3
If customer is running Oracle 12C, make sure the Customer is running on the latest Release or the Optimizer is set to 11G. | [5 empty] | Pending | PM | Checkpoint 3
Make sure Database Maintenance jobs such as Index Rebuild, Gather Statistics and partitioning are scheduled based on the recommendations from the Database Operations Guide. | [5 empty] | Pending | PM | Checkpoint 3
Are CSMs developed by Services or AD? Who will be supporting the customer CSMs? Does the customer Pay CSM Support? Does the customer planning to make their own CSMs? | [5 empty] | Pending | PM | Checkpoint 3
CSMs development adhered to secure coding practices - Security Scanning Policy. If not, the handover cannot be accepted. | [5 empty] | Pending | PM | Checkpoint 3 |  |  |  | Pending
Is the customer contracted to report capacity and pay capacity fees? | [5 empty] | Pending | PM | Checkpoint 2 |  |  |  | YES
If above is YES Ensure Active Accounts/Active Cards process is configured and running successfully in Production before Go-Live | [5 empty] | Pending | PM | Checkpoint 2 |  |  |  | NO
If the customer is contracted to report capacity: Ensure Active Accounts/Active Cards report is running successfully and last month Active Account report is provided. We’ll NOT take any exceptions approach to this in order to ensure there is no revenue gaps. | [5 empty] | Pending | PM | Checkpoint 3 |  |  |  | Not Applicable
If the customer is contracted to report capacity: Update BSO Operations Team that the handover is completed by sending email to the following email to insure customer is uploading Active Accounts report to eSupport on time. mbox-aci-cash-operations-transaction-volume-reporting@aciworldwide.com | [5 empty] | Pending | HELP24 | Checkpoint 3
Ensure demographic data loaded in Production | [5 empty] | Pending | HELP24 | Checkpoint 3
System Growth and Capacity
Detail current and future planned transaction volumes being processed by the system and the upgrade path of the software version including forecasted dates. What is the current TPS and future TPS expected? Any Performance review conducted or planned for future? Database Retention period?
ACI Product ACI PRM - Enterprise Risk | Transaction Volumes (est. per month) |  | System Capacity
Current
Future – next 6 months
Future – after 6 months
Custom Software Modifications (CSMs) - To be completed by PM
ACI-supplied customizations:
CSM Name and description (Dev/CSM Narrative) |  | Customer Pay CSM Support? | Comment |  | In Production?

## Money Guard (hidden)
ACI MG Environment Details - To be completed by PM
Please provide details on the following. Please note that not all fields may be relevant based on the project/product. |  |  |  |  | Please attach to Project or provide the location of a current copy of the customer’s system diagram and technical documentation regarding new functionality added during project phase.
MoneyGuard version | 5 |  |  |  | System Diagram
Customer environments : | Dev 12.12.13.145, UAT 12.12.13.147, Prod 12.12.13.148
ACI Logins and Passwords (Dev and UAT) | If applicable
Diagnostics | Tool installed in MGDiagnostics directory
Please provide the location of the following documents:
Functional specification | Enter link here
Dependency document | Enter link here
Installation instructions | Enter Link Here
Additional Information about the Project - to be completed by PM
Gateways used with MG
[5 empty] | Gateways |  | I/F |  | Vendor |  | Type | app
[5 empty] | SMS |  | SMPP V3.4 |  | Nexmo |  | Toll free number
[5 empty] | Email |  | SMTP |  | local |  | one way
[5 empty] | Push |  | Mobile browser |  | Spectrum |  |  | Mobile banking
[5 empty] | Voice |  | IVR Module |  | Spectrum |  | VOIP -HMP
MG Specific Components
[5 empty] | Component |  |  |  | Description |  |  | Comments
[5 empty] | Core engine | SPT- MG100 | Core engine | SPT- MG100
PRM Interface
[5 empty] | Batch campaign tool | SPT- MG108 | Batch campaign tool | SPT- MG108
[5 empty] | Two factor authen | SPT- MG106 | Two factor authen | SPT- MG106
[5 empty] | Call centre client | SPT- MG103 | Call centre client | SPT- MG103
Platform Information - to be completed by PM |  |  |  |  | IVR voice calling | SPT- MG109 | IVR voice calling | SPT- MG109
Billing engine
Servers (Prod) | Platform Name | Machine Type | Remote Access
Production and DR Servers
[5 empty] | Server Name |  |  |  | Function
example. MG123456
example. MG123457
Installed ACI Products
Scheduled Jobs
ACI Product | Release # Version # Service Pack # | System Name | Operation System
MoneyGuard Tasks | [6 empty] | STATUS |  | Owner | Timeline
Is the customer contracted to report capacity and pay capacity fees? | [6 empty] | Pending |  | PM | Checkpoint 2
If above is YES Ensure Capacity (TBP) process is configured and running successfully in Production before Go-Live | [6 empty] | Pending |  | PM | Checkpoint 2
If the customer is contracted to report capacity: Ensure Capacity report is running successfully and last month Capacity report is provided. We’ll NOT take any exceptions approach to this in order to ensure there is no revenue gaps. | [6 empty] | Pending |  | PM | Checkpoint 3
If the customer is contracted to report capacity: Update BSO Operations Team that the handover is completed by sending email to the following email to insure customer is uploading Capacity report to eSupport on time. mbox-aci-cash-operations-transaction-volume-reporting@aciworldwide.com | [6 empty] | Pending |  | HELP24 | Checkpoint 3
System Growth and Capacity | [12 empty] | Pending
Detail current and future planned transaction volumes being processed by the system and the upgrade path of the software version including forecasted dates. What is the current TPS and future TPS expected? Any Performance review conducted or planned for future? Database Retention period? | [12 empty] | YES
Product Spectrum MoneyGuard | Transaction Volumes (est. per month) |  | System Capacity | [9 empty] | NO
Current | [12 empty] | Not Applicable
Future – next 6 months | [12 empty] | Pending
Future – after 6 months | [12 empty] | Complete
Not Required
Custom Software Modifications (CSMs) - To be completed by PM
ACI-supplied customizations:
CSM # (Dev/CSM Narrative) | CSM Name (Deliverable Description) | CSM Size (Project Profile) | Owner | Sub-Type | CSM Status | CSM Phase

## RCS Specific Info (hidden)
RCS-specific requirements
Completed? | Servers |  | Completed? | Code Validation
No | List server names, function, server memory, memory allocated to db, db log sizes and dumps |  | Yes | Attach the zip file results of rcs-validate-install-1.0.25.jar (or higher) for *each* server to the handover case
|  |  | No | Has the customer been trained on how to use the RCS Validate Install tool
|  |  | No | List any code that is custom for this customer
Purge
|  |  | No | Is Purge configured for all tables
No | ACTIVE/ACTIVE - has the cusatomer performed failovers between the servers and they understand the process |  | No | Has the Purge process been reviewed to assure it is working
No | DR (not Active/Active) - has the customer performed failovers between the servers and they understand the process
| Encryption |  |  | Transaction Processing
No | Are IDs are encrypted in the database |  | No | List all authorizor / settlement processors
No | Is the customer familiar with changing encryption keys (*both* DEK and KEK) and re-encrypting IDs |  | No | List all card types certified to each authorizer / settlement processor
No | Does customer know how to decrypt deposit files (if applicable)
No | Does customer know how to decrypt \log\history files (needed when attaching to a case)
eSocket
| Logs |  | No | If the customer uses eSocket, attach the following (from a sample live store):
No | Are all \log\history logs are encrypted |  | No | esocketpos.applications
No | Is trace logging off in Production (exceptions must be noted) |  | No | properties
No | Have all logs been reviewed for errors prior to turnover |  | No | remote_properties
No | Attach *all* logs for a full business day (zipped), for every server, to the handover case |  | No | log folder
|  |  | No | trace folder
| General |  | No | Is the customer familiar and comfortable with Config Server, rolling out stores, adding new stores/terminals?
No | Has customer tested and validated every RCS report
No | List of outstanding cases (project team will retain ownership of cases opened prior to turnover accepted date) |  |  | Transaction Reporting to ACI
|  |  | No | Is the the monthly TBP/Monthly Count report configured and producing monthly reports
|  |  | No | Has the customer been trained on reporting monthly counts to ACI
No | List of outstanding projects/phases
Settlement
No | Documents/Environment Diagram; BRD, SOW, HLD, RPR and/or any other pertinent information; attach docs or link to docs to handover case |  | No | Trigger, RCS-capture, or host capture?
No | List trained RCS/Postilion administrator(s), including DBAs, at client
No | Are customer contacts set up in SalesForce and do they know how to use eSupport for case management and Articles |  | No | Is the customer contracted to report capacity and capacity fees? TBP process is configured and running successfully in production before Go-Live and reports upto latest month are provided to Cash Ops Team to ensure there are no revenue gaps. mbox-aci-cash-operations-transaction-volume-reporting@aciworlwide.com
No | Minimum 20-25% of locations must be rolled out before turnover |  | No
No | Processing must be stable
No handovers will be accepted for new implementations and version upgrades without TBP reports configured and run successfully.
No | Paste system diagram below
|  |  | No | Help24 to update BSO Operations Team that the handover is completed by sending an email to following email to ensure customer is sending TBP report on time. mbox-aci-cash-operations-transaction-volume-reporting@aciworlwide.com

## SalesforceAccountUpdate
Salesforce Account Update | Pending
Salesforce Project Link: |  |  |  | Pending
Completed
An Account should be reviewed for accuracy at the completion of every project. All sections of an account cannot be updated by the entire team. It will take some collaboration with the cross functional team to complete this review. Not every section is relevant to every product and some require additional information not captured in these fields. If there is additional information that needs to be documented review the product specific information for naming conventions etc. |  |  |  | Not required
ACCOUNT Assets Section |  | STATUS | Owner
Please review and update all fields in the Asset section and including test environment details etc. Please note that not all fields may be relevant based on the project/product.
Asset Information: must be updated to reflect current information in all valid fields. |  | Pending | PM
Product Release: must be updated to reflect the current release. |  | Pending | PM
System Name must be updated to reflect the current value. |  | Pending | PM
Hardware Information must be updated to reflect the current system. |  | Pending | PM
Operating System must be updated to reflect the current value. |  | Pending | PM
Additional Information, Notes and Attachments can be used to capture information not reflected in a field currently available. |  | Pending | PM
ACCOUNT Information Section |  | STATUS | Owner
Account team: must be reviewed and updated to reflect the current active team. |  | Pending | PM
Contacts: must be reviewed and updated to reflect the current active contacts. |  | Pending | PM
Project: must be updated to reflect the current status of the project. |  | Pending | PM
CSM’s - If the project included CSM’s they must be documented in the project Salesforce Development Deliverables section. |  | Pending | PM
Support Information must be populated to contain a 24/7 contact phone number and email address for the customer; 24x7 Command Center phone and 24x7 Command Center Email. |  | Pending | PM

## HVLV Specific Info
ACI Test Environment Details - To be completed by PM
Please provide details on the following. Please note that not all fields may be relevant based on the project/product. |  |  |  |  | Please attach to Project or provide the location of a current copy of the customer’s system diagram and technical documentation regarding new functionality added during project phase.
ACI Products and Versions (list down all components MTS, UPF, SAA, SAG, IP cartridges etc) | RTPS Global MTS -> MTS 5.8.78.0/6.8.78.0 June SP Patch 2 (Please refer ticket https://gojira.am.tsacorp.com/browse/H24-694664 & https://gojira.am.tsacorp.com/browse/H24-694594) UPF -> APSF Control Center (RT002 - 5.0.4-28): 5.0.4.20 MCAS (RT002 - 5.0.4-28): 5.0.4-28 ICE-XS-6.0.5.23 SAA-> SAG -> GATEWAY 1.5.1.1 IP Cartridges |  |  |  | solution topology diagram Please refer Customer system diagram from Solution document (Page 11) Solution Document Link : https://aciww.sharepoint.com/:w:/r/sites/isextnsn/proj/StateStreetPCS/Plan%20%20Design/Design%20Review/International%20SSD/State%20Street_SSG_RTGS_Bank%20Adapter%20SSDv06_SIGNEDOFF_FINAL.docx?d=w13e274665fa743718bb36ac8d0826777&csf=1&web=1&e=372Oek
ACI Test network machine and location | For MTS BOX: cov3lmtssvc10vm AREA: ssg_v60_svc_qa Path /usr/local/intranet/areas/ssg_v60_svc_qa/ | For UPF/PF/CB Box cov3ljkrapp12vm MQ server - same as above Logs : opt/aci/upf/log/switch1 For CC UI https://nrc3lmip20vm:9012/Responsive/platform/index.html#/home
ACI Logins and Passwords (Network and UI) | Video UI Login Password Global instance : Username: SAS Password: aci@1234
Simulator Test script location | Testing https://aciww.sharepoint.com/:f:/r/sites/isextnsn/proj/StateStreetPCS/Plan%20%20Design/Testing%20Plan?csf=1&web=1&e=ls68x1
Simulator Test script names | Testing https://aciww.sharepoint.com/:f:/r/sites/isextnsn/proj/StateStreetPCS/Plan%20%20Design/Testing%20Plan?csf=1&web=1&e=ls68x1
Production Runbook link | N/A
Production Support offering (PCS/HELP24), if PCS share SOW | scott walker (standar ba support ???
Warranty Period (below 30 days requires H24 Management Approval) | scott walker (standar ba support ???
Please provide the location of the following documents:
Test Validation Document (TVD): | Testing https://aciww.sharepoint.com/:f:/r/sites/isextnsn/proj/StateStreetPCS/Plan%20%20Design/Testing%20Plan?csf=1&web=1&e=ls68x1
Test master report | Testing https://aciww.sharepoint.com/:f:/r/sites/isextnsn/proj/StateStreetPCS/Plan%20%20Design/Testing%20Plan?csf=1&web=1&e=ls68x1
Maintenance and Support Plan | Not Applicable
Solution Design and any other documentation | Requirement Document : https://aciww.sharepoint.com/:w:/r/sites/isextnsn/proj/StateStreetPCS/Plan%20%20Design/Detailed%20Requirements/Signed-off/RTGS_Markets_BankAdapter_Intgeration_Requirements_v2.2.docx?d=w13153a0cc4a84e06b9fbc10508c59c62&csf=1&web=1&e=9MC90C Solution Document : https://aciww.sharepoint.com/:w:/r/sites/isextnsn/proj/StateStreetPCS/Plan%20%20Design/Design%20Review/International%20SSD/State%20Street_SSG_RTGS_Bank%20Adapter%20SSDv06_SIGNEDOFF_FINAL.docx?d=w13e274665fa743718bb36ac8d0826777&csf=1&web=1&e=372Oek
Functional specification documentation | https://jira.aciworldwide.com/browse/RTPS-95685
Host interface specification | N/A
NFR specification | N/A Performance Testing not done at ACI. However, refer https://jira.aciworldwide.com/browse/RTPS-104030 for the testing done by bank
UPF Production Configuration file in xml and binary format | Paul |  |  | go live from bank
UPF user cartridges used for the solution | N/A
End to end transaction flow diagrams | Please refer solution design
Additional Information about the Project - to be completed by PM for example, specific customer requirements, anything not considered "core product".
Note : All repair exception to be handled in CC (For contingency cases, bank can handle it via Video UI)
Additional Information about the Project - to be completed by PM
ACI Product | Platform Name | Machine Type | Remote Access
MTS Global | CUSTOMER SERVER DETAIL | CUSTOMER (Linux ... ) | N/A
UPF Global |  |  | N/A
HV/LV Requirments | [6 empty] | STATUS | Owner | Timeline | Timeline | Pending |  | Pending
[11 empty] | Completed |  | Completed
Is the customer on an N-2 code stream? If not please provide details on when they will be up to date | [6 empty] | Completed | PM | Checkpoint 3 | Nov 8 Global ( Jun 2025 SP Patch 2) | Not required |  | H24 Mgmnt approval
Has the customer signed up to the Snapshot service and if so please detail the versions, changes and schedule a specfic handover discussion with HELP24 and PD to handover the artifacts (refer to CSM/Snapshot section) | [6 empty] | Completed | PM | Checkpoint 3 | No SNAPSHOT |  |  | Completed
Individual HTML traces + ICE-XS traces capturing end to end flow (without the noise of other flow) | [6 empty] | Pending | PM | Checkpoint 3 | Paul
Has adequate training be provided to handle the solution and recovey, examples: • SELECT Querie(s) to identify stuck transactions that has not reached destination or if it has reached destination, but ACK not reached back to source • Steps to recover or repush the transaction through application (UPF or MTS) avoiding any duplicates and if customer is aware of these steps • Steps to recover or repush the transaction manually (any other way like UPDATE queries) • If possible, queries to identify the impacted messages categorized by there types post any incident (This is similar to first bullet but the scope is broader) | [6 empty] | Completed | PM | Checkpoint 3 | Please refer bank adapter user guide reconciliation part - Monitoring transaction detail by customer (reconcilation document)
Did the project involved CSMs developed by ACI on SDK? If yes, complete the CSM & SDK section below | [6 empty] | Completed | PM | Checkpoint 3 | N/A |  |  | NO
Provide a detailed view of any future phases of the project | [6 empty] | Completed | PM | Checkpoint 3 | Please refer Phase 3 & Phase 4 section from the Solution document, that are part of future phases
Is the customer contracted to report capacity and pay capacity fees? | [6 empty] | Completed | PM | Checkpoint 2 | Not Its Service Agreement |  |  | Not Appicable
If above is YES Ensure Capacity (TBP) process is configured and running successfully in Production before Go-Live | [6 empty] | Completed | PM | Checkpoint 2 | Not Its Service Agreement
If the customer is contracted to report capacity: Ensure Capacity report is running successfully and last month Capacity report is provided. We’ll NOT take any exceptions approach to this in order to ensure there is no revenue gaps. | [6 empty] | Completed | PM | Checkpoint 3 | Not Its Service Agreement
If above is YES Update BSO Operations Team that the handover is completed by sending email to the following email to insure customer is uploading Capacity report to eSupport on time. mbox-aci-cash-operations-transaction-volume-reporting@aciworldwide.com | [6 empty] | Completed | HELP24 | Checkpoint 3 | Not Its Service Agreement
Track ERRORs reported in production switch safeguard log for two weeks and generate report with fix plan. | [6 empty] | Pending | HELP24 | Checkpoint 3 | Paul - Upf Monitor production log daily
System Growth and Capacity
Detail current and future planned transaction volumes being processed by the system and the upgrade path of the software version including forecasted dates. Any Performance review conducted or planned for future?
N/A Performance Testing not done at ACI. However, refer https://jira.aciworldwide.com/browse/RTPS-104030 for the performance testing done by bank
Share performance test results to validate system can handle above volume and future capacity | [6 empty] | Completed | PM | Checkpoint 3
MANDATORY: For any CSM/Cusotomer Specific Configurations a separate handover discussion needs to arranged with PD | [5 empty] | N/A
Custom Software Modifications (CSMs) and Snapshot - To be completed by PM Refer to Dependancies Tab | [6 empty] | STATUS | Owner | Timeline | Timeline
Provide a Word Doc listing the following for each Change: • Scope/requirement • acceptance criteria • design • test case excel link • execution results doc link) • Test cases excel • Execution results docs (for every TCs). | [6 empty] | Completed | PM | Checkpoint 3 | N/A
Schedule a dedicated Handover Discussion including HELP24 and PD to arrange handover of the above | [6 empty] | Completed | PM | Checkpoint 3 | N/A
ACI-supplied customizations:
CSM # (Dev/CSM Narrative) | CSM Name (Deliverable Description) | CSM Size (Project Profile) | Owner | Sub-Type | CSM Status | CSM Phase
N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDK customizations:
CSM # (Dev/CSM Narrative) | CSM Name (Deliverable Description) | CSM Size (Project Profile) | Owner | Sub-Type | CSM Status | CSM Phase
N/A | N/A | N/A | N/A | N/A | N/A | N/A
MANDATORY: The following approvals are required before the project can be handed over to Production Support.
Project Handover Approvals
Department | Role | Name | Status | Date
HELP24 | Handover Lead | [10 empty] | Approved
HELP24 | Manager/Director | Peter Lee | [9 empty] | Not Approved
Product Development | Manager/Director | Amy Hanne
Implementation Services | Project Manager | Jeff Ranwson
Should all approvals not be received a call between HELP24, Services and PD Regional/Global Heads needs to be arranged.