## Sheet1
Task | Duration | Initial Date | End Date | Due Date | Resposible
INTENATIONAL DELIVERY
SSD Document Send for bank signoff ( International) |  |  |  | May 30th
[DEMO] ACI: Technical ACK/NACK (International Env) |  |  |  | Jun 05th
ACI - Control Center Setup Configuration (International Env) (internal) |  |  |  | Jul 11th
ACI - UPF Setup Configuration (International Env) (internal) |  |  |  | 2025-06-30
Monitoring MTS App Config Completion London |  |  |  | Jul 31th
Monitoring MTS App Config Completion Chats |  |  |  | Jul 31th
Monitoring MTS App Config Completion Lynx |  |  |  | Jul 31th
Monitoring MTS App Config Completion Rits |  |  |  | Jul 31th
Monitoring MTS App Config Completion Taiwan |  |  |  | Jul 31th
Monitoring MTS App Config Completion Target2 |  |  |  | Jul 31th
ACI - Internal - TESTING CHAPS
{DEMO] ACI - CHAPS END-END Validations
DOMESTIC DELIVERY
[DEMO] ACI: Control Center exception handling (Domestic Int) |  |  |  | Jun 05th
Documentation (Steps implement Control Center Config) |  |  |  | Jun 05th
Requirement document from Bank (Domestic) (Pending) |  |  |  | TBD
SSD Document Send for bank signoff ( Domestic) |  |  |  | TBD
Confirmation new sources for SSI / SSB /By bank |  |  |  | Jun 02th
ACI - Internal - TESTING SSI / SSB |  |  |  | TBD
ACI - Send Technical evidence (Testing) (SSI / SSB) |  |  |  | TBD