## SWIFT High level Bank Summary (hidden)
Customer Name | SM | Status - Risk, Ticket Count | MTS Version (March 2023) | UPF Version (March 2023) | GM Risk | Fix Pack Version (March 2023) | Snapshot Y/N | Guaranteed Messaging | Gateway - SAA/SAG/OTHER | Bank Adaptor | Plan Version | Region/ Business Hours | Start Business Day Time | Delivery Executive | Technical Go-LIVE Date | UPF On (Receiving Messages) | Control Center Usage in March (Y/N) | Implementation Details - Include UPF Components | Revised Plan - Meeting/Reviewed
ABC | Celia Christensen | Green | 5.8.59.0 | N/A | N/A for this phase Amit will work with bank to install for their ISO phase |  | N | N | SWIFT SAA (IF036): 1.4.2.8 | No | Plan C | Eastern |  | Christine Goddard-Brown | N/A | N/A (Non MTS) | N | As of 3/6: ABC let us know that they will onbly be using translation for march and wiill go full ISO at a later date MTS and Oracle Upgrade from 12c to 19c Live on Dec SP and ISO phase 7. No Bank adapter. • APSF Control Center: 5.0.2-9 • Control Center’s RTPF Plugin: 3.2.11.0 • MCAS: 5.0.2-18 • ICE-XS: ICE-XS 6.0.2.19 • MCAS IPF Cartridges: 3.2.11.0 • SWIFT SAA (IF036): 1.4.2.8 • SWIFT SAG (IF040): n/a • MTS Adapter (IF042): 1.5.4.0 • RTPS Bank Adapter (IF046): 1.2.0.2 n/a | Will be going live with Dec SP for March, date TBD.
Bank of America | Andee Coyle | Green | boa1_mts_50859 | RTPF MCAS 5.0.2-18 | Potential Solution - 5.0.2._20 w/MTS Adapter and SAA patch and latest ICE | FP5 | Y | N | SAA Version 7.6.57 | Yes | Plan A | Eastern |  | Christine Goddard-Brown | 2023-03-17 | Y | N | Jan Tech Go Live for SWIFT translator | BOA original plan was going live with Plan A in Feb/March and will continue with that plan, schedule to be revised mid-Nov
Bank of the West | Dayro Andrade | Green | 5.8.60.0 Snapshot BOW22 | N/A |  | FP4 January 2023 SP (In Testing) | Y | N | SAA |  | Plan C | Eastern |  | Jeff Rawson | 2023-03-11 | N | N | 11/19 - 11/20 - No UPF 2/10 - Delivered January 2023 SP and they plan to roll this into production before March. 3/11 - Installed snapshot BOW22 in prod | Remain on Plan C for March
BNP | Corina Brehui | Red | 5.8.60.0 - Snapshot BNP20 | ISO_Jan23: • Immediate Payments 3.2.13.0 • MTS ISO20022 Adapter 1.5.5.0-2 • RTPS Bank Adapter 1.2.1.0 • SWIFT ISO20022 SAA Gateway 1.4.2.9-1 • SWIFT ISO20022 SAG Gateway 1.3.2.10 | Potential Solution - 5.0.2._20 w/MTS Adapter and SAA patch and latest ICE | Snapshot BNP20 | Y | N | SAA | Yes | Plan A | Europe |  | Charles Codo | 2022-03-04 | Y | Y - inquiry only | 3/4: Tech go-live with MTS and UPF | Go-live with final bundle 2/18-19
Citizens | Kimberly Weathers | Green | 5.8.57.0 FP5 | N/A |  | FP5 | N | N | SAA |  | Plan C | Eastern | MTS back end processes start 5:45am ET and 6:30am ET interfaces are started and SWIFT connection comes up at 7:20am ET. Open for Business at 8:30am ET when VRU opens up. | Christine Goddard-Brown | TBD | N | N | CTZ has signed for 2,600 hours of ISO project work for a 24 month term. Project kickoff is late March / early April 2023. | Project kickoff is late March / early April 2023. Detailed timeline yet to be determined. They have said they want Fed ISO by Nov 2023. For March 2023 they will be on July 5.8.57 Fix Pack 5.
CNB | Kimberly Weathers |  | 5.8.57.0 FP6 | N/A |  | FP6 | N | Not yet, but trying to get setup in UP | SAA |  | Plan C | Pacific Time Zone | 5am PT | Christine Goddard-Brown | 2022-11-12 | N | N | Nov 12 completed with FP6 mandates on (hit an issues with admin verify function with code dark) 2/7/2023 - UPF TEST and PREPROD are configured and bank is testing UPF in TEST. PREPROD integration to UPF not setup yet. CNB is in the process of setting up UPF DR. | CNB will not use UP for March 2023 and will continue to use the SWIFT translator for March 2023. For March 2023, they will be on July 5.8.57 Fix Pack 6.
Fifth Third | Dayro Andrade | Green | N/A | N/A |  |  | N | N |  |  | Plan C |  |  | Christine Goddard-Brown | TBD | N | N | Not ready to start install of UPF - DELAYED
First Hawaiian | Danielle Gleason | Green | AOD | N/A |  | FP5 | N | N | SWIFT Lite2 |  | Plan D | Hawaiian |  | Jeff Rawson | TBD | N | N | Nov 19. - AOD, they only see MTS. UP is running SWIFTlite2 | AOD, they only see MTS. UP is running on SWIFTlite 2
First Horizon/First Tennesee | Christy Diffy | Green | 6.8.57.0 FP5 | ISO Phase 6f/October 17: APSF Conntrol Center 5.0.2-09 Control Center's RTPF Plugin 3.2.9.6 MCAS 5.0.2-20 ICE-XS 06.00.2.25 MCAS IPF Cartridges 3.2.9.6 SWIFT SAG (IF040) 1.3.2.7 MTS Adapter (IF042) 1.5.3.4 , MTS Baseline 1.5.3.4-1 - Patched for GM Looping RTPS Bank Adapter (IF046) 1.2.0.2 | Request PD to backport? | FP5 | N | Y | SAG | No | Plan B |  | MTS comes up around 6:30am CT after the balance file loads. Wire Transfer Team begins their start of day processes at 7:00 AM CT. | Christine Goddard-Brown | 2022-01-21 | Y | N | MTS Go-Live on Jan 21st UPF Go-Live on Feb 11th APSF Conntrol Center 5.0.2-09 Control Center's RTPF Plugin 3.2.9.6 MCAS 5.0.2-14 ICE-XS 06.00.2.13 MCAS IPF Cartridges 3.2.9.6 SWIFT SAG (IF040) 1.3.2.7 MTS Adapter (IF042) 1.5.3.4 RTPS Bank Adapter (IF046) 1.2.0.2 | First Horizon went live in Producion on FP5 - As of March 20, 2023 Frost will still be on FP5
FNBO | Julie Harvey | Green | 5.8.59 (Dec) | PH7 (21-Dec Release) APSF Control Center: 5.0.2-09 Control Center's RTPG Plugin: 3.2.11.0 MCAS: 5.0.2-18 ICE-XS: ICEXS-06.00.2.19 MCAS IPF Cartridges: 3.2.11.0 SWIFT SAA (IF06): 1.4.2.8 MTS Adapter (IF042): 1.5.4.0 RTPS Bank Adapter (IF046): 1.2.0.2 | Potential Solution - 5.0.2._20 w/hotfix and latest ICE | 5.8.59 (Dec SP) | N | N | SAA | Installed Not used | Plan B | North America EST | 6:30 AM ET (SOD) Processigng starts at 7AM, stops at 6PM | Allan Ramsey | 3/1/2023 (5.8.59) | Y | Y - Inquiry Only | Mar 1 2023 - MTS upgrade (Dec SP) UPF expected 3/18 - No GM | Plan C fully tested and "on the shelf" Preparations for Plan B in progress and expect to proceed. Detailed discussion on Go Live tasks expected 2/27
Frost National | Christy Diffy | Green | 5.8.57.0 FP5 | ISO Phase 6f/October 17 APSF Conntrol Center 5.0.2-09 Control Center's RTPF Plugin 3.2.9.6 MCAS 5.0.2-14 ICE-XS 06.00.2.13 MCAS IPF Cartridges 3.2.9.6 SWIFT SAG (IF040) 1.3.2.7 MTS Adapter (IF042) 1.5.3.4 RTPS Bank Adapter (IF046) 1.2.0.2 | Request PD to backport? | FP5 | Y | Y | SAG | No | Plan B |  | MTS open at 7:00am/CT | Christine Goddard-Brown | 2022-11-10 | Y | Y - inquiry only | Nov 10th - validation in progress - 11/15 - Completed APSF Conntrol Center 5.0.2-09 Control Center's RTPF Plugin 3.2.9.6 MCAS 5.0.2-14 ICE-XS 06.00.2.13 MCAS IPF Cartridges 3.2.9.6 SWIFT SAG (IF040) 1.3.2.7 MTS Adapter (IF042) 1.5.3.4 RTPS Bank Adapter (IF046) 1.2.0.2 | Frost went live in Producion on FP5 - As of March 20, 2023 Frost will still be on FP5
Huntington National Bank | Julie Harvey | Green | 5.8.57.0 FP5 | ISO Phase 6f/October 17: APSF Control Center: 5.0.2-09 Control Center RTPF Plugin: 3.2.9.6 MCAS: 5.0.2-14 ICE-XSL ICEXS-06.00.2.13 MCAS IPF Cartrdiges: 3.2.9.6 SWIFT SAG (IF040): 1.3.2.7 MTS Adapter (IF)42): 1.5.3.4 | Request PD to backport? | FP5 | N | Y | SAG | No | Plan B | North America EST |  | Jeff Rawson | 1/7 (UPF) | Y | Y - inquiry only | Nov 19 2022 - MTS only UPF Off Jan 7 2023 - UPF implemented Mar 19 2023 - Scheduled loopback test (8-9 EST) FP5: MCAS 5.0.2-14 MCAS IPF Cartridges: 3.2.9.6 MTS Adapter: 1.5.3.004 | HNB validated end-to-end with MTS Prod and UPF off-hours in Dec. Completed installation in January and on hold until Mar 19. Call Sun 3/19 8-9AM EDT will validate SWIFT Setup of InputChannel for Prod
Mizuho | Julie Harvey | Green | 5.8.57.0 FP6 | N/A |  | FP6 | N | N | SAA for their Plan E; will be SAG for ACI solution. | No | Plan E | North America EST | 5:00 AM ET (SOD) | Jeff Rawson | 2023-02-04 | N | N | 2/4 - MTS upgrade including components for Plan E (sysem profile, config updates) 2/25 - SAA upgrade UPF - Still TBD | While UPF is still not scheduled, MTS upgrade in Feb included updates to MQ channels, message queues for UPF interfaces to keep environments in sync.
MUFG/Union | Kimberly Weathers | Green | 5.8.57.0 FP5 | N/A |  | FP5 | N | N | SAA |  | Plan C | Pacific Time Zone | BAU Business day starts 8pmPT for next bus day. On 3/19/23 8:00 pm PT - Connect to FED for validation and then bring down the connection 8:30 pm PT - Connect to SWIFT FIN & FIN Plus 11:30 pm PT - Connect to FED 3/20/23 2:30 am PT - Connect to CHIPS 7:30 pm PT - COB, Roll the date and run EOD | Allan Ramsey | 2022-11-19 | N | N | Not ACI - ISO. MTS go live 19 Nov 2022 on July Fix Pack 5. ISO has been disabled and CHIPS format turned off. Deployed all ISO changes but did not enable it, including new SWIFT adapters. | MUFG installed July FP 5 on 19 Nov 2022 in PROD and will go live on that. On 18 March 2023, system profiles will be activated for ISO to be "on" for incoming messages however may have some pass thru messages to Fed with MX format. Using SWIFT translator with SWIFT custom code for MUFG to receive the MT format and using the 77T field. In Q2, US Bank will take the MUFG traffic and migrate into their systems to process. No more Service Packs will be installed for the March ISO go live. Nov 2023 SWIFT go live will be on US Bank, MUFG will have no work required for MTS on this go live event.
NTP | Celia Christensen | Green | 5.8.59.0 | ISO Phase 7/December | Potential Solution - 5.0.2._20 w/hotfix and latest ICE Working with Cam to get them installed | Dec '22 | N | N | AMH | no | Plan B | UK | CBPR+ & RITS EDT: Sunday, March 19, 2023 6:15 PM Target2 EDT: Monday, March 20, 2023 4:30 AM | Christine Goddard-Brown | 2023-02-17 | Y | N | No Control Center, No bank adapter CBPR+ and RITS for March '23 Pre installed Feb 17. 2023. No control center UPF Components: •• APSF: 5.0.2.9 • IP/Control Center’s RTPF Plugin: 3.2.11.1 • UPP:5.0.2-18-UC-008 (as observed from the summariseusercartridge output) • MCAS: 5.0.2-17 (as observed from the summariseusercartridge output) • ICE-XS: ICE-XS 6.0.2.19 • MCAS IPF Cartridges: 3.2.11.0 • SWIFT SAA (IF036): 1.4.2.8 n/a • SWIFT SAG (IF040): 1.3.2.9 n/a • MTS Adapter (IF042): 1.5.4.0 • RTPS Bank Adapter (IF046): 1.2.0.2 n/a | April '23 deply will be for Chaps, dates TBD Bank not using bank adapter but has future plans for it, no date as of now.
NTC | Celia Christensen | Green | 5.8.59.0 | N/A |  | FP3 | N | N |  | no | Plan C | Central |  | Christine Goddard-Brown | 2022-10-22 | Y | N | Oct 22. NTC will next focus on Chips, now April '24. | Already live - Not using UP/all iso going through NTP
Regions | Kimberly Weathers | Green | N/A | N/A |  |  | N | N | SAA |  | Plan C |  |  | Allan Ramsey |  | N | N | Using a SWIFT bureau (live for many years) who are performing the translation using a local SAA
Standard Chartered (JP) | Kimberly Weathers | Red | SCJ12 Dec 5.8.59 Snapshot (as of 25 Feb 2023) | New software and UPF reactivation 25th Feb. MTS 5.8.59 Dec Snapshot APSF Control Center - 5.0.2.9 RTPF(IP) Plugin - 3.2.11.1 MCAS - 5.0.2-20 ICE-XS for UP- ICEXS-06.00.2.25-Linux64 MCAS IPF Cartridges - 3.2.11.0 SWIFT SAA Cartridges - 1.4.2.008 MTS Adapter Cartridges - 1.5.4.000 | Workaround in Place | SCJ12 Dec 5.8.59 Snapshot (as of 25 Feb 2023) | Y | Y | SAA |  | Plan A |  |  | Allan Ramsey | 2023-02-25 | Y | Y - inquiry only | UP previously activated and then deactived do resolve a number of defects and operational issues. New software and UPF reactivation 25th Feb. MTS 5.8.59 Dec Snapshot APSF Control Center - 5.0.2.9 RTPF(IP) Plugin - 3.2.11.1 MCAS - 5.0.2-20 ICE-XS for UP- ICEXS-06.00.2.25-Linux64 MCAS IPF Cartridges - 3.2.11.0 SWIFT SAA Cartridges - 1.4.2.008 MTS Adapter Cartridges - 1.5.4.000
Standard Chartered (UK) | Kimberly Weathers | Red | SCG22 MTS 5.8.59 Dec Snapshot delivered 31 Mar 2023. Bundle 173 | New software and UPF reactivation 25th Feb. MTS 5.8.59 Dec Snapshot APSF Control Center - 5.0.2.9 RTPF(IP) Plugin - 3.2.11.1 MCAS - 5.0.2-20 ICE-XS for UP- ICEXS-06.00.2.25-Linux64 MCAS IPF Cartridges - 3.2.11.0 SWIFT SAA Cartridges - 1.4.2.008 MTS Adapter Cartridges - 1.5.4.000 | Workaround in Place | SCG22 MTS 5.8.59 Dec Snapshot delivered 31 Mar 2023. Bundle 173 | Y | Y | SAA |  | Plan A |  |  | Allan Ramsey | 2023-02-25 | Y | Y - inquiry only | UP previously activated and then deactived do resolve a number of defects and operational issues. New software and UPF reactivation 25th Feb MTS 5.8.59 Dec Snapshot APSF Control Center - 5.0.2.9 RTPF(IP) Plugin - 3.2.11.1 MCAS - 5.0.2-20 ICE-XS for UP- ICEXS-06.00.2.25-Linux64 MCAS IPF Cartridges - 3.2.11.0 SWIFT SAA Cartridges - 1.4.2.008 MTS Adapter Cartridges - 1.5.4.000
Standard Chartered (US) | Kimberly Weathers | Red | SCB08 Dec 5.8.59 Snapshot (as of 22 Mar 2023) Bundle 60 | New software and UPF reactivation 25th Feb. MTS 5.8.59 Dec Snapshot APSF Control Center - 5.0.2.9 RTPF(IP) Plugin - 3.2.11.1 MCAS - 5.0.2-20 ICE-XS for UP- ICEXS-06.00.2.25-Linux64 MCAS IPF Cartridges - 3.2.11.0 SWIFT SAA Cartridges - 1.4.2.008 MTS Adapter Cartridges - 1.5.4.000 | Workaround in Place | SCB08 Dec 5.8.59 Snapshot (as of 22 Mar 2023) Bundle 60 | Y | Y | SAG |  | Plan A |  |  | Allan Ramsey | 2023-03-04 | Y | Y - inquiry only | UP previously activated and then deactived do resolve a number of defects and operational issues. New software and UPF reactivation 4th Mar MTS 5.8.59 Dec Snapshot APSF Control Center - 5.0.2.9 RTPF(IP) Plugin - 3.2.11.1 MCAS - 5.0.2-20 ICE-XS for UP- ICEXS-06.00.2.25-Linux64 MCAS IPF Cartridges - 3.2.11.0 SWIFT SAG Cartridges - 1.3.2.009 MTS Adapter Cartridges - 1.5.4.000
State Street | Wanda Shurson | Green | 6.8.60 | ISO_Jan23 | Potential Solution - 5.0.2._20 w/MTS Adapter and SAA patch and latest ICE | MTS 6.8.60 FP5/ Jan SP | N | Y | SWIFT SAA (IF036): 1.4.2.9 |  | Plan B (Plan A June) | Eastern | Mar 19 6PM ET | Jeff Rawson | 2/23/2023 complete 11/5/2022 - Completed | Y | Y - inquiry only | 2/17 test complete, 2/23 Prod Deploy. MTS 6.8.60 UPF ISO_Jan23 (pending confirmation 2/22): • APSF Control Center: 5.0.2-11 • Control Center’s RTPF Plugin: 3.2.13.0 • MCAS: 5.0.2-18 • ICE-XS: ICEXS-06.00.2.19 • MCAS IPF Cartridges: 3.2.13.0 • SWIFT SAA (IF036): 1.4.2.9 • SWIFT SAG (IF040): N/A • MTS Adapter (IF042): 1.5.5.0 • RTPS Bank Adapter (IF046): N/A | 3/10: On Call support 3/19 for LYNX test/validation. 3/9: Confirmed patches for GM on top of JanSP delivered. Pending test/prod deploy timeline following 3/20 GoLive 3/9: Mtg sched with SS 4:30PM ET to review GM resolution timeline 3/6: RITS testing successful 3/5: LYNX testing successful 2/28: Internal Mtg 3/2 to review GM issues and determine ISO_Jan23 vs ISO_Feb23 2/9: updated timeline received from State Street (SSG).
Truist | Danielle Gleason | Green | 5.8.57.0 FP6 | ISO Phase 6g/October 31 | Request PD to backport? | FP6 | N | Not yet, but trying to get setup in UP | SAA |  | Plan B |  |  | Jeff Rawson | 2023-02-06 | Y | y | FP6 went into prod. 06 of Feb. with corresponding. UP for limited CC uses (inquiry nly) ISO Golive, the bank will enable ISO processing via standard PRULE updates within application | original plan for golive
UMB Bank | Christy Diffy | Yellow |  | N/A |  | FP6 | N | N | SAA |  | Plan C |  |  | Jeff Rawson | 2022-12-12 | N | N
Wells | Celia Christensen | Green | k | N/A | Cam will work with wells to get them installed for their iso phase | FP4 | Y | N | other (SMH) | no | Plan C |  |  | Christine Goddard-Brown | 2022-11-20 | N | N | 11/20 - No UPF code installed in January already with snapshot built on FP4 for both emts and gmts, No UP, No ISO, translation only - march 29 is turn on only, no code install 6/23/23: Plan B ISO Target release is 6/23/23 weekend with Jan SP base for both MTS and UP, probably a snapshot. - Starting to test bank adapter, target for go live for bank adapter tbd. | Wells original plan was going live with Plan B in March -Wells will now go live with plan c in March '23 and looking to go to plan B in June 2023
Zions |  | Green | N/A | N/A |  |  | N | N | SAA |  | Plan C |  |  | Christine Goddard-Brown | TBD | N | N | Using an SAA to perform translation
BMO (Bank of Montreal) | Wanda Shurson | Yellow | Swift Gateway 2.0.0.1 | BMO Specific - UPF 4.0 |  | Swift Gateway 2.0.0.1 | N | Y | SAA | No | N/A |  |  | Jeff Rawson | 3/4/2023 & 3/18/2023 | N/A (Non MTS) | N/A (Non MTS) | Technical Go-Live 3/4 UPF 4.0.0.45.2 / IPF 2.6.6.x | 3/13: BMO is not planning to install the hotfix (for ctx.comm_address) prior to Mar 20 cutover. GM will remain enabled in production 3/4: Tech GoLive completed, H24 supporting Production environment 2/13: TARGET Tech Go-Live for Swift Gateway 2.0.0.1 on March 4

## Program Update (hidden)
FED ISO Program Updates
Customer Name | Technical Go Live Status (If applicable) | Connectivity Test | 7:45PM Unsolicited Balance (CAMT52) | 8:30PM Non-Financial Messages | 9:00PM Payment Messages (7) | 12am Payment Messages | Project Status using Drop Down (Green, Amber, Red) | As of Date, Time | Status Summary/Notes | # Fed Inbound Transactions | # Fed Outbound Transactions | ACI Support Requested | SF P1 Cases | SF P2 Cases | SF P3 Cases | Next Status Update
Comerica Bank
Bank of America
Citizens Bank
Huntington National Bank
Northern Trust Bank - New York NTC
Truist Bank
Wells (EMTS-WEL)
Wells (GMTS-WFI)
Mizuho Bank
First Horizon Bank
UMB Bank N.A.
Federal Home Loan Bank-NY
Fifth Third Bank
Frost National Bank
Regions
State Street Domestic
Zions Management Services Company
Standard Chartered Bank New York
Agricultural Bank of China
City National Bank
First National Bank of Omaha
Federal Home Loan Bank of Atlanta
DnB Nor - NY Branch
Federal Home Loan Bank-Cincinnati
Federal Home Loan Bank-Des Moines
First Hawaiian Bank
Flushing Savings Bank

## High level Bank
Type | Customer Name | Delivery Executive | SM/PM | Timezone | Start Business Day Time (What time do they start their day?) | End Business Day Time (What time do they end their day) | Expected First Transaction Timeframe (What time will we see the first financial transaction?) | Support Days Needed | Support Times | Technical Go-LIVE Target Date/Complete Date | Technical Go Live Start and end Time | Control Center Usage | Date Go Live Implementation Plan Provided or when will it be provided
AOP | Agricultural Bank of China (ABC) | Denise | Dayro | ET | 9:00 PM (MTS date is the next business date) | It depends when Operations end all the daily transactions, normally between 5:30 PM to 6:30 PM | 11/23 9:00 PM (Value date is the next business date) | 11/21 & 11/23 | 11/21 at 7pm - 11pm 11/23 at 6pm - 10pm | Complete |  | Control Center is always on (IT will shutdown the MQ channel during the go-live weekend). | 2025-11-24
AOP | Bank of America | Denise | Andrea/Nasser | ET | 9pm Sunday 11/23 | 8pm | 9pm Sunday 11/23 | 11/20-12/8 | 24/7 call in's still TBD by BOA | 2025-11-21 | 2025-11-22 | CHP/FED Admin Only | 2025-11-18
AOP | BNPPF | Charles | Luc Lippens | CET | 3AM CET Monday morning | It depends when Operations end all the daily transactions, normally between 5:30 PM to 6:30 PM | 11/24 03:00AM CET | 11/23: penny testing with BOE/CHAPS between 08:30AM - 17:00PM CET 11/24: gradual release activation from 2AM CET onwards | 11/23: penny testing with BOE/CHAPS between 08:30AM - 17:00PM CET 11/24: gradual release activation from 2AM CET onwards | Complete | Snapshot BNP40 was activated in production 25-26 October | Limited to consultation only for now | 2025-10-25
AOP | Citizens Bank | Christy | Dayro | ET | 3am. Back End Start of Day Process will be run at 3am EST on 11/24. Connectivity of some interfaces including FED connection will be enabled ~3:20am EST. Connectivity of remaining interfaces including SWIFT will be enabled ~5:40am EST. | 7pm. Planned end time to bring down our connections in MTS is 7pm EST (corresponding with the Fed closure). If the Fed has an extension, we will remain processing/up until the Fed closes. Backend End of Day processes will begin approximately 10-15 minutes after our connections have been brought down (~7:10-7:15pm EST). | 3:20am. Once our Fed connections are enabled at ~3:20am EST, we will start to receive inbound traffic from the Fed and our first financial transaction will more than likely be received around this timeframe. | 11/21 & 11/23 | 11/21 at 10pm - 11:59pm 11/23 at 8am - 12pm | NA |  | Control Center usage – Payment Search/Inquiries, and FED ISO Admin messages | 2025-11-24
AOP | City National Bank (CNB) | Christy | Christy | PST | 5:00 | 6:00pm EOD starts | 5:00 | Sunday evening flip flag; Monday morning |  | Complete |  | Y | 2025-11-20
AOP | Comerica | Christy | Dayro | ET | 6:00 AM ET | 8:00 PM ET | 6:20 AM ET | 2025-11-22 | 11/22 at 6am - 1pm | NA |  | Inquiry transactions Investigation Returns Investigation Rejects NOTE: Entry, Verify, Repair, Verify Callback and Exceptions is still being done using MTS. | 2025-11-24
AOP | Fifth Third Bank | Christy | Dayro | ET | 2:35 AM EST | 7 PM EST | We’ll receive inbound FED wires when we come up at 2:30 am on Monday the 24th. We also normally have a few outbound wires around the same time. With respect to the SAB wires that will start flowing through the SAA Gateway to UPF, that will start around 6:30 am. It could potentially be earlier since they should flow into UPF as soon as they are received into SWIFT Alliance Access from the SWIFT Network. | Bussines hours | Bussines hours | Complete |  | Only for inquiry or FED/CHP Administrative messages. | 2025-11-24
AOD | First Hawaiian Bank (AOD) | Denise | Stephen | [6 empty] | Complete
AOP | First Horizon Bank | Stephanie | Christy | CST | 6:45am | 8:00pm EOD starts | 6:45am | Saturday for code deployment; Sunday evening flip flag; Monday morning | 8:00 - 3:00 Saturday | 2025-11-21 |  | Y | Not provided yet
AOP | First National Bank of Omaha (FNBO) | Denise | Jason | CT | 8:00AM | 5:00PM |  | Bussines hours | Bussines hours | N/A |  | y
AOP | Frost National Bank | Denise | Christy | CST | 7:00am | 6:30pm EOD starts | 7:00am | N/A |  | Complete |  | Y | 2025-11-21
AOP | Huntington National Bank | Stephanie | Nisha | EST | 2:00PM | 7:30PM | 7:30AM |  |  | 2025-11-22 | 11/21/25 9:00AM - 11/22/2025 11:59PM | Payment Search/Inquiry & FED ISO Admin | 2025-11-24
AOP | Mizuho Bank | Stephanie | Stephen | [6 empty] | 2025-11-22
AOP | Northern Trust Bank - NTC | Christy | Christy | CST | 11:00pm | 7 PM CT, Mon-Fri NTP APAC EOD is 8 AM CT, Sun-Fri, EMEA EOD is 6 PM CT, Sun-Fri. | 11:00pm | N/A |  | Complete |  | Y | 2025-11-21
AOP | Regions | Denise | Jason | CT | 8:00AM | 5:00PM | 11/24/2025 6:00am | Bussines hours | Bussines hours | 2025-11-21 | 11/21/25 9:00AM - 11/22/2025 11:59PM | Yes | 2025-11-11
AOD | Republic Bank (AOD) | Stephanie | Stephen | [6 empty] | 2025-11-15
AOP | Standard Chartered Bank New York (SCB, SCG, SCJ ) | Ka Fui | Kheng Teong, Junaid | EST |  | 8:00pm EOD starts | 11/22 11PM EST | 11/21 to 11/23 | 11/21 at 8pm - 11/23 11am | 2025-11-22 |  | Payment Search/Inquiry & FED ISO Admin | 2025-11-24
AOP | State Street Bank (Global/Domestic) | Stephanie | Oscar Herrera | EST | 9:00 | 17:00 | 11/24/2025 EST 3:00 PM 11/22 /2025 11/23/2025 11/24/2025 | Bussines hours | Bussines hours | 2025-11-22 | 11/22/25-8:00AM - 11/23/24-4:00 PM | Admin messages only; not for exceptions or repairs | 2025-11-24
AOP | Truist Bank | Stephanie | Nisha | EST | 4:00AM | 7:00PM | 4:00AM | 11/21/2025 11/22 /2025 11/23/2025 11/24/2025 | 11/21 – 7PM – 11:59PM 11/22 – 12PM – 5PM 11/23 – 3PM – 5PM 11/24 – 2AM – 11:59PM | 2025-11-21 | 11/21/25-7:00PM - 11/23/24-7:30AM | Admin messages only; not for exceptions or repairs | 2025-11-24
AOP | UMB Bank N.A. | Stephanie | Stephen | [6 empty] | 2025-11-22
AOP | Wells (EMTS-WEL/GMTS-WFI) | Christy | Celia | EST | gmts sun 11/23 @9:00 pm emts Mon 11/24 @ 4:30 am | 19:00 | Bank will perform penny transactions on 11/22 at 2:00 pm, else see sod times | 11/21, 22, 23, and 24 | 11/21 - 9:00 PM 11/22 - 8:30 PM 11/23/25 8:00am 11/23/2025 11:59:00 AM | 2025-11-22 | 11/21 7:30 through 11/22 4:00 | admin only and inquiry | already provided (final provided 11/19)
AOP | Zions Management Services Company | Christy | Christy | MST | 6:00am | 6:00pm EOD starts | 6:00am | Sunday evening flip flag; Monday morning |  | Complete |  | Y | 2025-11-04

## Case Tracker (hidden)
Instructions:
1) Please ensure all go-live cases created include 'GO_LIVE_CASE' label, both goJira and PDJira - each case should have its own row
2) Detail is not necessary - but would like status to be either 'Green' = Experiencing no issues, processing, 'Yellow' = Has one or more P2 open issues, 'Red' = Has ar least one P1 opened.
3) This will be updated by Lolita Florence, based on the Jira Dashboard but the PMs can add any additional details 4) Dashboard - https://gojira.am.tsacorp.com/secure/Dashboard.jspa?selectPageId=124100
Bank | Status | H24 # | RTPS # | Priority | # Issues (P1, P2, P3) | Last Check-In | Owner | Assistance Needed | Project Manager | Notes/Descriptions
Wells Fargo | Resolved, Awaiting Customer Acceptance | H24-683656 | N/A | 2 - High |  |  | Juan Mateus | N | Celia Christensen | Wells Fargo upgraded their secondary data center to Patch 9, however when selecting the upgrade options they incorrectley selected the primary platform, causing an incorrect database to be selected. Once the upgrade step was corrected, the installation suceeded sucessfully.
Comerica - CMA | Awaiting Customer Action | H24-683661 | N/A | 2 - High |  | 2025-07-12 13:13 | Ananth Rajah | N | Dayro Andrade | Periodically users are unable to access Control Center via SSO CMA requested the project team support to join on a call this morning (July 12th). They were having issues with the Control Center SSO login. There were five major issues/errors identified since yesterday. Three of them were on Comerica to address, and ACI will investigate two. Although the impact of these issues on ACI is currently limited, they anticipate an increase as more CC operators access the CC via SSO Login.
Bank of America - BOA | Resolved, Awaiting Customer Acceptance | H24-683666 | N/A | 2 - High |  | 2025-07-13 11:40 | Cam Jackson | N | Andee Coyle | 7/13: 11:30pm - Nathan Brown joined to help analyze the latest Logs uploaded by BOA. ACI engaged this am to fix the work yesterday. The Default setting needed to be tweaked to include the -Doption not just changing the true/false. Tushar confirmed an exssiting case H24-607017 from 7/2024. 7/12: Cam and Siva fixed the issue, cartridge loaded and activated at 4:14pm ET. Issues were tied to Attribute "rcvBufSize" has illegal value "-" and the missing R. Siva & Jeff joined Cam after a soft escalation by Robin to Steve. Additional info being uploaded to the ticket. Cam is currently triaging with Mansi and BOA team. RTPF- Unable to activate bofaendpoint cartridge in prod: Unable to activate bofaendpoint cartridge version 1.0.0.014 in production and getting this error Enter MCAS password: Error executing mcas command mcas/config insertUserCartridgeReferences cartridges=BOFA_ENDPOINTS:1.0.0.014 schemaUpdateMode=DISRUPTIVE_UPDATE - Failed to execute management command: Unable to define components
ABC | Resolved, Awaiting Customer Acceptance | H24-683707 | N/A | 2 - High |  | 2025-07-13 22:00 | Carlos Castaneda | N | Dayro Andrade | 7/13: "we've set up prod UPF with Lterm MMQFMPDH, but the payment message sent from prod shows our test code MMQFMCDH. FED confirmed our prod message sent to their test env because of the test code" Issue reported by ABC at 9:42pm. Carlos provided guidance/support which the customer is following, seems to be configuration.
NTC | Researching | H24-683712 | TBD | 2 |  |  | Brian Winn | Y | Christy Diffey | 7/13/2025 Some FED Inbound messages are failing in MTS due to the error "OBI and BBI characters is too long". They are leaving this a P2 and will let ACI know tomorrow if we can down grade it to a P3.
FHLBNY | Closed | H24-683793 | N/A | 2 - High |  | 7/14/2025 7:03AM | Paula Boston | N | Wanda Shurson | 7/14/2025: RHS is down with internal error disk.c.6327. Production is up and processing. Joint triage completed, root cause: Bank did a reboot of the system Saturday and RHS may have not been brought down.
Bank of America - BOA | New | H24-683810 | NA | 2 - High |  | 7/14/2025 7:29:00AM | TBD still working with BOA |  | Andee Coyle | 7/14: we are still trying to understand the issue. There are 500 trans rejecting w/the FED with E416 error
CMA | Resolved, Awaiting Customer Acceptance | H24-683802 | N/A | 3 - Medium |  | 7/14/2025 8:00:00AM | Ananth Rajah |  | Dayro Andrade | 7:14: This issue was due to missing columns in the db seed script with Patch 8 delivery. This was later fixed with a updated script. After running the correct seed script, the issue is resolved.
FTB | Researching | H24-683822 | N/A | 3 - Medium |  | 7/14/2025 8:40:00AM | Carlos Castaneda |  | Dayro Andrade | 7:14: UPF RT DB MCAS_REJECT2 Table has System Malfunction for Drawdown pain.013 Review is ongoing. Carlos Castaneda and Anu Pandey are on the bridge call with the customer
TFC | Slotting | H24-683799 | RTPS-98703 |  |  |  | Jean Harty |  | Alnicia Howard | Incoming Wires from the FED are going to Repair and have to be manually updated to ADV: LTR to process the transaction
NTC |  | H24-683831 |  | 2 |  | 8:00AM |  | Y | Christy Diffey | We have observed an urgent issue after having togged FED ISO ON in production. Incoming FED messages intended to get routed to GPP via SWG advice is generating MT910 credit confirmation message in FED ISO mode whereas it was generating MT103 or MT202 in Legacy mode which is causing issues in LME downstream application. We have noticed that for FED ISO message, only CDT party is mapped, and no Beneficiary details are getting mapped in FTR screen. Also note that, we have performed a test including CdtrAgtAcct in the incoming FED message and observed that both CDT and BNF are mapped and MT103/202 is getting generated as expected. We need a solution for payments which could mimic the behavior when CdtrAgtAcct is received. In Legacy mode, when we received {4200} Beneficiary: D/5186061000, both CDT and BNF are mapped in FTR. We believe it could be due to the presence of CDTAIN P-rule with D/5186061000 in Profile IDI which is attached as well.
NTC |  | H24-683824 |  | 2 |  |  |  | Y | Christy Diffey | Ops PARTNERS REPORTED MTS Slowness issue while accessing PSR screen and users' session crating mutual locks in MTS

## Bank Code Versions
Customer Name | Delivery Executive | SM/PM | Snapshot Y/N Version? | MTS Version (Baseline or Snapshot code) Eg: Patch 9 / Patch 9 Snapshot | UP Framework Version | ICE-XS Version | Control Center IP/F Version | FEDWire GW Version | MTS Adapter Version | Bank Adapter Version | SAG GW Version | SAA GW Version | CHIPS GW Version | Sanctions GW Version
123 Bank(Example) |  |  | Y | Patch 9 Snap | 5.0.4-23 | 6.0.5.23 | IP 3.5.2.10 | 1.1.2.9 | 1.7.2.7 | N/A | N/A | 1.5.0.5 | 1.1.1.5 | 1.0.0.4
Agricultural Bank of China (ABC) | Denise | Dayro | N | Jun_25 SP Patch 3 (MTS 6.8.78) | 5.0.4-28 | ICE-XS.6.0.5.23 | 3.5.3.2 | 1.1.2.13 | 1.7.3.2 | 1.5.0.1 | N/A | 2.1.1.1 | n/a | n/a
Bank of America | Denise | Andrea/Nasser | Y | Jun_25 SP (MTS 5.8.78) boa2_mts_50878 snapshot | 5.0.4-28 | 6.0.5.23 | APSF CC: 5.0.4.20 CC IP Plug In: 3.5.3.2 MCAS IPF: 3.5.3.3 | 1.1.2.013 | 1.7.3.002 | 1.5.0.001 | N/A | 2.1.1.001 | 1.1.2.003 | N/A
BNPPF | Charles | Luc Lippens | Y | Jun_25 SP (MTS 5.8.78) | MCAS: 5.0.4-28 | ICE-XS 6.0.5.21 | APSF Control Center: 5.0.4.20 MCAS IPF Cartridges: 3.5.3.0 | N/A | MTS ISO20022 Adapter: 1.7.3.0 | RTPS Bank Adapter: 1.5.0.0 | N/A | SWIFT ISO20022 SAA Gateway 2.1.1.0 | N/A | N/A
Citizens Bank | Christy | Dayro | y | Sep_25 SP Patch 1 Snapshot (MTS 6.8.79) | 5.0.4-21 | ICE-XS.6.0.5.24 | 3.5.4.1 | 1.1.3.1 | 1.7.4.1 | 1.5.1.1 | N/A | 2.1.1.0 | N/A | N/A
City National Bank (CNB) | Christy | Christy | N | MTS 5.8.78 June SP Patch 4 | ISO_Jun25 UPF Patch 4 | ICE-XS-6.0.5.23 | 3.5.3.3 | 1.1.2.13 | 1.7.3.2 | 1.5.0.1 | 1.5.1.2 | 2.1.1.1 | 1.1.2.3 | 1.0.0.4
Comerica | Christy | Dayro | N | Jun_25 SP Patch 4 (MTS 5.8.78) | 5.0.4-28 | ICE-XS.6.0.5.23.L64 | 3.5.3.2 | 1.1.2.13 | 1.7.3.2 | 1.5.0.1 | N/A | 2.1.1.1 | n/a | n/a
Fifth Third Bank | Christy | Dayro | N | Jun_25 SP Patch 2 (MTS 6.8.78) | 5.0.4-28-UC-001.019 | ICE-XS.6.0.5.23 | 3.5.3.2 | 1.1.2.012 | 1.7.3.001 | 1.5.0.000 | N/A | 2.1.1.000 | 1.1.2.002 | N/A
First Hawaiian Bank (AOD) | Denise | Stephen | N | Jun_25 SP Patch 2 (MTS 5.8.78) | 5.0.4-28 | ICE-XS.6.0.5.23 | 3.5.3.2 | 1.1.2.12 | 1.7.3.1
First Horizon Bank | Stephanie | Christy | N | MTS 5.8.78 June SP Patch 4 | ISO_Jun25 UPF Patch 4 | ICE-XS-6.0.5.23 | 3.5.3.3 | 1.1.2.13 | 1.7.3.2 | 1.5.0.1 | 1.5.1.2 | 2.1.1.1 | 1.1.2.3 | 1.0.0.4
First National Bank of Omaha (FNBO) | Denise | Jason | N | Jun_25 SP Patch 2 (MTS 5.8.78) | 5.04-28 | 6.0.5.23 | 3.5.3.2 | 1.1.2.13 | 1.7.3.1 | N/A | N/A | 2.1.1.0 | 1.1.2.1 | 1.0.0.4
Frost National Bank | Denise | Christy | Y | MTS 5.8.78 June SP Patch 2 | ISO_Jun25 UPF Patch 2 | ICE-XS-6.0.5.23 | 3.5.3.2 | 1.1.2.11 | 1.7.3.1 | 1.5.0.0 | 1.5.1.0 | 2.1.1.0 | 1.1.2.1 | 1.0.0.4
Huntington National Bank | Stephanie | Nisha | N | 5.8.78/SO_Jun25_HF2 | UPF 5.0.4-28 | 5.0.4.20 | Real-Time Payments 3.5.3.2 | Fedwire ISO20022 Gateway 1.1.2.12 | MTS ISO20022 Adapter 1.7.3.1 | Bank Adapter 1.5.0.0 | SWIFT ISO Gateway (SAG) 1.5.1.1 | N/A | CHIPS ISO Gateway 1.1.2.2 | N/A
Mizuho Bank | Stephanie | Stephen
Northern Trust Bank - NTC | Christy | Christy | Y | MTS 5.8.78 June SP Patch 2 | ISO_Jun25 UPF Patch 5 | ICE-XS-6.0.5.23 | 3.5.3.3 | 1.1.2.14 | 1.7.3.2 | 1.5.0.1 | 1.5.1.3 | 2.1.1.2 | 1.1.2.3 | 1.0.0.4
Regions | Denise | Jason | N | Jun_25 SP Patch 1 (MTS 5.8.78) | 5.0.4-28 | 6.0.5.23 | 3.5.3.2 | 1.1.2.1 | 1.7.3.1 | N/A | N/A | 2.1.1.0 | 1.1.2.1 | 1.0.0.4
Republic Bank (AOD) | Stephanie | Stephen | N | Jun_25 SP Patch 2 (MTS 5.8.78) | 5.0.4-28 | ICE-XS.6.0.5.23 | 3.5.3.2 | 1.1.2.12 | 1.7.3.1 |  |  | 2.1.1.0
Standard Chartered Bank New York (SCB, SCG, SCJ ) | Ka Fui | Kheng Teong |  |  | UPF 5.0.4-28 | 6.0.5.21 | 3.5.3.2 | 1.1.2.012 | 1.7.3.001 | 1.5.0.000 | 1.5.1.1 | 2.1.1.0 | 1.1.2.2 | 1.0.0.4
State Street Bank (Global/Domestic) | Stephanie | Oscar Herrera | N/Y | Global :Jun 2025 Sp5 / Domestic: MTS 6.8.78.0 ISO_Jun25_HF2 -Snapshot1 | UPF 5.0.4-28 | 6.0.5.23 | 3.5.3.2 | Fedwire ISO20022 Gateway 1.1.2.12 | MTS ISO20022 Adapter 1.7.3.1 | Bank Adapter 1.5.0.0 | SWIFT ISO20022 SAA Gateway 2.1.1.0 | 2.1.1.0 | CHIPS ISO20022 Gateway 1.1.2.2 | 1.0.0.4
Truist Bank | Stephanie | Nisha | N | Patch | UPF 5.0.4-28 | ICE-XS 6.0.5.23 Mod 250618 | 5.0.4-20 | 1.1.2.13 | 1.7.3.2 | 1.5.0.1 | N/A | 2.1.1.1 | 1.1.2.3 | N/A
UMB Bank N.A. | Stephanie | Stephen | N | Jun_25 SP Patch 2 (MTS 5.8.78) | 5.0.4-28 | ICE-XS.6.0.5.23 | 3.5.3.2 | 1.1.2.12 | 1.7.3.1 |  | SWIFT ISO20022 SAG Gateway 1.5.1.1 |  | CHIPS ISO20022 Gateway 1.1.2.2
Wells (EMTS-WEL/GMTS-WFI) | Christy | Celia | Y | June sp patch 2 base emts: WEL15 gmts: WFI24 | 5.0.4.28 | ICE-XS 06.00.5.23 | 5.0.4.20 | ISOFedBaseline:1.1.2.010 | MTSAdapterBaseline: 1.7.3.001 | Bank Adapter Scheme XSD:1.5.0.000 | n/a | ISOSwiftNetInteractSchemeXSD:1.3.2.014 | CHIPS ISO Baseline:1.1.2.002 | n/a
Zions Management Services Company | Christy | Christy | N | MTS 5.8.78 June SP Patch 4 | ISO_Jun25 UPF Patch 4 | ICE-XS-6.0.5.23 | 3.5.3.3 | 1.1.2.13 | 1.7.3.2 | 1.5.0.1 | 1.5.1.2 | 2.1.1.1 | 1.1.2.3 | 1.0.0.4

## Collaboration Principles (hidden)
Process
Step 1: The customer should open a case in support portal regardless of the priority Step 2: All calls go through Help24. Please do not take any troubleshooting or support calls via cell phone as it will be hard to track – significantly if it could affect other customers.
Room Layout:
ISO Go-Live Roles/Responsibilities
· Executive Lead (1) –ELT member Martina Powers/Anup Thomas
o Point of escalation and contact with customers that are in high critical states
· War Room Coordinators - Lolita Florence/Jeff Rawson and Bev Hrabik/Rahul Kulal
o Manage the war room – physically and virtual.
o Manage Help24 queue, P1’s, P2’s for immediate impact across the customer base
o Communication source for status – across the Program
o Facilitate triage work on all P1’s, P2’s with Triage Room (Physically located in Norcross office)
o Established reporting - internal - on status; verbal and written
o Dispatch P2 issues to identified project teams -****
o Point of contact for internal escalation
o Hand-off between leaders.
o Partner with all other teams to coordinate communication and process flow
· Help24 Team
o Partners with the war room in Norcross to support ISO customers as they go-live
o Intake all calls relating to issues faced in Production for Fed ISO change
· PS Project Teams
o Support of their customer – responsible for customer’s hours of business.
o Initial triage of issues
o Work through any reported issues, testing, replication
o Communication to customer
· PD Team
o In the event there are blockers or showstoppers reported, resolve to fix.
After hours support:
· All calls run through Help24
· Help24 will triage and try to resolve. In the event they cannot, they will call the appropriate on-call person associated with the project team.
o If project team needs Infrastructure – MTS or UPF – please review sheet for appropriate on call person.
o If on call person needs higher level of support or visibility, on-call war room coordinator is then called.
Open Questions
1. Will there be any swag for the individuals onsite?
2. Bev confirm ELT - done
3. Confirm status of dual monitors PD list - Chetan, Monique, Rahul, Neelima
4. Are rooms reserved? Reserved
5. Cubes need to be reserved
6. Order food
7. Lolita Confirmed (10 cubes with a monitor and 10 monitors on the shelf - Lolita will go into the office in the next few weeks to confirm setup.) we'll need to know names to look up computer names, to see what docks they will need, there's standard usb ones, then dev lenovos and dev dells, they need different types
Seating Chart: Reserved Saturn(10), Pluto(8), Neptune(8), Calypso(8), Mars(14) - Rooms to be used for breakout and working sessions. Mars - Command Center
Command Center - MARS

## CD Go Live Shifts & On-Call
All Times in Eastern
War Room Coordinator - SUPPORT
| 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28
Jeff Rawson | All Day | All Day |  | All Day | All Day | All Day | Holiday | Holiday
Lolita Florence |  |  |  | 8am - 130pm then back at 3pm - 5pm | All day until 5pm Phone, online via chat after | All Day | Holiday | Holiday
Denise Lunn | All Day | All Day | All Day- DE On Demand | All Day | All Day | Not available after 17:00 | Holiday | Holiday
Steve Riddick | All Day | All Day | All Day | All Day | All Day | PTO | Holiday | Holiday
Christy Purser | All Day | All Day - DE ON DEMAND | All Day | All Day | All Day | All Day | Holiday | Holiday
Stephanie Cox | PTO | PTO | PTO | PTO | PTO | PTO | Holiday | Holiday
On Call War Room Conference Room Coordinator
UPF / MTS - INFRASTRUCTURE
| 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28
Kevin Stillwell | Traveling | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Bill Polleys | Traveling | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Cameron Jackson | Traveling | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Carlos Castaneda Juan | Traveling | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Ananth Rajah | Traveling - 3PM- 12AM | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Siva Alugoju | 8 am - 5 pm | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Tomas Rojas | Traveling | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Umesh Sharma | 8 am - 5 pm | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Maykol Yara | Traveling | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Juan Mateus | 8 am - 5 pm | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
On Call MTS | Kevin Stillwell | Kevin Stillwell | Bill Polleys | Bill Polleys | Kevin Stillwell | Kevin Stillwell | Holiday | Holiday
On Call UPF | Maykol Yara | Umesh Sharma | Cameron Jackson | Ananth Rajah | Siva Alugoju | Tomas Rojas | Holiday | Holiday
APP CONFIG SUPPORT
| 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28
Jean Harty | 7 am - 6 pm | Traveling | 8 pm - 12:00 am | 6 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Denise Feeney | 7 am - 6 pm | On Call 6 am -6 pm | Traveling | 6 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
On Call App Config | Denise Feeney | Jean Harty | Denise Feeney | Jean Harty | Denise Feeney | Jean Harty | Holiday | Holiday
RTPS - A (REG, BBT/TRU, SCB)
| 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28
Phil Hegarty | 3 pm - 5 pm (Traveling) | On Call 6 am -6 pm | 8 pm - 12:00 am | 6 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Janet Zirpolo | 3 pm - 5 pm (Traveling) | On Call 6 am -6 pm | 8 pm - 12:00 am | 6 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Siva Alugoju | 8 am - 5 pm | On Call 6 am -6 pm | (On Call before 7PM) 8 pm - 12:00 am | 6 am -6 pm | 6 am -6 pm | 6 am -6 pm | Holiday | Holiday
Jean Harty | 7 am - 6 pm | Traveling | 8 pm - 12:00 am | 6 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Debalina Dogra | 7:30 am - 11:30 pm | On Call 8 am - 5PM | On Call | 8 am - 5 pm | 8 am - 5 pm | 8 am - 5 pm | Holiday | Holiday
Prabhu Paulraj | 8:00 am - 5:00 pm; 6:30 pm - 8:30 pm | 7:30 am - 10:30 pm Traveling in the afternoon | 8:00 pm - 11: 30 pm | 8:00 am - 5:00 pm | 8:00 am - 5:00 pm | 8:00 am - 5:00 pm | Holiday | Holiday
Primary Contact (BBT/TFC) Nisha Gaston | 2025-11-27: Holiday; 2025-11-28: Holiday
Primary Contact (Regions) Jason Howell | 2025-11-25: PTO; 2025-11-26: PTO; 2025-11-27: Holiday; 2025-11-28: Holiday
Primary Contact (SCB) Junaid Saeed Baig | bar: 2025-11-21 to 2025-11-26
On Call | 2025-11-27: Holiday; 2025-11-28: Holiday
RTPS - B (HNB, FNB, FNBO, CMA)
| 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28
Vishal Bute | 7:30 pm -12:00 am | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Debalina Dogra | 7:30 pm -12:00 am | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Prabhu Paulraj | 8:00 am - 5:00 pm; 6:30 pm - 8:30 pm | 7:30 am - 10:30 pm Traveling in the afternoon | 8:00 pm - 11: 30 pm | 8:00 am - 5:00 pm | 8:00 am - 5:00 pm | 8:00 am - 5:00 pm | Holiday | Holiday
Ananth Rajah | Business hours Traveling/ 7:30 pm - 12:00 am | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Jean Harty | 7 am - 6 pm | Traveling | 8 pm - 12:00 am | 6 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Primary Contact (HNB) Nisha Gaston | 2025-11-27: Holiday; 2025-11-28: Holiday
Primary Contact (FNB) Christy Diffey | 2025-11-27: Holiday; 2025-11-28: Holiday
Primary Contact (CMA) Dayro Andrade | 2025-11-27: Holiday; 2025-11-28: Holiday
Primary Contact (FNBO) Jason Howell | 2025-11-25: PTO; 2025-11-26: PTO
On Call | 2025-11-27: Holiday; 2025-11-28: Holiday
RTPS - C (MIZ, FHLBNY, UMB, SSC (Domestic)
| 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28
Scott Bobeck | Traveling | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Paula Boston | 8 am - 5 pm | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Neethu Sreekumar | 8 am - 1 pm | 8 am - 1 pm | 8 am - 1 pm | 7 am - 1 pm | 7 am - 1 pm | 7 am - 1 pm | Holiday | Holiday
Tomas Rojas | Traveling | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Umesh Sharma | 8 am - 5 pm | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Maykol Yara | Traveling | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Jean Harty | 7 am - 6 pm | Traveling | 8 pm - 12:00 am | 6 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Kevin Stillwell | Traveling | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Bill Polleys | Traveling | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Primary Contact - Wanda Shurson | 2025-11-27: Holiday; 2025-11-28: Holiday
On Call | 2025-11-27: Holiday; 2025-11-28: Holiday
RTPS - AOD (FHB, FHLBCIN, FHLBATL, FHLBDM, FSB, DNB)
| 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28
Anjanette Mayor | 8 am - 5 pm | 7 am - 12 pm | Traveling | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Debalina Dogra | 8 am - 5 pm | 7 am - 12 pm |  | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Prabhu Paulraj | 8:00 am - 5:00 pm; 6:30 pm - 8:30 pm | 7:30 am - 10:30 pm Traveling in the afternoon |  | 8:00 am - 5:00 pm | 8:00 am - 5:00 pm | 8:00 am - 5:00 pm | Holiday | Holiday
Tejas Tarawade | 8 am - 5 pm | 7 am - 12 pm |  | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Tomas Rojas | Traveling | 7 am - 12 pm |  | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Umesh Sharma | 8 am - 5 pm | 7 am - 12 pm |  | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Alex Kittenplan | 8 am - 5 pm | 7 am - 12 pm |  | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Primary Contact - Stephen Reeve | 2025-11-27: Holiday; 2025-11-28: Holiday
On Call | 2025-11-27: Holiday; 2025-11-28: Holiday
RTPS - E (FTB, ABC, CTZ)
| 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28
Brian Winn | 8 am - 5 pm | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Debalina Dogra | 8 am - 5 pm | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Primary Contact - Dayro Andrade | 2025-11-27: Holiday; 2025-11-28: Holiday
On Call | 2025-11-27: Holiday; 2025-11-28: Holiday
RTPS - F (Wells Fargo)
| 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28
Kim Roberts | 8 am - 5 pm | 8 am - 5 pm | 12 Noon - 8 PM | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Donna Kehoe | 8 am - 5 pm | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | on call | Holiday | Holiday
Harini Palugulla | 8 am - 5 pm | 5 pm to 12:01 am | 5 pm to 12:01 am | 5 pm to 12:01 am | 9 am - 7pm | 9 am - 7pm | Holiday | Holiday
Vaishali Thakur | Traveling | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Sharon McFarland | on call | on call | on call | 10 am - 2:00 pm | 10 am - 2:00 pm | 10 am - 2:00 pm | Holiday | Holiday
Juan Mateus | 7:30 pm - midnight | Midnight - 4:00 pm |  | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Prinary Contact - Terrie Travis | 8 am - 5 pm | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Primary Contat - Christy Purser | 8 am - 5 pm | 5 pm to 12:01 am | 5 pm to 12:01 am | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Primary Contact - Celia Christensen | 8 am - 5 pm | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
On Call | 2025-11-27: Holiday; 2025-11-28: Holiday
RTPS - G (NTC/NTP, ZIONS, FTN, CNB) & FNB
| 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28
John Berger | 8 am - 5 pm | 8 am - 5 pm | 8 am - 3 pm | 8 am - 5 pm | 8 am - 5 pm | 8 am - 5 pm | Holiday | Holiday
Amit Kulkarni | 8 am - 5 pm | 8 am - 5 pm | 8 am - 3 pm | 8 am - 5 pm | 8 am - 5 pm | 8 am - 5 pm | Holiday | Holiday
Cam Jackson | 8 am - 5 pm | 8 am - 5 pm | 8 am - 3 pm | 8 am - 5 pm | 8 am - 5 pm | 8 am - 5 pm | Holiday | Holiday
Brian Winn (NTC/NTP) | 8 am - 5 pm | 8 am - 5 pm | 8 am - 3 pm | 8 am - 5 pm | 8 am - 5 pm | 8 am - 5 pm | Holiday | Holiday
Primary Contact - Christy Diffey | PTO JBA | 8 am - 5 pm | 8 am to 3pm | 6 am - 6 pm | 8 am - 6 pm | 8 am - 6 pm | Holiday | Holiday
On Call | 2025-11-27: Holiday; 2025-11-28: Holiday
RTPS - H (BofA)
| 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28
Kristen Bagdasarian |  | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Jennifer Lytle |  | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Tim Joyce |  | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Siva Kanagashanmuga |  | apa |  |  | OOO | OOO | Holiday | Holiday
Soujanya Cherukupalli | 2025-11-27: Holiday; 2025-11-28: Holiday
Cam Jackson |  | 8 am - 5 pm | 8 am - 5 pm | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Primary Contact - Andrea Coyle | 5pm - 8am Sat | 8am - 3pm | 12:01am - 3pm | 12:01am - 7am | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
Primary Contact - Nasser Ospina | 8am - 5pm | 3pm - Midnight | 3pm - Midnight | 7 am - 6 pm | 7 am - 6 pm | 7 am - 6 pm | Holiday | Holiday
On Call | KB, JL, TJ, AC, NO | KB, JL, TJ, AC, NO | KB, JL, TJ, AC, NO | KB, JL, TJ, AC, NO | KB, JL, TJ, AC, NO | KB, JL, TJ, AC, NO | Holiday | Holiday
CITIZENS (CTZ)
| 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28
Carlos Castaneda | 9:00 pm - 12:00 am Saturday ET | 8:00 am - 6:00pm ET | 8:00am - 4:00pm ET |  |  |  | Holiday | Holiday
Brian Winn | 9:00 pm - 12:00 am Saturday ET | 8:00 am - 6:00pm ET | 8:00am - 4:00pm ET |  |  |  | Holiday | Holiday
John Berger | 2025-11-27: Holiday; 2025-11-28: Holiday
Primary Contact - Dayro Andrade | 2025-11-27: Holiday; 2025-11-28: Holiday
On Call | 2025-11-21: Carlos, Brian; 2025-11-22: Carlos, Brian; 2025-11-27: Holiday; 2025-11-28: Holiday
BNPPF
| 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28
Ketan Bibave | 09:00 - 17:00 CET | All day CET |  | 09:00 - 17:00 CET | 09:00 - 17:00 CET | 09:00 - 17:00 CET | 09:00 - 17:00 CET | 09:00 - 17:00 CET
Jim Gordon | 09:00 - 17:00 CET |  | All day CET | 09:00 - 17:00 CET | 09:00 - 17:00 CET | 09:00 - 17:00 CET | 09:00 - 17:00 CET | 09:00 - 17:00 CET
Anthony Tornambe | 09:00 - 17:00 CET |  |  | 03:00AM CET onwards | 09:00 - 17:00 CET | 09:00 - 17:00 CET | 09:00 - 17:00 CET | 09:00 - 17:00 CET
Primary Contact - Ludmila Kheyar |  | All day CET | All day CET | All day CET | 09:00 - 17:00 CET | 09:00 - 17:00 CET | 09:00 - 17:00 CET | 09:00 - 17:00 CET
Note on B24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Florence, Lolita How can Kevin be our on call support person if he is traveling? Thanks! Reply: I am not updating this tab. This will be done by the PMs.

## PD Coverage (hidden)
All Times in Eastern
War Room Coordinator - SUPPORT
| SME | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02
Neelima Inti | Mgt | 9am - 6 pm | 9am - 5pm | 10am - 2pm 8pm-12am | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm
Bev Hrabik | PM | Remote | Traveling | 10am - 2pm 8pm-12am | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | Traveling | Off Site Support
Rahul Kulal | PM | 9am - 6 pm | 9am - 5pm | 10am - 2pm 8pm-12am | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm
US On Call War Room Coordinator - Rahul Kulal
EI/India On Call War Room Coordinator - Saumya Reddy
On Site Support
| SME | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02
Don Beer | Architect | Remote | Remote | Remote | Traveling | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm
Tushar Bhatia | Architect | 9am - 5pm | 9am - 5pm | 10am - 2pm 8pm-12am | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | Travelling
Sandra Boddy | MTS QE | N/A | Traveling | 12pm - 2pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | Treveling | Remote | Remote | Remote
Ram Boga | Mgt | 9am - 5pm | Remote | 12pm - 2pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm
Mamatha Govindaraju | MTS QE | 9am - 5pm | 9am - 5pm | 12pm - 2pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm
Yoga Govindaraju | CC QE | 9am - 5pm | 9am - 5pm | 12pm - 2pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm
Alina Grui | Mgt | 9am - 5pm | Remote | 12pm - 2pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | Remote | Remote | Remote | Remote
Monique Hassett | MTS QE | Traveling | 9am - 6 pm | 12pm - 2pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | Traveling | Remote | Remote | Remote
Chetan Konka | CC Eng | 9am - 6 pm | 9am - 6 pm | 12pm - 2pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | Traveling | Remote | Remote | Remote | Remote
EU/India Remote Support (follow the sun)
| SME | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02
Ingo Biggs | MTS Eng | 9pm - 6am | N/A | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | If required | 9pm - 6am | 9pm - 6am | 9pm - 6am
Denis Broderick | MTS Eng | 9pm - 6am | N/A | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | If required | 9pm - 6am | 9pm - 6am | 9pm - 6am
Jisna Janardhanan | MTS QE | 9pm - 6am | N/A | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | If required | 9pm - 6am | 9pm - 6am | 9pm - 6am
Varalakshmi Narayanaswamy | CC QE | 9pm - 6am | N/A | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | If required | 9pm - 6am | 9pm - 6am | 9pm - 6am
Hari Shankar Pankajakshan | SM | 9pm - 6am | N/A | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | If required | 9pm - 6am | 9pm - 6am | 9pm - 6am
Saumya Reddy | SM | 9pm - 6am | N/A | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | If required | 9pm - 6am | 9pm - 6am | 9pm - 6am
Marina Reyder (US Based) | MTS Eng | 7am - 6pm | N/A | N/A | 7am - 6pm | 7am - 6pm | 7am - 6pm | 7am - 6pm | 7am - 6pm | If required | 7am - 6pm | 7am - 6pm | 7am - 6pm
Sayan Sadhukhan | GW Eng | 9pm - 6am | N/A | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | 9pm - 6am | If required | 9pm - 6am | 9pm - 6am | 9pm - 6am

## PM Coverage & SWIFT ISO (hidden)
Support Hours - All Times in Eastern
War Room Support
| Role | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20
Amy Haney | Sr Product Manager | TBD | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | TBD | TBD
Adam Needel | Subsegment Leader | TBD | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | TBD | TBD
On Site Support
| Role | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20
Joseph Carey | Fedwire PO | TBD | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | TBD | TBD
Divalkar Chandru | Fedwire PO | TBD | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | TBD | TBD
Ashutosh Gupta | Fedwire PO | TBD | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | TBD | TBD
Neel Soni | Control Center PO | N/A | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | TBD | TBD
Jerry Bao | PO | N/A | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | 7am - 6 pm | TBD | TBD
Jessica O'Rourke | Director
Tony Smith | Director
Triage Artifacts and References
Fed ISO Artifacts & Triage Resources - Main Sharepoint
Quicklink for Fed Docs

## Checkpoint Call Schedule (hidden)
Day | ACI Internal Customer Update | ACI ELT Update
Day 1 (Every 2 hour) | 8am, 10am, 12pm, 2pm, 4pm, 6pm | 930am, 1130am, 130pm, 330pm, 530pm, 730pm
Day 2 (Every 3 hours) | 9am, 12am, 3pm, 6pm | 930am, 1230am, 330pm, 630pm, 730pm
Day 3 – 5 Call-in Times | 12pm and 6pm | 1pm and 7pm

## Stakeholder Update (hidden)
Template
FED ISO– Go Live Status Update, mm/yy – 12:00 (EST)
Go Live Overall Status GREEN/Yellow/RED
Notes:
IE: All customers have communicated they are receiving ISO formatted messages.
Cases:
Number P1 issues – ##
Number P2 issues - ##
FED ISO Go live has started The teams are actively preparing in Norcross GA, and virtually, to support our banks. I wanted to explain the communication plan for this group during the first few days of go-live. Updates will be sent every two hours for the first day of go-live (4/8), then every 3 hours for the following two days, then daily - unless issues present themselves to increase frequency. In the event there are many large issues, updates will increase in frequency. Expect the following format: FED ISO – Go Live Status Update, mm/yy – 12:00 (EST) Go Live Overall Status GREEN Notes: • All customers have communicated they are receiving ISO formatted messages. Cases: • Number P1 issues – ## • Number P2 issues - ##
`
Column1 | Status | # Issues (P1) | # Issues (P2) | # Issues (P3) | Last Check-In
Technical Go Live Project Health by Customer
Customers | Program RAG | Updates | PM | SM/DE |  | Stakeholder List
Bank of America |  |  | Andee |  |  | TO:
Citizens Bank |  |  | Dayro |  |  | tom.warsop@aciworldwide.com
Huntington National Bank |  |  | Nisha |  |  | erich.litch@aciworldwide.com
Truist Bank |  |  | Nisha Howard |  |  | abe.kuruvilla@aciworldwide.com
Wells (EMTS-WEL) |  |  | Raja/Celia |  |  | martina.power@aciworldwide.com
Wells (GMTS-WFI) |  |  | Raja/Celia |  |  | anup.thomas@aciworldwide.com
Regions | Green | They started work at 7 pm, 7/11 finished at 8:30pm They will be on the Fed calls today and Sunday. The only work for Regions this weekend is Sunday night Cliff and Tony Dillion will check their queues. | Jason |  |  | scotty.perkins@aciworldwide.com
Zions Management Services Company |  |  | Christy |  |  | craig.maki@aciworldwide.com
First National Bank of Omaha |  |  | Nisha Howard |  |  | dennis.byrnes@aciworldwide.com
Federal Home Loan Bank of Atlanta |  |  | Stephen |  |  | CC:
DnB Nor - NY Branch |  |  | Stephen |  |  | nathan.brown@aciworldwide.com
Federal Home Loan Bank-Cincinnati |  |  | Stephen |  |  | steve.riddick@aciworldwide.com
Federal Home Loan Bank-Des Moines |  |  | Stephen |  |  | Jeff.Rawson@aciworldwide.com
First Hawaiian Bank |  |  | Stephen |  |  | Neelima.Inti@aciworldwide.com
Flushing Savings Bank |  |  | Stephen |  |  | bev.hrabik@aciworldwide.com
jaime.danielson@aciworldwide.com
Go Live Project Health by Customer | [5 empty] | anne.welch@aciworldwide.com
amy.haney@aciworldwide.com
Customers | Program RAG | CHIPs Go Live | Updates | SM/DE |  | alina.gugu@aciworldwide.com
Adam.Needel@aciworldwide.com
rammurthy.boga@aciworldwide.com
craig.ramsey@aciworldwide.com
denise.lunn@aciworldwide.com
sai.kalaga@aciworldwide.com
erin.woosley@aciworldwide.com
matt.addison@aciworldwide.com
matthew.grech@aciworldwide.com
jean.espinal@aciworldwide.com
melvin.renderos@aciworldwide.com
matthew.tannahill@aciworldwide.com
peter.lee@aciworldwide.com
james.mcilhagga@aciworldwide.com

## Technical Go Live Update Templa (hidden)
FED ISO – Technical Go Live Status Update, mm/yy – (Please provide at the beginning and end of day unless help is needed.)
a. Go Live Overall Status: Green and stable
b. Customer Temperature: Green and stable
c. Notes:
BOA started their technical go live on time at 8pm ET
ACI and BoA Resources are on a joint war room and all contact numbers have been provided.
d. Cases:
Number of P1 Issues: None at this time
Number of P2 Issues: None at this time
e. Help Needed: None at this time

## PM Fed Go Live Update Template (hidden)
|  |  |  | FED ISO Transactions |  |  | SF Priority Cases
Technical Go Live Status (Green, Amber, Red) | FED ISO Go Live Status (Green, Amber, Red) | As of Date, Time | Status Summary | # Inbound | # Outbound | ACI Support Requested | P1 | P2 | P3 | Next Status Update
N/A | Green | 8AM ET, 7/14/25 | Monitoring Receipt of PROD ISO formatted messages | 12 | 3 | Joint triage requested 7:45am, issue resolved | 01234567 | 01234568 | 01234569 | 10AM ET, 7/14/25
|  | 8AM ET, 7/14/25 | [7 empty] | 10AM ET, 7/14/25
|  | 10AM ET, 7/14/25 | [7 empty] | 12PM ET, 7/14/25
|  | 12PM ET, 7/14/25 | [7 empty] | 2PM ET, 7/14/25
|  | 2PM ET, 7/14/25 | [7 empty] | 4PM ET, 7/14/25
|  | 4PM ET, 7/14/25 | [7 empty] | 6PM ET, 7/14/25
|  | 6PM ET, 7/14/25 | [7 empty] | 8AM ET, 7/15/25
|  | 8AM ET, 7/15/25 | [7 empty] | 11AM ET, 7/15/25
|  | 11AM ET, 7/15/25 | [7 empty] | 2PM ET, 7/15/25
|  | 2PM ET, 7/15/25 | [7 empty] | 5PM ET, 7/15/25
|  | 5PM ET, 7/15/25 | [7 empty] | 12PM ET, 7/16/25
|  | 12PM ET, 7/16/25 | [7 empty] | 6PM ET, 7/16/25
|  | 6PM ET, 7/16/25 | [7 empty] | 12PM ET, 7/17/25
|  | 12PM ET, 7/17/25 | [7 empty] | 6PM ET, 7/17/25
|  | 6PM ET, 7/17/25 | [7 empty] | 12PM ET, 7/18/25
|  | 12PM ET, 7/18/25 | [7 empty] | 6PM ET, 7/18/25
6PM ET, 7/18/25

## Communication Plan (hidden)
General Communication Plan
ISO Team Chat Room
On Call Bridge
Note book creation
BANK Contact Sheet
Customer | On Prem / AOD | Delivery Exec | Bank - Sr Contact Name | Bank Sr Contact Title | Bank Sr Contact E-mail
Agricultural Bank of China | On Prem |  | Pengfei Cong | Head of IT | congpengfei@abchinausa.com
Bank of America | On Prem | Denise Lunn | Andrew McKibben | Managing Director; GCIB/GPS Technology CIO and International Head of Technology | andrew.mckibben@bofa.com
Bank of America | On Prem | Denise Lunn | Waymon Chen | Managing Director; AMRS Payment & Core Cash Technology and Head of LATAM & Canada Tech | waymon.n.chen@bofa.com
Bank of America | On Prem | Denise Lunn | Kumar Subramanyan | Managing Director; US Payments Technology | kumar.subramanyan@bofa.com
Citizens Bank | On Prem |  | Maria Mason | Senior Digital Product Director, Senior Vice President | Maria.Mason@CitizensBank.com
City National Bank | On Prem |  | Eric Sandoz | SVP, Head of Core Payments & Treasury Technology | Eric.Sandoz@cnb.com
Comerica Bank | On Prem |  | Sheila Card-Jones | SVP, Director of Global Funds Transfer | sdcard-jones@comerica.com
DnB Nor - NY Branch | AOD | Jeff Rawson | Asbjorn Ure | Department Head | asbjorn.ure@dnb.no
Federal Home Loan Bank - NY | On Prem | Jeff Rawson | Anastasiya Svyatova | AVP, Bank Operations Project Services | anastasiya.svyatova@fhlbny.com
Federal Home Loan Bank of Atlanta | AOD | Jeff Rawson | Wendy Eversley | Director of Safekeeping, EPayments & Compliance | weversley@fhlbatl.com
Federal Home Loan Bank of Cincinnati | AOD | Jeff Rawson | Diane Halpin | Correspondent Services Officer | HalpinDM@fhlbcin.com
Federal Home Loan Bank of Des Moines | AOD | Jeff Rawson | Cherie Schuler | Senior Director Member and Financial Operations | cschuler@fhlbdm.com
Fifth Third Bank | On Prem |  | Rodney Baker | Vice President, IT Director – Treasury Management' | Rodney.Baker@53.com
First Hawaiian Bank | AOD | Jeff Rawson | Ed Char | Vice President and Digital Payments Operations Manager | echar@fhb.com
First Horizon Bank | On Prem |  | Nancy Bradley | Sr Vice President, Director of Payment & Process Operations | nebradley@firsthorizon.com
|  |  | RAMSON, JAMES E | VP, Payables Product Team Lead | JERamson@firsthorizon.com
First National Bank of Omaha | On Prem |  | Sammy Sufian | SVP Technology | ssufian@fnbo.com
Flushing Savings Bank | AOD | Jeff Rawson | Barbara Beckmann | Executive Vice President - Director of Operations | bbeckmann@flushingbank.com
Frost National Bank | On Prem |  | Tarun Dewan | SVP, Head Digital Channels and Payments | Tarun.Dewan@frostbank.com
|  |  | Linda Albornoz | CIO | Linda.Albornoz@frostbank.com
Huntington National Bank | On Prem |  | Adriana Hastings | EVP, Treasury Management Director | Adriana.Hastings@huntington.com
Mizuho Bank | On Prem | Jeff Rawson | Rob Fasanello | Head of Corporate Application Services | Robert.Fasanello@mizuhogroup.com
Northern Trust Bank - New York | On Prem |  | Farooq Jawaid | Chief Information Officer – Cash & Corporate Services | fj16@ntrs.com
|  |  | Natarajan Muralidharan | Head of Cash Technology ¦ Cash and Corporate Services | nm177@ntrs.com
Regions | On Prem |  | Franklin Danley | EVP, Head of Payment Operations | franklin.danley@regions.com
Standard Chartered Bank - New York | On Prem | Ka Fui Chin | Ivy Yee | Head of Technology - Liquidity, Collections, Billing & Pricing, FI Clearing, Messaging and Payment Utilities | ivy.yee@sc.com
Standard Chartered Bank - New York | On Prem | Ka Fui Chin | Venkat Raghavan | CIO, Cash | venkat.raghavan@sc.com
State Street | On Prem | Jeff Rawson | Jay Fulchino | Executive Vice President and Head of Custody and Centralized Services | jfulchino@StateStreet.com
|  |  | Kartikesh Herur | Executive Vice President and Chief Information Officer | KHerur@StateStreet.com
|  |  | Brian Franz | Chief Information Officer and Head of Enterprise Resiliency | bfranz@statestreet.com
Truist Bank | On Prem |  | Venkat Banu | SVP, Global Head of Payment Technology | Banu.Venkat@truist.com
UMB Bank | On Prem | Jeff Rawson | Uma Wilson | Executive Vice President, Chief Information & Product Officer | Uma.Wilson@umb.com
Wells Fargo (EMTS) | On Prem | Jeff Rawson | Sarah Berwick | CIO Commercial and Corporate & Investment Banking Technology | Sarah.Berwick@wellsfargo.com
Wells Fargo (GMTS) | On Prem | Jeff Rawson | Sarah Berwick | CIO Commercial and Corporate & Investment Banking Technology | Sarah.Berwick@wellsfargo.com
Zions Management Services Company | On Prem |  | Frank Dipuma | EVP, Director of Enterprise Corporate Treasury Manager | frank.dipuma@zionsbancorp.com

## P2 Case Burndown (hidden)
Customer | Key | Internal Ref ID | Links | Priority | Status | Summary | Created | Go Forward Plan | Targeted Date Out of Development | Targeted Date Out of Development2

## P1_P2 Case Summary (hidden)
Customer | JIRA ID | P1/P2 | Owner | Group | Status | Summary | Notes/Resolution | Why was this not caught early?

## Technical Go Live (hidden)
Customer​ | PM/ Delivery Executive​ | Implementation Plan Delivery Date | Technical Go-Live Date ​ | First Transaction (EST)
Comerica Bank | Gene/Dominic
Bank of America | Andee/Christine
Citizens Bank | Dayro/Christine
Huntington National Bank | Nisha/Dominic
Northern Trust Bank - New York NTC | Celia/Christine
Truist Bank | Gene/Dominic
Wells (EMTS-WEL) | Raja/Celia/Jeff
Wells (GMTS-WFI) | Raja/Celia/Jeff
Mizuho Bank | Wanda/Jeff
First Horizon Bank | Christy/Christine
UMB Bank N.A. | Wanda/Jeff
Federal Home Loan Bank-NY | Wanda/Jeff
Fifth Third Bank | Dayro/Christine
Frost National Bank | Christy/Dominic
Regions | Gene/Dominic
State Street Domestic | Wanda/Jeff
Zions Management Services Company | Christy/Christine
Standard Chartered Bank New York | Nisha/Dominic
Agricultural Bank of China | Dayro/Christine
City National Bank | Christy/Christine
First National Bank of Omaha | Nisha/Dominic
Federal Home Loan Bank of Atlanta | Stephen/Jeff
DnB Nor - NY Branch | Stephen/Jeff
Federal Home Loan Bank-Cincinnati | Stephen/Jeff
Federal Home Loan Bank-Des Moines | Stephen/Jeff
First Hawaiian Bank | Stephen/Jeff
Flushing Savings Bank | Stephen/Jeff

## On-Call Contact Information
War Room Coordinator | Contact Details
Lolita Florence | 404.734.7194
Bev Hrabik | 402.301.1121
Rahul Kulal | 402.306.6957
Jeff Rawson | 402.318.1765
Denise Lunn | 402.968.3867
Christy Purser | 404-805-6273
Steve Riddick | 404.955.7467
Adam Needel | 402.321.9741
Amy Haney | 404-259-6484
INFRASTRUCTURE | Contact Details
Kevin Stillwell | 214.205.0487
Bill Polleys | 781-439-2861
Cameron Jackson | 801.884.3515
Carlos Castaneda Juan | 402.686.5002
Ananth Rajah | 416 930 4430
Siva Alugoju | 317.440.3364
APP SUPPORT | Contact Details
Jean Harty | 617.901.9603
Denise Feeney | 617.872.0118
SA/TC SUPPORT | Contact Details
Kristen Bagdasarian | 617.930.2164
Jennifer Lytle | 303.472.8597
Tim Joyce | 929.706.7095
Alex Kittenplan | 617 930 8279
John Berger | 508.397.1676
Scott Bobeck | 863.873.0026
Paula Boston | 203.470.1030
Phil Hegarty | 508.361.7595
Donna Kehoe | 617.438.6533
Amit Kulkarni | 678.600.1415
Anjanette Mayor | 805.387.5006
Sharon McFarland | 415.408.1012
Prabhu Paulraj | 215.326.9595
Kim Roberts | 720.560.4170
Vaishali Thakur | 203.998.8777
Harini Palugulla | 573.578.4251
Brian Winn | 336.413.3008
Janet Zirpolo | 617.971.6183
Jim Gordon | +44 7408 868945
Vishal Bute | 647.448.6266
Anthony Tornambe | +44 7920 475980
Tomas Rojas | 531.800.4530
Umesh Sharma | +91-7303088950
Sai Vijay | +52 56 6230 6710
Client Project Managers | Contact Details
Dayro Andrade | +573 002 004 784
Andee Coyle | 402.578.3905
Celia Christensen | 512.497.0831
Terrie Travis (PO for wells) | +1 817 680 9459
Christy Diffey | 706-888-9238
Stephen Reeve | 603-340-0903
Alanicia Howard | 770.366.1544
Nasser Ospina | 404.923.6100
Jason Howell | 614.402.7616
Lim, Kheng Teong | +60122307363
Saeed Baig, Junaid | 346.681.9866
Product Management | Contact Details
Divalkar S Chandru | 848.228.6867
Ashutosh Gupta | 704.791.6099
Joe Carey | 617.935.4368
Neel Soni
Jerry Bao | 817-235-5929
Product Development | Contact Details
Neelima Inti | 402.321.7630
Rahul Kulal | 402.306.6957
Saumya Reddy | 91 9619858809
Bev Hrabik | 402.301.1121
Ram Boga | 770.885.8662
Alina Grui | 402.516.2016
Srini Pembarthi | 91 9948664977
Hari Shanker Pankajakshan | 061-260852
BNPPF On-Call Team | Contact Details
Ketan Bibave | +91 (99) 6086 2450
Jim Gordon | +44 (0)7408 868 945
Anthony Tornambe | +44 (0)7920 475 980
Ludmila Kheyar | +33 (7) 7730 54 50

## Go Live Updates
| November Mandates Go Live RAG Status & Update |  |  | November Mandates Go Live RAG Status & Update | [10 empty] | November Mandates Go Live RAG Status & Update | [8 empty] | November Mandates Go Live RAG Status & Update
11/23 - 11/26 | 2025-11-23 |  |  | 2025-11-24 | [10 empty] | 2025-11-25 | [8 empty] | 2025-11-26
Bank | 11/23 Overall Status (RAG) | 10pm Update | 11/23 COMMENTS | Overall Status (RAG) | 8am Update | 9am Update | 10am Update | 12pm Update | 2pm Update | 3pm Update | 4pm Update | 6pm Update | 8pm Update | 11/24 COMMENTS | Overall Status (RAG) | 8am Update | 10am Update | 12pm Update | 2pm Update | 4pm Update | 6pm Update | 8pm Update | 11/25 COMMENTS | Overall Status (RAG) | 9am Update | 10am Update | 12pm Update | 2pm Update | 5pm Update | 6pm Update | 11/26 COMMENTS
Agricultural Bank of China (ABC) | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
Bank of America | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
BNPPF | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
Citizens Bank | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
City National Bank (CNB) | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
Comerica | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
Fifth Third Bank | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
First Hawaiian Bank (AOD) | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
First Horizon Bank | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
First National Bank of Omaha (FNBO) | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
Frost National Bank | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
Huntington National Bank | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
Mizuho Bank | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
Northern Trust Bank - NTC | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
Regions | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
Republic Bank (AOD) | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
Standard Chartered Bank New York (SCB, SCG, SCJ ) | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
State Street Bank (Global/Domestic) | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
Truist Bank | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
UMB Bank N.A. | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
Wells (EMTS-WEL/GMTS-WFI) | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported
Zions Management Services Company | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported |  | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported | Not Reported

## Guaranteed Message Configured (hidden)
GM Enabled | Customer | Further Data
Bank of America (RTPS)
Fifth Third Bank (RTPS)
Northern Trust Bank - New York NTC (RTPS)
State Street (RTPS)
Mizuho Bank
Standard Chartered Bank New York
Truist Bank (RTPS)
Wells(EMTS-WEL) (RTPS)

## Milestone (hidden)
Customer Name | Status - Risk, Ticket Count | Fix Pack Version | Snapshot Y/N | Gateway - SAA/SAG/OTHER | Plan Version | Region | Delivery Executive | Technical Go-LIVE Date | UPF On | ISO 'On' | Implementation Details - Include UPF Components | Revised Plan - Meeting/Reviewed
Bank of America (RTPS)
Fifth Third Bank (RTPS)
Northern Trust Bank - New York NTC (RTPS)
State Street (RTPS)
Mizuho Bank
Standard Chartered Bank New York
Truist Bank (RTPS)
Wells(EMTS-WEL) (RTPS)

## First Request Onsite (hidden)
Amit Kulkarni
Ananth Rajah
Anjanette Mayor
Brian Winn
Cameron Jackson
Carlos Castaneda
Damo Vaddeppalli
Debalina Dogra
Denise Feeney
Janet Zirpolo
Jean Harty
Jennifer Lytle
John Berger
Kristen Bagdasarian
Paula Boston
Phil Hegarty
Prabhu Paulraj
Scott Bobeck
Siva Alugoju
Suraj Bothe
Tim Joyce
Tomas Rojas III