## Sheet1
ACI list of Issues Discussed in July on site | State Street comments 9/8 | Category | Owner of Next Step
Operational Review | n/a - no follow up needed | No follow up needed | n/a
MTS Training Certification: Set a training call with Debasish and Venkata on Control Center and SAML | ACI please suggest timing for this session | Prod support | ACI
New Global Instance | SSD in progress | New Global Instance | ACI / State Street
ACI needs to understand additional International volumes for proper sizing | To be provided in SSD discussions | New Global Instance | State Street
New ABA Account | In progress with PCS team | PCS - in progress | ACI / PCS
Determine if New MTS Instance is required | Duplicate? ACI: Is this the same as the Global RTPS approach?? I'm not aware of any other reason for a new MTS instance beside the new Global RTPS instance | No follow up needed | n/a
New Book Tran Code | In progress with PCS team | PCS - in progress | ACI / PCS
Boston Accts from Hogan to Transact | In progress with PCS team | PCS - in progress | ACI / PCS
Determine approach on Global RTPS | SSD discussions | New Global Instance | ACI / State Street
Commercial Productization | ACI to schedule follow up discussion re: CHATS/Taiwan etc | Product | ACI
ACI to review Pelican rules to determine if rules can be used or if at point of payment initiation to eliminate the need for Pelican end point | State Street would like a review/discussion with ACI to see how we can do enrichment without Pelican for International and US. | Processing rules | ACI
State Street would like a call set up on simplifying the nostro | To be discussed as part of the SSD discussions | New Global Instance | ACI / State Street
State Street would like a call set up on how to handle unauthorized messages and the unhappy path | To be discussed as part of the SSD discussions | New Global Instance | ACI / State Street
State Street would like a call on how our correspondent banking product works | To be discussed as part of the SSD discussions | New Global Instance | ACI / State Street
ACI to provide examples of processing rules |  | Processing rules | ACI
State Street would like sample cross bank use cases | SS asked in the session if there is any existing material which describes the intercompany “single TRN” solution. If ACI has material please send it, otherwise SS will review the ACI solution document (committed for later in Sept). | Processing rules | ACI
State Street to send us their tranche scheduling on Boston | SS to send when tranches are finalized | Misc | State Street
Explore the option of the RGW database for International (static data) until move to Control Center | State Street would like to use RGW database for International (Similar to US/Domestic). ACI to sugget timing for a discussion | Prod support | ACI
DataCenter move Opportunity | State Street wants to use Public Cloud for New Global Instance. This can be part of the SSD discussions | New Global Instance | ACI / State Street
Set up a consulting call with product and aci chief architect | Per Matt: We can reach out organically, we have each others contact information and can do that as needed. No need for a dedicated meeting. | No follow up needed | n/a
Design solution to speed up Requirements Document creation | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
HK Chats Alternate Network | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
Enterprise ISO 20022 Structured Address | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
ISO 20022 Mandates Enhanced Data 2026 | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
ISO 20022 Mandates Enhanced Data 2027 | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
Enterprise ISO 20022 Structured Remittance | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
US RTPS Customer and Counterparty Ref Data Model | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
US RTPS Batch Payment Modernization | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
US RTPS Remaining Surrounding Sys Integration | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
GWH Banking/ Intercompany Posting System | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
INTL RTPS Design Optimum Int Branch | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
INTL RTPS Customer and Counterpay | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
INTL RTPS Integration with DWH SSCD | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
INTL RTPS Integration with ACE Pelican | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
INTL RTPS Interface Isolation with Gateway | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
INTL RTPS Full Payment Engine Cofiguration | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
INTL RTPS with Transact branch by branch | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
INTL RTPS Incoming Payment Settlement Model | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
INTL RTPS Surrounding System Integration | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
Direct Clearing Marketing Expansion | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street
Payment Status Messaging | Roadmap items SS needs to prioritze | Roadmap Prioritization | State Street