## International Plan
Task Name | Duration | Start | Finish | Predecessors | Resource
International Bank Adaptor Project
International Delivery
SSD Document Send for bank signoff ( International) |  | 2025-05-30
[DEMO] ACI: Technical ACK/NACK (International Env) |  | 2025-06-05
Deliver Documentation |  | 2025-06-03
ACI Configurations (UPF/APP) | 5 days
ACI Internal Control Center Config |  |  |  |  | PCS
ACI Internal UPF Config LON-CHAPS | TBD | J | TBD |  | PCS
Connectivity Testing (E2E) LON-CHAPS | 4 days | TBD |  |  | PCS
QA Testing LON-CHAPS | 10 days | 2025-07-07 | 2025-07-07 |  | Katheya /PCS
ACI Internal UPF Config MUN-TARGET2 | TBD | 2025-05-19 | TBD |  | PCS
Connectivity Testing (E2E) MUN-TARGET2 | 4 days | TBD |  |  | PCS
QA Testing MUN-TARGET2 | 10 days | TBD |  |  | Katheya /PCS | check with jean about testing will done after 30 july or befor
ACI Internal UPF Config SYD-RITS | TBD | 2025-05-19 | TBD |  | PCS
Connectivity Testing (E2E) SYD-RITS | 4 days | TBD |  |  | PCS
QA Testing SYD-RITS | 10 days | TBD |  |  | Katheya /PCS
ACI Internal UPF Config TOR-LYNX | TBD | 2025-05-19 | TBD |  | PCS
Connectivity Testing (E2E) TOR-LYNX | 4 days | TBD |  |  | PCS
QA Testing TOR-LYNX | 10 days | TBD |  |  | Katheya /PCS
ACI Internal UPF Config HON-CHATS | TBD | 2025-05-19 | TBD |  | PCS
Connectivity Testing (E2E) HON-CHATS | 4 days | TBD |  |  | PCS
QA Testing HON-CHATS | 10 days | TBD |  |  | Katheya /PCS
ACI Internal UPF Config TAI-FISC | TBD | 2025-05-19 | TBD |  | PCS
Connectivity Testing (E2E) TAI-FISC | 4 days | TBD |  |  | PCS
QA Testing TAI-FISC | 10 days | TBD |  |  | Katheya /PCS
ACI Internal App Config ALL | 10 days | 2025-06-15 | 2025-06-21 |  | Jean
SOA Server configuration disucssion | 1 | 2025-06-11 |  |  | Amit
Create Test Scripts LON-CHAPS |  |  |  |  | Katheya /PCS
UPDATE ACI UPF ENV For Jun Service Pack (All markets ) ????? |  | 2025-07-01 |  |  | Umesh / Maykol | CHECK umesh duration product release for product release
Smoke Testing LON-CHAPS | 2 days | TBD |  |  | Katheya /PCS
Smoke Testing MUN-TARGET2 | 2 days | TBD |  |  | Katheya /PCS
Smoke Testing SYD-RITS | 2 days | TBD |  |  | Katheya /PCS
Smoke Testing TOR-LYNX | 2 days | TBD |  |  | Katheya /PCS
Smoke Testing HON-CHATS | 2 days | TBD |  |  | Katheya /PCS
Smoke Testing TAI-FISC | 2 days | TBD |  |  | Katheya /PCS
Delivery |  | TBD
Build | 2 days | TBD |  |  | Oscar H
Code Delivery to | 2 days | TBD
Product Scheduled Release (Customer Support Testing Incident) | 17 days | TBD

## Domestic Plan
Task Name | Duration | Start | Finish | Predecessors | Resource
Plan Below if the bank requires a New BIS line
SSB/SSI Bank Adaptor Project
Domestic Delivery
Requirement Document by the Bank
SSD Document under ACI interal review
ACI Configurations (UPF/APP) | 5 days
ACI Internal Control Center Config
ACI Internal UPF Config | 3 days | TBD
ACI Internal App Config | 3 days | TBD
Testing
Connectivity Testing (E2E) | 4 days | TBD
QA Testing | 10 days | TBD
Smoke Testing | 2 days | TBD
Delivery |  | TBD
Build | 2 days | TBD
Code Delivery to | 2 days | TBD
Product Scheduled Release (Customer Support Testing Incident) | 17 days | TBD
Plan Below if the bank uses existing BTR line
SSB/SSI Bank Adaptor Project
Domestic Delivery
Requirement Document by the Bank
SSD Document under ACI interal review
SSD Signoff by SSB
[DEMO] ACI: Control Center exception handling (Domestic Int)
Deliver Documentation
ACI Configurations (UPF/APP) | 5 days
ACI Internal Control Center Config
ACI Internal UPF Config | 3 days | TBD
ACI Internal App Config | 3 days | TBD
Testing
Connectivity Testing (E2E) | 4 days | TBD
QA Testing | 10 days | TBD
Smoke Testing | 2 days | TBD
Delivery |  | TBD
Build | 2 days | TBD
Code Delivery to | 2 days | TBD
Product Scheduled Release (Customer Support Testing Incident) | 17 days | TBD