## ACI CHAPS - RTPS Ent ISO
Issue Type | Issue key | Summary | Outcome | Status | Due Date | Assignee | Parent summary
[SCRUM] Story | PACSH-78449 | [DEMO] ACI: Consume Outbound CHAPS Payment instr MX + send UPF Technical Acknowledgments | RTPS upgraded to consume Outbound Payment Instr. and send Acknowlegments back. Show working model and provide documention as input to State Street IT team Scope: pacs.008 | In Development | 2025-06-04 | ACI | ACI Deliverables - RTPS Ent ISO
[SCRUM] Story | PACSH-82101 | ACI - Enable CHAPS Outbound Payment Processing lines in MTS [Tech] | MTS component of RTPS upgraded to consume & process Outbound CHAPS Payment Instr. in ISO MX format via ACI RTPS Bank Adapter. | Not Started | 2025-07-31 | ACI | ACI Deliverables - RTPS Ent ISO
[SCRUM] Story | PACSH-82101 | ACI - Enable CHAPS Outbound Payment Processing lines in UPF (Platform Mgr + config Builder) [Tech] | UPF component of RTPS upgraded to consume & process Outbound CHAPS Payment Instr. in ISO MX format via ACI RTPS Bank Adapter. | Not Started | 2025-07-31 | ACI | ACI Deliverables - RTPS Ent ISO
[SCRUM] Story | PACSH-82101 | [DEMO] ACI - Enable Repair & Edits CHAPS Outbound payment Processing: Control Center | RTPS application upgraded to perfrom Repair & Edit via Control Center for Outbound CHAPS Payment Instr. Scope: pacs.008 | Not Started | 2025-06-04 | ACI | ACI Deliverables - RTPS Ent ISO
[SCRUM] Story |  | {DEMO] ACI - CHAPS END-END Validations | RTPS upgraded to consume Outbound Payment Instr., send acknowledgements, Repair & edits via control center and other payment processing flows as BAU. BAU processing incl. but not limited to: screen outbound payments, repair & edits via video cleint, send TSI RFML status updates generate FIN MT, Send Payment out to market and consume network & Market acknowledgements, produce debit/ credit confirmations, consume & process Inbound Payment Insr and generate acknowldgements. scope: pac.008, pacs.009, pacs.009 cov Happy path & exceptions | Not Started |  | ACI | ACI Deliverables - RTPS Ent ISO
[SCRUM] Story |  | ACI - CHAPS Code Delivery (MTS Config Express) [Tech] | Package & deliver upgraded ACI code for State Street to install and upgrade RTPS | Not Started | 2025-07-31 | ACI | ACI Deliverables - RTPS Ent ISO
[SCRUM] Story |  | ACI - CHAPS Code Delivery (UPF & Control Center June SP - Target July 11) [Tech] | Package & deliver upgraded ACI code for State Street to install and upgrade RTPS | Not Started | 2025-07-11 | ACI | ACI Deliverables - RTPS Ent ISO

## SSG RTPS CHAPS - Ent ISO
Issue Type | Issue key | Summary | Outcome | Status | Due Date | Assignee | Parent summary
[SCRUM] Story |  | [IT Analysis] Gateway -> Intl.RTPS : ISO MX , RTPS headers (CHAPS Market) | Document - analysis outcome for required message formats to be consumed by RTPS Banks Adapter. |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | [IT Analysis] Gateway <- Intl.RTPS : RTPS Acknowledgements (CHAPS Market) | Document - analysis outcome for required messages formats generated by RTPS Banks Adapter. |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | [Analysis] Identify the CHAPS use cases & need for enrichment of ISO MX from ISVC | Document - list of enrichmnets required to be made in ISO MX content from ISVC and review with SS Product & Payment ops. |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM DEV : [CHAPS] Consume Outbound Payment instr MX + send UPF Technical Acknowledgments | RTPS Integration with ISVC & GWH for CHAPS ; RTPS integration to consume outbound pay instr in ISO MX format with RTPS headers and generate Technical Acknowlegements (Short ACKs/NAKs). |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM DEV - Enable CHAPS Payment Processing lines in MTS [Tech] | MTS component of RTPS upgraded to consume & process Outbound CHAPS Payment Instr. in ISO MX format via ACI RTPS Bank Adapter. Scope: pacs.008 |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM DEV - Enable CHAPS Payment Processing lines in UPF [Tech] | UPF component of RTPS upgraded to consume & process Outbound CHAPS Payment Instr. in ISO MX format via ACI RTPS Bank Adapter. Scope: pacs.008 |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM DEV : Enable Repair & Edits CHAPS payment Processing: Control Center | RTPS application upgraded to perfrom Repair & Edit via Control Center for Outbound CHAPS Payment Instr. Scope: pacs.008 |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM DEV - CHAPS END-END Validations | RTPS upgraded to consume Outbound Payment Instr., send acknowledgements, Repair & edits via control center and other payment processing flows as BAU. BAU processing incl. but not limited to: screen outbound payments, repair & edits via video cleint, send TSI RFML status updates generate FIN MT, Send Payment out to market and consume network & Market acknowledgements, produce debit/ credit confirmations, consume & process Inbound Payment Insr and generate acknowldgements. scope: pac.008, pacs.009, pacs.009 cov Happy path & exceptions |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM DEV - Intl. RTPS MTS Express Code Install & deploy - MTS [Tech] | Install & deploy upgraded ACI code and upgrade RTPS MTS component in DEV Environment |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM DEV - Intl. RTPS June Code Install & deploy - UPF [Tech] | Install & deploy upgraded ACI code and upgrade RTPS UPF component in DEV Environment |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM DEV - Intl. RTPS June Code Install & deploy - Control Center [Tech] | Install & deploy upgraded ACI code and upgrade RTPS Control Center component in DEV Environment |  |  |  | RTPS Ent ISO - CHAPS/LON
task |  | SS GBM DEV - infra task1 in DEV [Tech] |  |  |  |  | RTPS Ent ISO - CHAPS/LON
task |  | SS GBM DEV - infra task2 in DEV [Tech] |  |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | [Demo] SS GBM UAT : [CHAPS] Consume Outbound Payment instr MX + send UPF Technical Acknowledgments | RTPS Integration with ISVC & GWH for CHAPS ; RTPS integration to consume outbound pay instr in ISO MX format with RTPS headers and generate Technical Acknowlegements (Short ACKs/NAKs). Scope: pac.008/pacs.009 |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM UAT - Enable CHAPS Payment Processing lines in MTS [Tech] | MTS component of RTPS upgraded to consume & process Outbound CHAPS Payment Instr. in ISO MX format via ACI RTPS Bank Adapter. |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM UAT Enable CHAPS Payment Processing lines in UPF (Platform Mgr + config Builder) [Tech] | UPF component of RTPS upgraded to consume & process Outbound CHAPS Payment Instr. in ISO MX format via ACI RTPS Bank Adapter. |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | [Demo] SS GBM UAT : Enable Repair & Edits CHAPS payment Processing: Control Center | RTPS application upgraded to perfrom Repair & Edit via Control Center for Outbound CHAPS Payment Instr. Scope:pac.008/pacs.009 |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | [Demo] SS GBM UAT - CHAPS END-END Validations | RTPS upgraded to consume Outbound Payment Instr., send acknowledgements, Repair & edits via control center and other payment processing flows as BAU. BAU processing incl. but not limited to: screen outbound payments, repair & edits via video cleint, send TSI RFML status updates generate FIN MT, Send Payment out to market and consume network & Market acknowledgements, produce debit/ credit confirmations, consume & process Inbound Payment Insr and generate acknowldgements. scope: pac.008, pacs.009, pacs.009 cov Happy path & exceptions |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM UAT - Intl. RTPS MTS Express Code Install & deploy - MTS [Tech] | Install & deploy upgraded ACI code and upgrade RTPS UPF component in PERF Environment |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM UAT - Intl. RTPS June Code Install & deploy - UPF [Tech] | Install & deploy upgraded ACI code and upgrade RTPS Control Center component in PERF Environment |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM UAT - Intl. RTPS June Code Install & deploy - Control Center [Tech] | Install & deploy upgraded ACI code and upgrade RTPS Control Center component in UAT Environment |  |  |  | RTPS Ent ISO - CHAPS/LON
task |  | SS GBM UAT - infra task1 in UAT [Tech] |  |  |  |  | RTPS Ent ISO - CHAPS/LON
task |  | SS GBM UAT - infra task2 in UAT [Tech] |  |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM BUAT : [CHAPS] Consume Outbound Payment instr MX + send UPF Technical Acknowledgments | RTPS Integration with ISVC & GWH for CHAPS ; RTPS integration to consume outbound pay instr in ISO MX format with RTPS headers and generate Technical Acknowlegements (Short ACKs/NAKs). |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM BUAT - Enable CHAPS Payment Processing lines in MTS | MTS component of RTPS upgraded to consume & process Outbound CHAPS Payment Instr. in ISO MX format via ACI RTPS Bank Adapter. |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM BUAT Enable CHAPS Payment Processing lines in UPF (Platform Mgr + config Builder) | UPF component of RTPS upgraded to consume & process Outbound CHAPS Payment Instr. in ISO MX format via ACI RTPS Bank Adapter. |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM BUAT : Enable Repair & Edits CHAPS payment Processing: Control Center | RTPS application upgraded to perfrom Repair & Edit via Control Center for Outbound CHAPS Payment Instr. Scope: pacs.008 |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM BUAT - CHAPS END-END Validations | RTPS upgraded to consume Outbound Payment Instr., send acknowledgements, Repair & edits via control center and other payment processing flows as BAU. BAU processing incl. but not limited to: screen outbound payments, repair & edits via video cleint, send TSI RFML status updates generate FIN MT, Send Payment out to market and consume network & Market acknowledgements, produce debit/ credit confirmations, consume & process Inbound Payment Insr and generate acknowldgements. scope: pac.008, pacs.009, pacs.009 cov Happy path & exceptions |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM BUAT - Intl. RTPS MTS Express Code Install & deploy - MTS | Install & deploy upgraded ACI code and upgrade RTPS UPF component in PERF Environment |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM BUAT - Intl. RTPS June Code Install & deploy - UPF | Install & deploy upgraded ACI code and upgrade RTPS Control Center component in PERF Environment |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM BUAT - Intl. RTPS June Code Install & deploy - Control Center | Install & deploy upgraded ACI code and upgrade RTPS Control Center component in UAT Environment |  |  |  | RTPS Ent ISO - CHAPS/LON
task |  | SS GBM BUAT - infra task1 in BUAT |  |  |  |  | RTPS Ent ISO - CHAPS/LON
task |  | SS GBM BUAT - infra task2 in BUAT |  |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM PERF : [CHAPS] Consume Outbound Payment instr MX + send UPF Technical Acknowledgments | RTPS Integration with ISVC & GWH for CHAPS ; RTPS integration to consume outbound pay instr in ISO MX format with RTPS headers and generate Technical Acknowlegements (Short ACKs/NAKs). |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM PERF - Enable CHAPS Payment Processing lines in MTS [Tech] | MTS component of RTPS upgraded to consume & process Outbound CHAPS Payment Instr. in ISO MX format via ACI RTPS Bank Adapter. |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM PERF Enable CHAPS Payment Processing lines in UPF (Platform Mgr + config Builder) [Tech] | UPF component of RTPS upgraded to consume & process Outbound CHAPS Payment Instr. in ISO MX format via ACI RTPS Bank Adapter. |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM PERF : Enable Repair & Edits CHAPS payment Processing: Control Center | RTPS application upgraded to perfrom Repair & Edit via Control Center for Outbound CHAPS Payment Instr. Scope: pacs.008 |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM PERF - CHAPS END-END Validations | RTPS upgraded to consume Outbound Payment Instr., send acknowledgements, Repair & edits via control center and other payment processing flows as BAU. BAU processing incl. but not limited to: screen outbound payments, repair & edits via video cleint, send TSI RFML status updates generate FIN MT, Send Payment out to market and consume network & Market acknowledgements, produce debit/ credit confirmations, consume & process Inbound Payment Insr and generate acknowldgements. scope: pac.008, pacs.009, pacs.009 cov Happy path & exceptions |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM PERF - Intl. RTPS MTS Express Code Install & deploy - MTS [Tech] | Install & deploy upgraded ACI code and upgrade RTPS UPF component in PERF Environment |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM PERF - Intl. RTPS June Code Install & deploy - UPF [Tech] | Install & deploy upgraded ACI code and upgrade RTPS Control Center component in PERF Environment |  |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | SS GBM PERF - Intl. RTPS June Code Install & deploy - Control Center [Tech] | Install & deploy upgraded ACI code and upgrade RTPS Control Center component in UAT Environment |  |  |  | RTPS Ent ISO - CHAPS/LON
task |  | SS GBM PERF - infra task1 in PERF [Tech] |  |  |  |  | RTPS Ent ISO - CHAPS/LON
task |  | SS GBM PERF - infra task2 in PERF [Tech] |  |  |  |  | RTPS Ent ISO - CHAPS/LON

## SSC RTPS CHAPS SQA
Issue Type | Issue key | Summary | Outcome | Status | Due Date | Assignee | Parent summary
[SCRUM] Story |  | [SQA] Test Outline Document for CHAPS | Document : Test Outline for CHAPS | Done |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | [SQA] Test Strategy and Plan for CHAPS | Document : Test Plan & Test Strategy for CHAPS | In progress |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | [Demo - future sprint][SQA] Runbook prep for CHAPS | Document : Test Runbook for CHAPS | In progress |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | [DEMO] [SQA] Functional testing for CHAPS based on ACI releases - Part 1 | Validate End-End Outbound CHAPS ISO MX payment pocessing for Intl.RTPS for payments instructed via ACI Bank Adapter. | Not Started |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | [DEMO] [SQA] Functional testing for CHAPS based on ACI releases - Part 2 | Validate End-End Outbound CHAPS ISO MX payment pocessing for Intl.RTPS for payments instructed via ACI Bank Adapter. | Not Started |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | [SQA] Joint Integration testing for CHAPS Outbound - Part 1 | Validate End-End Outbound CHAPS ISO MX payment pocessing for Intl.RTPS via ACI Bank Adapter integrated with upstream and downstream applications in scope. | Not Started |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | [SQA] Joint Integration testing for CHAPS Outbound - Part 2 | Validate End-End Outbound CHAPS ISO MX payment pocessing for Intl.RTPS via ACI Bank Adapter integrated with upstream and downstream applications in scope. | Not Started |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | [SQA] Joint Integration testing for CHAPS Outbound - Part 3 | Validate End-End Outbound CHAPS ISO MX payment pocessing for Intl.RTPS via ACI Bank Adapter integrated with upstream and downstream applications in scope. | Not Started |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | [SQA] Regression testing for CHAPS Inbound - Part 1 | Validate BAU use cases for CHAPS Inbound ISO MX payment processing. | Not Started |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | [SQA] Regression testing for CHAPS Inbound - Part 2 | Validate BAU BAU use cases for CHAPS Inbound ISO MX payment processing. | Not Started |  |  | RTPS Ent ISO - CHAPS/LON
[SCRUM] Story |  | [SQA] Intl. RTPS Release notes analysis | Document : Analyze and prepare test document | Not Started |  |  | RTPS Ent ISO - CHAPS/LON

## RTPS CHAPS Automation
Issue Type | Issue key | Summary | Outcome | Status | Due Date | Assignee | Parent summary
[SCRUM] Story |  | [Automation] Set up SV for CHAPS in DEV outbound from IBS | Enable & Validate Service Virtualization for CHAPS Payments via IBS in DEV environment. | Not Started
[SCRUM] Story |  | [DEMO] [Automation] Set up SV for CHAPS in BUAT outbound from IBS - Part 1 | Enable & Validate Service Virtualization, PDL (Prod Data Load) for CHAPS Payments via IBS in BUAT environment. | Not Started
[SCRUM] Story |  | [DEMO] [Automation] Set up SV for CHAPS in BUAT outbound from IBS - Part 2 | Enable & Validate Service Virtualization, PDL (Prod Data Load) for CHAPS Payments via IBS in BUAT environment. | Not Started
[SCRUM] Story |  | [Automation] Set up SV for CHAPS in PERF outbound from IBS | Enable & Validate Service Virtualization for CHAPS Payments via IBS in PERF environment. | Not Started