## 00 Executive Dashboard Program
PORTFOLIO — EXECUTIVE DASHBOARD
As of: | 2026-01-30
| Key: | On Track | At Risk | Delayed | Done
Workstreams | Release Code Delivery | App Config Delivery Date | PCS Delivery Date | SBB Go-live Date | Project % Complete | Days to Go Live | Schedule Status | Overall Status | Client Satisfaction
ABA Support a New Fedwire SSD | 2026-11-25 |  |  | March
Transact MPA lines | 2026-12-25 | Jan 31th | Feb 13th | May
Transact MPA Multiple Lines | Feb 13th | Jan 31th | Feb 13th | May
Intercompany Bank Setlements | 2026-03-26 | Early Feb | Feb 15th | May
Transact MPA lines - new (Risk Requirement) | TBD |  |  | May
Intercompany Bank Setlements - new (Serial Cover Req) | TBD |  |  | May
A. Overview
This week, our primary focus is on the daily tracking and documentation of cases, as well as ensuring consistency in RTPS case updates across the team.The key areas of focus are as follows: -Project release for testing New MPA lines: These have already been released, and Neethu and Katheeja advanced 50% due date feb 10th MPA lines: Pending release. Sai / Tejas Testing due data feb 10th. Bank Settlement: Pending release, to start the testing (102) cases with an expected timeline of mid-February. -Other pending cases: --UPF Case: We had meeting this week to clarify the dudes after that meeting the bank bring resolution and recomendations to bank. --Target Cases: Two cases are with Product already scalated. Two cases are currently in the PCS process and are being recreated and reviewed with the SME. --Chips Cases: We are currently awaiting a response from the bank. These cases have been placed on hold until February 13th. --Additional RTPS Case: RTPS-107540 – Transact MPA lines Login request contains junk characters. A meeting with the developer is scheduled for February 2nd to review the reason the issue could not be recreated in ACI.
Contract Updates: All contractual documents have been updated, except for Schedule 15, which is pending approval from GD; Waiting for a final update from Kirk Walters.
Exception File Update: Configuration changes related to SAD data and enrichment of event logs PR182 and PR 183 deployed in UAT1. Green Dot is testing from 10/20 to 11/20.
Backlog Reduction: Bug Fest continues, with L2 and L3 teams focused on analyzing and clearing backlog cases. 72 cases have been resolved, in October alone with 60 (includes cases for all teams) overall cases being opened to be added to the Backlog. The team will continue triaging and addressing issues to maintain momentum.
B.Workstream Highlights
ACI # 03711383- MPA New Lines / MPA Multi line (expected due date feb 10th) • RTPS-106894 Closed • RTPS-107299 Resolved Waiting finalize RTPS-107058 • RTPS-107058 Progress ACI # 03711383- MPA Multiple Lines (expected due date feb 10th) • RTPS-106764 – Resolved Testing (25/50) ACI # 03749089- Bank Settlement (included in release March ) • RTPS-106276 – Test 100 cases due date Feb 20 waiting release code in QA to start the testing UPF cases • '03779477-Control Center December Service Pack Installation Errors TARGET Cases • RTPS-85173-Inbound CAMT025 Receipt not mapping with Outbound CAMT050 Liquidity Credit Transfer message (product due March 30) • RTPS-106930-Outbound CAMT050 MX Message - SAA Header Section populated with incorrect values-product(development) • RTPS-107894-ACK TRN's are not received in MTS and matched with original outbound transaction-PCS process • RTPS-107959-Outbound PACS009 wis routed to EXCQ due to TGT Channel Derivation issue.PCS process CHIPS Cases • RTPS-105098-CHIPS ISO Inbound - Field 72 OBI/BBI long characters-Bank hold till Feb 13. • RTPS-106826-Field 72 - Need sequencing changes in the data--Bank hold till Feb 13. Other Cases • RTPS-106921-CHAPS-LEI is not retained in the credit payment text where its mandatory for the regulations-Dev Assigned • RTPS-107539-MTS routing issue: Payment flagged for TRS still routed to Hogan queue (DDA_AUTQ)-confim bank working as designed • RTPS-107540-Transact MPA lines Login request contains junk characters for Transact Accounts-Dev Assigned
C. Next Steps
• MPA testing- we need to conclude the pending issues to be ready for the test on Jan 31 UPF cases • 03777412-ISO 20022: UPF Control Center - Super1 Login - "null" (Excalate to UPF engineer)
Overall Portfolio
75%

## Project Meeting Minutes
February 03, ACI & SSB - Part 2 Discuss ACI Questions on CRCU RPH risk queue requirements
Discussion Summary: Focus: Risk queue handling for Transact accounts after migration from Hogan; treatment of dormant/inactive accounts and “marked for deletion” behavior.
Minutes of Meeting (MoM) ACI & SSB - Part 2 Discuss ACI Questions on CRCU RPH risk queue requirements Meeting Topic: Dormant Account Handling, Deletion Flags, and STP / Risk Queue Behavior Date: Feb 03 3:30 PM Attendees: • Ajay Amit (ACI) • Philip Hegarty (ACI) • Mary Kate Savini (State Street) • Indira Mallela (State Street) • Mark Coppola (State Street) • Renee Hickey (State Street) • Mayjane Co (State Street) ________________________________________ 1. Account Deletion Flags and SOD Processing Discussion • ACI tested scenarios using two dummy accounts marked with ‘D’ through the Start-of-Day (SOD) file. • Once accounts were flagged: o Debit hold and credit hold = “D” o Status marked for manual deletion o Attempting to update or reverse these flags via subsequent SOD files failed. • The system made errors indicating no updates are permitted once an account is flagged for manual deletion. Conclusion • Accounts marked for manual deletion cannot be updated or reverted via SOD. • There is no automated way to remove deletion flags. • Manual intervention is the only option to delete or change these accounts. ________________________________________ 2. Bulk Deletion or Flag Reversal Feasibility Discussion • State Street raised concerns about potential future bulk deletion scenarios (e.g., ~37,000 accounts). • Question posed on whether flags (debit hold, credit hold, deletion indicator) could be reset in bulk. Conclusion • No bulk or automated mechanism exists to: o Remove deletion flags o Reset debit/credit holds to “N” • Any such activity must be performed manually. • ACI confirmed that bulk deletion or reversal is not supported today. ________________________________________ 3. Dormant Account Identification (Non-Deletion) Discussion • State Street clarified the goal was not to delete dormant accounts, but to identify them. • Dormancy example: accounts inactive for 180 days. • Question raised on whether RTPS/RPH has an internal mechanism to flag dormant accounts. Conclusions • RPH does not provide an online or internal dormant-account flagging mechanism. • Dormant identification must come from: o Upstream systems (Hogan / Transact), or o Reporting or queries against the Oracle database (e.g., last-used date). • Any dormancy logic would be external to ACI, unless custom development is pursued. ________________________________________ 4. System of Record (TRS) and Risk Queue Routing Discussion • State Street asked whether: o Transact accounts could bypass the risk queue o While Hogan accounts continue current behavior • TRS (System of Record) was currently being used to differentiate accounts. Conclusion • System of Record (TRS) is not used to alter process flow or routing logic. • TRS only determines: o Where authorization occurs o Where posting occurs • Risk queue and STP behavior remain the same for Transact and Hogan accounts. • It is not possible to route Transact accounts away from risk queue solely based on TRS. ________________________________________ 5. Monitor Points and STP Breaking Discussion • Monitor points are currently used to: o Break STP o Route transactions to the risk queue • Business preference stated: o Certain messages should break STP without entering risk o Ideally routed to an exception queue Conclusions • Monitor points: o Cannot route directly to exception queues o Always route to risk • No standard ACI mechanism allows STP break without risk, unless: o Customization, or o Alternative routing configuration is applied ________________________________________ 6. Possible Alternative: Route Insertion Configuration Discussion • ACI described a “route insertion” configuration: o Allows messages that would normally be STP to be routed to a specific exception queue o Based on message characteristics o Not custom code, but still a configuration change Status • ACI to verify: o Whether string-based criteria (keywords/phrases) are supported o Or if criteria are limited to message attributes (currency, originator, etc.) ________________________________________ 7. Holds Removal (Debit/Credit Holds) Conclusion • Removal of debit/credit holds must be done manually • No automation exists to: o Remove holds o Reverse dormant or deletion flags • Teams must also stop applying these holds to Transact accounts if issues are to be avoided. ________________________________________ 8. Overall Conclusions • Transact accounts currently behave identically to Hogan accounts in: o Risk handling o STP flow • Any changes to: o Dormancy handling o Risk queue behavior o STP bypass require process changes, configuration changes, or customization. • Dormant account identification should be handled outside of ACI via reporting mechanisms. ________________________________________ 9. Action Items / Next Steps Action Owner Confirm business requirements for Transact account risk handling State Street Follow up with Indira on internal State Street alignment Mayjane Evaluate external reporting for dormant account identification State Street Review feasibility of routing based on string criteria (non-STP, non-risk) ACI (Philip) Please feel free to share any observations or clarifications regarding these minutes.
February 03, SSB ACI # 03777412 ISO 20022: UPF Control Center - Super1 Login - "null"
Meeting Title: ACI # 03777412 ISO 20022: UPF Control Center - Super1 Login - "null" Date: Feb 03 8 AM Duration: ~40 minutes Meeting Type: Technical Troubleshooting / Incident Review Attendees • Adam Kneisel • Manjula Nalla • Tausif Patel • Paul Contreras • Oscar Herrera ________________________________________ Objective To review and troubleshoot the BUAT Control Center login failure that occurred after data migration and MFA-related activities, and to identify possible root causes—specifically the potential impact of Dynatrace. ________________________________________ Background Summary • The Bank was working on implementing MFA in the BUAT environment. • During initial access to Control Center, the user management screen failed to render, producing a typical error seen when the Data Migrator has not run. • Manjula and Adam worked together to run the Data Migrator, encountering initial failures but eventually achieving a successful run with no errors. • Following the migration (Friday night), all login attempts failed on Monday morning, including access via the super user, returning a null error. • Multiple remediation attempts were made: o Rebuilding the environment o New deployment o Running the Data Migrator multiple times o Updating the migrator properties file and re-importing data • Despite these actions, Control Center remains inaccessible. ________________________________________ Key Discussion Points Environment & Installation • The environment was previously running the June Service Pack. • A redeployment using the December Service Pack was completed successfully with no installation errors. • Database health was discussed and appears to be stable; current evidence does not indicate a DB-related issue. Dynatrace Observation • Tausif noted that based on exception logs, the issue is likely not database-related. • A possible cause identified is the Dynatrace agent injecting special characters into response URLs, which may be breaking Control Center login. • This issue appears environment-specific, as other environments using Dynatrace do not show the same behavior. Proposed Troubleshooting Approach • Temporarily disable Dynatrace in the BUAT environment. • Restart Control Center after disabling Dynatrace. • Attempt login post-restart to validate whether Dynatrace is the root cause. • If the issue persists without Dynatrace, further investigation will be required (logs review, escalation). ________________________________________ Decisions Made • ✅ Proceed with disabling Dynatrace as the next troubleshooting step. • ✅ Validate Control Center login functionality after Dynatrace is disabled. • ✅ Share relevant logs and files as needed. • ✅ Schedule a follow-up meeting on Thursday to review results and next steps. ________________________________________ Action Items Action Owner Status Disable Dynatrace in BUAT Manjula (with Server Team) Pending Restart Control Center Manjula Pending Attempt login post-Dynatrace disable Manjula Pending Provide logs/files if requested Manjula As needed Identify Dynatrace-related documentation (SA/notes) Tausif In progress Follow-up meeting Adam / Team Scheduled (Thursday) ________________________________________ Open Questions / Risks • Why Dynatrace is causing an issue only in this BUAT environment and not in others. • Impact if disabling Dynatrace does not resolve the issue—potential need for deeper root cause analysis or escalation. • Desire to avoid a full environment rebuild, as this would be highly impactful for BUAT. ________________________________________ Next Steps • Complete Dynatrace disablement and validation. • Share findings during the next scheduled meeting. • If unresolved, escalate with logs and pursue alternative root cause paths. Please share any comments or corrections on these minutes.

## Sprint Backlog
State Street Bank Sprint 23 Jan 28 - Feb 12
| Case Number | Project | H24 Case Number | RTPS | Defect Title | Severity/Priority | ACI Status | Planned Delivery Date | Comments | Assignee
x | 03711383 | MPA new Lines | H24-658385 | RTPS-107058 | Reverse Posting for Functional cancel doesn't happen for Bank Adapter/Manual Create messages for Transact accounts | Major | In Progres | 2026-02-10 | Feb06 ready for test Feb 05 Tejas confirm still pending to start testing(jean need to confirm on this) Feb 04 Sail will ask jean code to start this test today Jean Harty added a comment - jan 26 analyzing these cancels. | Tejas
x | 03711383 | MPA new Lines | H24-658385 | RTPS-107299 | Functional cancellations trapping for all Book To Book Transfer transactions in State Street Domestic | Major | Wating Input RTPS-107058 | 2026-02-10 | Feb06 ready for test Feb 05 (need to be tested together with RTPS-107058) Feb 04 Sail will ask jean code to start this test today Jean Harty added a comment - jan 28 Saikumar Vemasani this was fixed under RTPS-107058. This should be retested when RTPS-107058 is built and ready for QA, then can be closed if the test results are satisfactory. | Sai
x | 03711383 | MPA new Lines | H24-658385 | RTPS-106894 | SSB Cancellations -> Reverse bookings is not happening for upon cancellations | Major | Closed |  | Tested - | Sai
x | 03711383 | MPA multiple lines | H24-658385 | RTPS-106764 | SSC - US Boston (SSB) : Bank request for multiple parallel AUT/POST lines for Transact | Minor | Ready for testing | 2026-02-10 | Feb06 Line 21 (/ 25) will completed today, start line 22 (8/25) Feb 05 Line 21 (50% completed) will start line 22 Feb 04 Neethu advancing but still with issues ( Jan 29 advace (4/50) cases , create file also update in the share point | Neethu/ Katheeja
x | 03777412 | UPF | H24-716063 |  | ISO 20022: UPF Control Center - Super1 Login - "null" | High | Waiting customer answer |  | Feb 06 still waiting from bank comments in the ticket Feb 05 meetig discuss on Dynatrace again - Bank need to update the ticket and Pausti will review it and update the ticket after that Feb 04 Bank confirmed that is working, (without Dynatrace system). Update the ticket Jan 28 Paul escalte to UPF enginneer | Paul
x |  | New Requirement for RISK Queue | [6 empty] | Feb 06 we will discuss on this today Feb 05 Philp will explore the option .(Review feasibility of routing based on string criteria (non-STP, non-risk)) Feb 04 Bank need to advance in requirement to ACI Jan 29 After jan 27 meeting it's require to create POC, also will have feb 3th new meeting to continue the Analysis on this. | Amit
x | 03749089 | New Requirement[ Direct Cover Scenario] | H24-692138 | RTPS-108203 | RPH-US instance RTPS : New Requirement for Intercompany Bank Settlement DDA | High |  |  | Feb 06 Phill need to check with Jean on this (SDD alredy had Oscar will share with Jean / Philp) Feb05 same status Feb 04 Feb 04 POC sai is advancing on this jan 29 Amit will advance in Solution Document, pending from bank requirement sign off | Amit
x | 03749089 | Bank Settlement DDA | H24-692138 | RTPS-106276 | Test 100 Cases | Low | Open | 2026-02-15 | Feb 06 same status feb 05 Feb 05 Jean update ticket as resolved .. Need to know next steps Feb 04 in progress by jean Include release end March | Neethu
x | 03748411 | Target Cases | H24-691549 | RTPS-85173 | Ent ISO - Target2 - Inbound CAMT025 Receipt not mapping with Outbound CAMT050 Liquidity Credit Transfer message | High | Ready for Dev | 2026-03-30 | Feb 05 same status feb 04 Feb 04 release for march Develope Prod assgned | Mamatha Govindaraju | sai
x | 03757439/'03757445 | Target Cases | H24-699371/H24-699374 | RTPS-106930 | Outbound CAMT050 MX Message - SAA Header Section populated with incorrect values under certain data elements. | High | In Progres |  | Feb 06 in turn 11 Jason H Feb 04 already scalate with Stephanie Jan 29 Jason H assign 16 site in development | Padmasri Mudugonda | sai
x | 03757391 | Target Cases | H24-699334 | RTPS-107894 | ACK TRN's are not received in MTS and matched with original outbound transaction | Major | Open |  | Feb 06 Tejas sent mail to bank check swift, now banking is asking ACI (Tejas will update the ticket) Feb05 Tejas review info from bank , it's not recreate yet. Need discuss with Philp. Feb 04 Tejas received data from bank will update and review with Paul on this Jan 29 recreate to review with Philp | Tejas
x | 03757393 | Target Cases | H24-699336 | RTPS-107959 | Outbound PACS009 with Receiver/Cdtr Agt - BCITITMMXXX is routed to EXCQ due to TGT Channel Derivation issue. | Major | Open |  | Feb 06 Tejas confirm that work find, will send bank asking what bank is using this data Feb 05 Tejas partially recreate Amit suggest change the account to test it. Feb 04 Tejas will recreate, with the information received by bank Jan 29 recreate to review with Philp | Tejas
|  |  | H24-711312 | RTPS-107184 | 2026 Mandates (March Release) |  | Open |  | Feb 06 Amit wil review on this Feb 05 Amit will review the RTPS-107074 Amy H. request follow this | Amit
| 03771976 | CHIPS Cases | H24-711312 | RTPS-105098 | CHIPS ISO Inbound - Field 72 OBI/BBI long characters | Minor | Open |  | As per bank's request we will be keeping this on hold till Feb 13. | Katheeja
| 03771976 | CHIPS Cases | H24-711312 | RTPS-106826 | Field 72 - Need sequencing changes in the data shown in Field Tag 72 of the MT910 Credit Confirmation sent out by MTS | Minor | Open |  | As per bank's request we will be keeping this on hold till Feb 13. | Katheeja
x | 03775326 | Other cases | H24-714233 | RTPS-106921 | CHAPS-LEI is not retained in the credit payment text where its mandatory for the regulations | Major | In Progress |  | Feb 06 After today meeting with Saumya, next steps call to Joe C and send mail to bank on this (sai) Feb 05 Sail will update the ticket H24, and will check with developer. Oscar arrange the call tomorrow 8 am Feb 04 After feb 03 meeting with the bank the bank comment that with june 25 is working . | Anindya Ganguly | sai
x | 03781262 | Other cases | H24-719521 | RTPS-107539 | MTS routing issue: Payment flagged for TRS still routed to Hogan queue (DDA_AUTQ) | Major | Awaiting Customer Action |  | Feb 04 will update the ticket to closed ACI configuration team have reviewed this concern, and this is confirmed to be ‘Working as Designed’. Please find the response from the team below. | Katheeja
x | 03781260 | Other cases | H24-719519 | RTPS-107540 | Transact MPA lines Login request contains junk characters for Transact Accounts | Major | Open |  | Feb 06 Feb 05 Tejas will update messages in RTPS / H24 Feb 04 Tejas will update the ticket Develope Prod assgned | Jitendra Gupta | Tejas
x | 03754982 | Other cases | H24-697226 |  | Wait-Posting event not sent for messages with source BTR from MTS to UPF(Domestic) |  | Awaiting Customer Action |  | Jan 29 bank confirmed be closed Tejas will closed and send mail bank to bank | Tejas
[5 empty] | HKICL RTGS Dual Network Channel Requirement |  |  |  | Feb 04 we received mail from bank related to analyze the implementation on this Jan 19 Mayjane replayed that bank is analyzing on this will confirm at the end of jan | Amit
| '03640399 |  | H24-595902 |  | Payments Canada / Lynx mandatesmail sent by Scott to Bank request (jan27) | Minor | Open |  | jan 29 Mayjane answer mail to Scott with the info, Scott resent to Amy H product | Scott
[5 empty] | Venkata - Can BankAdapter consume FedWire format message as is for Non-Pass Through/Pass Through Model | Minor | Awaiting Customer Action |  | jan 26 Amit will send mail on this today | Amit
x | 03785212 | Inquiry | H24-722986 |  | Inquiry - MPA post interface changes | Minor | Open |  | Feb 06 we try to recreate issue here to discuss with Philp today Feb 05 to discuss with Philp today meeting Feb 04 Amit will document on this before review with Philp Jan 30 Oscar sent mail to Scott | Oscar
|  |  | H24-709214 |  | SSG ¦ MTS ¦ Processes getting TRAPPED | Minor | Open
x | 03785216 | Inquiry | H24-722988 |  | Inquiry - Charges information configuration based on Source | Minor | Open |  | Feb 06 already sent to bank waiting bank response Feb 04 Amit need to response to bank on the question | Amit
x | 03785363 | Inquiry | H24-723118 |  | Inquiry - Need sample of CBPR+ PAIN.001 message with multiple CdtTrfTxInf and corresponding PAIN.002 responses (Batch Adaptor) | Minor | Open |  | Feb 06 we need to wait for ACI product annoucment Feb 05 SME agenda / after that call with joe (prod) Feb 04 Amit already sent the response | Amit
x | 03785698 | Other Cases | H24-723416 |  | SSC¦ MTS¦ FED Payments incorrectly routing through CHP | Minor | Open |  | Feb 06 Philp will change in the rules. Feb 05 Katheeja already recreate the issue. (SSI) create RTPS Feb 04 Katheeja start recreation found TRAPs | Katheeja
x |  |  |  |  | Code Delivery Feb 13 | High | Open |  | Feb 05 need discuss with Jean to send the ticket for snapshoot to bank | Oscar
x | 03779477 | UPF | H24-717875 |  | Control Center December Service Pack Installation Errors | High | Open |  | Feb 06 Bank will test it , next steps wait for Bank comments on this. Feb 05 Bank insist they have version mq-client different that ACI recommend, Paul will escalate this | Paul
x |  |  |  | RTPS-67069 | SSG - modify NON_BUSINESS_DAY_EDIT to allow for Sunday processing | Minor | Open |  | Feb 06 open by jean to test by PCS | sai

## Budget
State Street Project Budget
First Horizon MTS ISO-20022 - Schedule 5 @ $225/hr Expires 24 Feb 2024
Description | Oracle Number | Original Est Low Hours | Contingency Hours | Actual Hours through 4/10/2024 | Hours Burned Current Month () | Estimate to Complete | Estimate at Completion | Variance to Original High Estimate | Hours Invoiced to date @ $225/hr
MTS ISO-20022 - Sch 5 | 114512 | 3000 |  | 3000.8 |  | 8.95 | 3000 |  | 2432
| 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | TOTAL
Actual | 8.5 | 50 | 177.5 | 280 | 168 | 201 | 229.25 | 178.05 | 140 | 44.5 | 81.5 | 154.25 | 318.25 | 102.25 | 113.75 | 164.75 | 169.75 | 96.75 | 88.75 | 65.25 | 119.5 | 24.75 | 41 | 17.75 | 3035.05
Forecast ISO |  | 200 | 200 | 240 | 200 | 150 | 150 | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Forecast Email Mask, Repet from BBOL, REL Addr | [5 empty] | 50 | 30
Travel Rule Dev 55.06 | [6 empty] | 14 |  |  |  |  | 89 | 110 | 4.25
|  |  | MTS Link coding UP Install | MTS Link Code June SP delivery | July SP delivery | July FP 2 delivery | July FP 4 delivery | July FP 5 delivery |  |  | Technical Go Live |  | Go Live Took the March SP | [7 empty] | Deployed 6.8.67 to PROD | Took 6.8.71
CHANGE CONTROLS FOR SCHEDULE 05 - ORACLE CODE 114512
Services Oracle 114512 | Task Code | High Budget | Hours Used | Est to Complete | Comments
ISO 20022 | 55.01 + | 0 | 149.75 | 700
Email Masking | 55.02 |  | 2.5 | 0
Repetitive from BBOL to MTS | 55.03 | 50 | 25.75 | 40
REL Address Updates | 55.04 | 50 | 13.5 | 40
put EXCPPRTQ queue into sub history for OFC | 55.05
Travel Rule Development | 55.06 | 217 | 217.25
Travel Rule Services | 55.07 | 110 | 0
March SP Rework | 22.05 | 47
TOTAL |  |  | 191.5 | 780
State Street Bank PCS SERVICES SCHEDULE No. 9
Description | Oracle Number | Original Est Low Hours | Contingency Hours | Actual Hours through 12/27/2025 | Hours Burned Current Month () | Estimate to Complete | Estimate at Completion | Hours Invoiced to date @ $260/hr | Invoices Paid
Premium Customer Support |  | 3360 |  | 10042.25 |  | -6682.25 | 3360 | 3054.4 | 2965.4
| 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | TOTAL
Actual | 31.5 | 514.25 | 603.75 | 495.5 | 700.5 | 822.25 | 1014.75 | 890.75 | 1094.75 | 747.75 | 874.25 | 1379.25 | 834 | 39 | [10 empty] | 10042.25
PRE-CONTRACT BUDGETS
Description | Subproject/ Oracle Nbr | Precontract Hours | Actual Hours Used to Date | Approved Hours Remaining | Percent Used | Expiration Date | Comments
MTS/RPI Entry Function Full Originator details required if any Originator details are present FR-29547 | 115316 | 200 | 31.5 | 168.5 | 15.75% | 2022-09-30
| 2022-08-01 | 2022-09-01 | 2022-10-01 |  |  | TOTAL
Actual | 12 |  |  |  |  | 12
TRAVEL EXPENSES
Project Name | Oracle Nbr | Amount | Approve Date | Invoice Date | Invoice Nbr | Team Member |  | Purpose
FUTURE PLANNED TRAVEL EXPENSES
Project Name | Oracle Nbr | Est Amount | Est Start Dt | Est End Date |  | Team Member |  | Purpose

## Release Schedule
2026
Month | MTS Code Base Availability Date | MTS Release Name | UPF Release Date | ISO 20022 RTPS Solution Name
January |  |  | 2026-01-14 | 3.5.5.1 Patch - 14-Jan
January | 2026-01-22 | MTS 6.8.80.0 | 2026-01-22 | Dec_25 SP January Patch
February | 2026-02-22 | SNAPSHOT 2
February
March | 2026-03-27 | MTS 5.8.81.0/6.8.81.0 | 2026-03-30 | ISO_Mar26
June | 2026-06-26 | MTS 5.8.82.0/6.8.82.0 | 2026-06-29 | ISO_Jun26
September | 2026-09-25 | MTS 5.8.83.0/6.8.83.0 | 2026-09-28 | ISO_Sep26
December | 2026-12-11 | MTS 5.8.84.0/6.8.84.0 | 2026-12-14 | ISO_Dec26