## Sheet1
Summary | Sprint | Notes | Owner
DEC SP (2025) ASAP | -
Amit * ACI #03779477 Control Center December Service Pack Installation Errors | RTPS Sprint 22 | All of the Bank's projects are stalled because we do not have a working copy of this December Service Pack | [Paul / APFS team] need to resolve to bank can install Dec Service Pack
ABA (2025) March Go-Live
Katheeja * [TEsting 4 CC Use Cases] ACI Ticket 03713432 - ABA | RTPS Sprint 22 | Waiting on Paul to resolve an issue. But Paul is occupied with December Service Pack issue above. | [Paul C] need to resolve UPF and after Katheeja test if not error finish 2 pending cases
Bank 52 (2025) February Integration Test; May Go-Live | -
Tejas/Sai * [Testing] ACI Ticket 03711383 - 60 cases New MPA & Tran Codes for Transact | RTPS Sprint 22 | Waiting on a resolution to Cancellation Issues. State Street planned to begin Integration Testing in February but is held up by this | [Jean H] , Cancellation Issues we create a internal ticket [RTPS-106894] SSB Cancellations -> Reverse bookings is not happening for upon cancellations - PD…
Amit * [2nd week Jan] ACI Roadmap/ Milestones for Bank 52 Intercompany requirement | RTPS Sprint 22 | States Street needs this functionality as part of the above Integration Testing in February. But we still don't even have an ESTIMATE of when this can be delivered | [Jean H] resolve the estimation for Intercompany Bank Settlement
Amit ** [BUG] ACI to update number of DDA AUTH and POST lines for ACI Ticket 03711383 - New MPA & Tran Codes for Transact; | RTPS Sprint 22 | States Street needs this functionality as part of the above Integration Testing in February. Need confirmation of when this can be delivered. | [Jean /PCS] Jean configure / PCS test
Amit * ACI to Review Requirement for RISK Queue | RTPS Sprint 22 | Waiting on results of ACI analysis | [Amit / Bank] Amit sent question to bank / Bank pending answer on new requirement
TARGET2 (2025) June Go-Live | - | This was supposed to Go-Live in Nov 2025 but was descoped due to open tickets below.
PP * Date for a Date Q1 2026 * ACI Ticket 03748411/RTPS-101750 for Target2 Camt.050 matching to camt.025 | PRIORITY | This ticket has been open since August of 2025. ACI Product Team is yet to provide a Release date. | [Prod ] Ashutosh comment only this will be in the first Q.
PP Sai* [ACI #03757439]TARGET2 Outbound CAMT050 MX Message - SAA Header Section populated with incorrect values under certain data elements. | RTPS Sprint 22 | Opened Sep 2025 | [Sai/Amit] Recreated and present to Product
PP Sai* [ACI #03757445]TARGET2 Outbound CAMT050 MX Message - APP HEADER Section populated with incorrect values under certain data elements. | RTPS Sprint 22 | Opened Sep 2025 | [Sai/Amit] Recreated and present to Product
PP Sai* ACI# 3757391 TARGET2 - ACK TRN's are not received in MTS and matched with original outbound transaction. | PRIORITY | Opened Sep 2025
PP Sai* ACI# 3757393 TARGET2 - Outbound PACS009 with Receiver/Cdtr Agt - BCITITMMXXX is routed to EXCQ due to TGT Channel Derivation issue | PRIORITY | Opened Sep 2025
ACI Tickets (2025) ASAP as High Risk Issues in PROD | - | These are HYPER-CRITICAL. We have another list of CRITICAL tickets that I can provide once these HYPER-CRITICAL ones are addressed.
PP * Katheeja * [ACI #03777421] - *Follow up of 3771976* - Need sequencing changes in the data shown in Field Tag 72 of the MT910 Credit Confirmation sent out by MTS | RTPS Sprint 22 |  | [Katheeja] update ticket, bank need to update his expectation
PP [ACI #03772878] RITS Outbound PACS009 MX - REC & BNF keyword information is mapped to both Remittance Information and Instruction for Next Agent data element is mapped incorrectly as part of Bank Adapter flow. | PRIORITY
PP [ENT ISO GBM] ACI# 03767600 Lynx Outbound PACS009 omitting Dbtr Agt | PRIORITY
PP ACI Ticket # 03775326 - RTPS dropping LEI in CHAPS Outbound message for Instructed Agent in App Hdr. GBP 18.88 24/10 - 25JWIZZP9M3FTA (CHAPSP8TC01A) | PRIORITY
Coming up in 2026 | -
Oscar** TARGET2 June Release - ACI Schema Changes? June Go-Live; Industry Test TBD (usually months before Go-Live) | RTPS Sprint 22 | This is a Regulatory Release in June. Amy Haines from ACI said there are no schema changes. State Street send an example of what might be required schema changes. Need ACI to relook at this. With a June Go-Live by TARGET2 market, there will not be much time for ACI to make the changes/deliver and for State STreet to install, test, and deploy toPROD. There is also usually mandatory Industry Testing months before Go-Live so will need to have the code in place. | [Oscar] Close Already sent to bank
HKICL Dual Network Channel June Industry Test; October Go-Live |  | Email sent yesterday about this. This is a Hong Kong Regulatory requirement. Mandatory Industry Test set for June | [Amit] Already send to bank the ACI position for this point
Full Payment Engine for Global Instance June Integration Test
SWIFT Market Mandates July-Sep Industry Test; Oct-Nov Go-Live
IISI Batch decommissioning Nov End of Life |  | Need a lot of lead time to contact clients and give them time to make changes to their system and test with State Street

## Sheet2
Milestone | Release code delivery | Status
ABA Support a New Fedwire SSD | 2025-11-01 | Bank in testing process
New SSB MPA Transact lines & New Tran Codes SSD | 2026-01-01
Intercompany Bank Settlements | 2026-03-01
MPA New Requirement | ( understanding phase)
Old tickets related with TARGET
Old tickets related with RITS