## Sheet1
Mails | ACI #03749089 : Intercompany Bank Settlement
|  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January
|  |  |  | sp8-sp12 | sp15-sp19 | sp22-sp26 | sp 29 -oct 3 | oct 6 oct 10 | oct 13 oct 17 | oct 20 oct 24 | oct 27 oct 31 | nov 3 nov7 | nov 10 nov14 | nov 17 nov21 | nov 24 nov28 | dic1-dic5 | dic8-dic12 | dic15-dic19 | dic22-dic27 | dic 29 -jan 2 | jan5-jan9 | jan12-jan16
Understanding Requirement
POC proposed
POC excution (15 different cases)
Solution Document
New requirements COVER
Signoff solution document
Estimation ACI
Estimation to Bank
| 2026-08-18 | Bank Create ticket 03749089
| 2026-09-02 | Dolores meeting
Intercompany Bank Settlement - Requirement finalization | 2026-09-10 | Amit to Mayjane | Good day Mayjane/ Team, As discussed, attached is the requirement document created by ACI depicting State Street requirement provided by bank on page 1. Please confirm on the clarification points (couple of them) and the subsequent page 2 depicting the flow and accounting in ACI RTPS. Once clarified and aligned on this, we can finalize and proceed on further steps. Thanks Best Regards, Amit
| 2026-09-15 | Matt Myers | Hello, Attaching the use case document describing the high-level requirement / approach. I asked Kai to capture additional points raised by the business (during the call and/or follow ups) and include another page or section to drill into those requirements and ensure they are covered (e.g. capture or look-up the debtor name/address, enable pending CHIPS payment to be updated to MOP = Fed as needed, etc). We can walk though in the call. Thanks Matt
| 2026-09-17 | Amit internal meeting | Hi Oscar, Agenda as follows- • Discuss on Interbank settlement requirement for Outgoing o Direct/Cov Scenario o Switching from CHIPS to Fed and vice-versa scenarios • Discuss on Incoming flow for Interbank settlement Thanks, Amit
| 2026-09-23 | Amit send mail to bank POC for outbond | Good day SS Team, As discussed, attached is the POC document created by ACI showcasing accounting on cross bank chips scenario for payment initiated from SSB and sent via SSI to chips in a single TRN. Please review the document and confirm on the POC results to set the expectations right. Thanks. Best Regards, Amit
| 2026-10-06 | Amit request internal meeting | Agenda To discuss on additional requirements and scenarios to do a POC in ACI environment for Intercompany Bank Settlement Requirement, mainly slide 5 & 6(attached). Thanks
| 2026-10-09 | Amit send internal mail with update scope | This is regarding Intercompany Bank Settlement requirement we discussed with Dolores and Phil earlier. This was a straightforward requirement for which Phil did the POC and we sent to bank for review and confirmation that this is what they are looking for. However, bank has now updated the requirement with additional scope on pg#5 (i.e #g. 1 to 3), which was discussed internally with Phil, but needs further discussion with bank. While we understand their ask on the first point, we will need some SME review the other 2 points together(in Phil’s absence) with bank on review call scheduled on 10/14 ( Phil will be unavailable & travelling during this week). Thanks.
| Wed 10/15/2025 9:24 AM | Mayjane mail: RE: SSB & ACI - Discuss Intercompany Bank Settlement POC & Requirements | Hi PCS team, Seems I’m unable to share the recording outside of SSB. Please see the attached transcript. Thanks. Mayjane Co PCC – Payments mxco@statestreet.com
| 2026-11-03 | Mayjane sent question to amit regarding call with Matt | Hi Amit, Regarding the call with Matt - Please provide a list of items you expect to discuss - How soon do you need this meeting? I ask because we don’t want to hold up progress but at the same time, as you know, everyone is hyper-focused on Go-Live.
| 2026-11-06 | Amit sent mail | Good day Mayjane, There are 3 items to discuss. 1. Fed line down scenario : Payment initiated from SSB and SSB Fed line is down. Bank business wants MTS to route the payment through SSI CHIPS. It does not look to be feasible prima facie and ACI request to discuss on this. 2. Payments initiated from SSB intended for SSI CHIPs, SSI CHIPs closed, Payments to route from SSI CHIPS to SSI FED , post CHIPS cutoff – Feasible, REROUTING logic as it is done today BAU, can be discussed with bank to be aligned on the same understanding. 3. Matt requested ACI to come back and explain on the out-of-box functionality supported by MTS to identify COVER payments. ACI can walk -through the supported logic OOB (SEC-WIRE evaluation). Need clarity on this requirement specific to Cover scenarios after knowing that SS processes direct outside MTS and cover within MTS. Please let us know the time in advance, so that we can arrange the appropriate expert in this subject. Please feel free to post any other thoughts or topics we may want to discuss. As for your 2nd question – We understand the situation and SSB & ACI are trying to accomplish as much as possible; need this call whenever we have some breather. Thanks
| Mon 11/17/2025 4:02 PM | Matt Myers | Hello, I recently updated the US intercompany settlement document for another meeting, so including it here to have the latest if we want to pull it up for this meeting. FYI, there are updates on the cover payment scenario based on what we learned from the last call a few weeks ago. Thanks Matt
| 2025-11-18 | Amit sent mail to Philp | Hi Phil, Bank has updated the requirement on Cover scenario.(attached) Please refer trailing email from Matt (bank business team) and below changes , we can discuss further on this tomorrow before bank call. Thanks. ii. When a payment is set to use the Cover Method (Advice + Cover), the system must generate and send a pacs.008 advice message to the Creditor Agent via Swift, alongside the pacs.009 cover payment for clearing and settlement (to Fed or CHIPS). • The COV method should be selected based on the presence of an instructed reimbursement agent (MX) or Receivers Correspondent field 54 (MT). • In the legacy IBS operating model, the MT103 (pacs.008) pre-advice message is first sent outbound via Swift and when the ACK is received the MT202COV (pacs.009cov) is released. If we receive a Swift NAK because there is no RMA in place with the Instructed Reimbursement Agent, the payment will be held in the IBS exception queue. o ACI has explained that RTPS has an upfront control to validate an RMA is in place with the Instructed Reimbursement Agent before either of the messages of the cover payment are released from the system. The business has agreed this capability meets our requirements. o We must load an RMA file into US RTPS (Boston Bank) for all the required counterparty BICs and this must be maintained going forward. o Upon processing a cover payment and there is no RMA is in place, the RTPS system must support converting the cover to a straight customer transfer to be paid directly through the Fed or CHIPS. Thanks, Amit
| November 18, 2025 1:00 PM-2:00 PM | Meeting Mayjane :FW: SSB & ACI - Discuss Intercompany Bank Settlement Open Items (inline) | Agenda: There are 3 items to discuss. 1. Fed line down scenario : Payment initiated from SSB and SSB Fed line is down. Bank business wants MTS to route the payment through SSI CHIPS. It does not look to be feasible prima facie and ACI request to discuss on this. 2. Payments initiated from SSB intended for SSI CHIPs, SSI CHIPs closed, Payments to route from SSI CHIPS to SSI FED , post CHIPS cutoff – Feasible, REROUTING logic as it is done today BAU, can be discussed with bank to be aligned on the same understanding. 3. Matt requested ACI to come back and explain on the out-of-box functionality supported by MTS to identify COVER payments. ACI can walk -through the supported logic OOB (SEC-WIRE evaluation). Need clarity on this requirement specific to Cover scenarios after knowing that SS processes direct outside MTS and cover within MTS. Please let us know the time in advance, so that we can arrange the appropriate expert in this subject.
| 2026-11-18 | Philp sent mail | Attached are the options in the secwire eval table that can be used to default the secondary wire. The default is based upon the FTR screen and is a default only. I thought I had asked for the bank to provide a message print of a TRN that is processed for discussion. Has that been requested/provided? Would help me to better assist.
| 2026-11-21 | Amit sent mail to Philp | Good day Phil, Attached is the Bank Adapter cross bank payment that worked successfully and has the Credit, BBK and Beneficiary details as you requested. However, not sure why it isn’t doing the RMA check. Thanks, Amit
| 2026-11-24 | Mayjane- FW: Re-scheduled Take 2 per ACI: SSmitB & ACI - Discuss Intercompany Bank Settlement Open Items (inline) | Agenda: There are 3 items to discuss. 1. Fed line down scenario : Payment initiated from SSB and SSB Fed line is down. Bank business wants MTS to route the payment through SSI CHIPS. It does not look to be feasible prima facie and ACI request to discuss on this. 2. Payments initiated from SSB intended for SSI CHIPs, SSI CHIPs closed, Payments to route from SSI CHIPS to SSI FED , post CHIPS cutoff – Feasible, REROUTING logic as it is done today BAU, can be discussed with bank to be aligned on the same understanding. 3. Matt requested ACI to come back and explain on the out-of-box functionality supported by MTS to identify COVER payments. ACI can walk -through the supported logic OOB (SEC-WIRE evaluation). Need clarity on this requirement specific to Cover scenarios after knowing that SS processes direct outside MTS and cover within MTS. Please let us know the time in advance, so that we can arrange the appropriate expert in this subject.
| 1-Dic | Mayjane - FW: Re-scheduled Take 3 per ACI: SSB & ACI - Discuss Intercompany Bank Settlement Open Items (inline) | Comments to ensure we are ready to discuss next week….. here are 3 items to discuss. 1. Fed line down scenario : Payment initiated from SSB and SSB Fed line is down. Bank business wants MTS to route the payment through SSI CHIPS. It does not look to be feasible prima facie and ACI request to discuss on this. PJH>>> There is not current functionality to re-route messages from the SSB FEDOUT line to the SSI CHIPs line. The current functionality allow re-routing form FED to CHP and CHP to FED (via PRR function) but only when in the same bank. So this can be done for SSI, which has both FED and CHP lines. 2. Payments initiated from SSB intended for SSI CHIPs, SSI CHIPs closed, Payments to route from SSI CHIPS to SSI FED , post CHIPS cutoff – Feasible, REROUTING logic as it is done today BAU, can be discussed with bank to be aligned on the same understanding. PJH>>> This needs to be tested for the POC. The PCS team will test processing from SSB to SSI CHP when after cutoff to see if the channel of FED (on SSB) is selected after cutoff. This needs to be done prior to the call on Monday 12/1. 3. Matt requested ACI to come back and explain on the out-of-box functionality supported by MTS to identify COVER payments. ACI can walk -through the supported logic OOB (SEC-WIRE evaluation). Need clarity on this requirement specific to Cover scenarios after knowing that SS processes direct outside MTS and cover within MTS. Please let us know the time in advance, so that we can arrange the appropriate expert in this subject. PJH>>> Standard out of the box functionality allows for the generation of a primary (pacs.009 to FED) and Secondary (pacs.008 to BBK via SWF). MTS has a secwire eval table that allow the bank to define when they want the BBK (or IBKs) to default the generation of the secondary pacs.008. The criteria has been shared with the bank for discussion purposes. The proof of concept here is to receive a pacs.008 with FED in the credit and the BBK would be a bank that SSB expects the secondary wire to be sent to. Testing will have to be a BBK with an RMA and one without.
| 2026-12-01 | Philp sent internal mail | As part of discussion, we need to discuss the flag SWF_AUTH_MODE: STR(1);N SSB has this set to N, which would imply that any authorization is done outside of MTS. The bank would have to load the RMAs onto mts for us to validate that it has an RMA. We can try to make this Y and do a proof of concept. I copied the cfg_rec.dat to the area specific directory and made the flag change. The file is named…. [hegartyp@cov3lmtssvc14vm]:/usr/local/intranet/areas/ssc_v60_svc_qa/config$ ls cfg_rec_swf_auth_mode.dat cfg_rec_swf_auth_mode.dat rename to cfg_rec.dat do an mts -c and mts -r then try to enter a message with the BBK without a SAT/RMA . I think we tried PHILUS33 but cannot really remember.
| 2026-12-01 | Tejas send mails to Philp related last mail
| 2026-12-01 | Philp sent mail to bank after 1 dec meeting | After out discussion today attached file Sec Wire Eval table
| 2025-12-02 | Mayjane sent mail to bank | Hi, Some updates from ACI after yesterday’s call: 1. ACI plans to deliver the Solution Document for Sign-off on Friday, Dec 5. It will exclude Cover Scenario. 2. ACI will complete 2 POCs by Friday, Dec 5. • POC for Inbound • POC for CHIPS-> FED. Note that FED->CHIPS is not able to be supported. 3. After Solution Document is signed-off, Estimates can be taken up.
| 2026-12-04 | Amit sent mail to Matt M (Bank) | Hello Matt & team, This is regarding the Inbound scenario for the Cross-bank requirement from the bank. Request you to review the questions below and provide feedback for the same, please. 1. For the scenario below – when the Incoming USD payment is received into RTPS NY Bank (CHIPS) for a client DDA on Transact Boston; the ask from bank is to update the CHIPS settlement instructions to pay into the client DDA(in Boston) if and only if the client DDA is on Transact Boston. Questions from ACI – a. What does the bank expect , when the Incoming USD payment received into RTPS NY Bank (CHIPS) is for a client DDA on Hogan Boston? Please advise. b. Or is #a not a valid case at all, and RTPS NY Bank will always receive Transact account? If answer to #b is yes, then transact account can either reside in Boston or NY. If the Transact a/c resides in Boston branch then the ask from bank is to update the CHIPS settlement instructions to pay into the client DDA(in Boston) with intercompany posting applicable; and if Transact a/c resides in NY branch then the ask is to update the CHIPS settlement instructions to pay into the client DDA(in NY) as it is done today (settle in SS branch account) . Please confirm if the understanding is correct. Thanks c. Can there be a use-case where the Incoming USD payment received into RTPS NY Bank is for a client DDA which is on both Boston & NY branch?
| 2026-12-05 | Amit sent mail to bank POC results | Please find updates below. Please note that 2 items are still in progress as follows, and we target to complete this by early next week i.e. Tuesday. 1. POC for CHIPSFED contains 3 use-cases Out of which , 2 use-cases are completed and is working as expected. While performing the POC for the 3rd use-case , it was realized that it requires additional MTS config change to be done before the POC can commence for this case. App config is working on the same and we are optimistic to be completed by Monday. 2. For a requirement related to Inward from CHIPs, we are awaiting response from bank on the mail attached. While the POC is completed for the same, it is important to have the answers to conclude on the expectations and incorporate in the design document. Thanks !
| 2026-12-05 | Matt answer mail Amit | Hello Matt & team, This is regarding the Inbound scenario for the Cross-bank requirement from the bank. Request you to review the questions below and provide feedback for the same, please. 1. For the scenario below – when the Incoming USD payment is received into RTPS NY Bank (CHIPS) for a client DDA on Transact Boston; the ask from bank is to update the CHIPS settlement instructions to pay into the client DDA(in Boston) if and only if the client DDA is on Transact Boston. Questions from ACI – a. What does the bank expect , when the Incoming USD payment received into RTPS NY Bank (CHIPS) is for a client DDA on Hogan Boston? Please advise. Existing processing should continue for unconverted accounts that remain on Hogan. Keep in mind, there are no client DDAs on the NY bank. We only have State Street branch settlement/nostro accounts and our current SSIs (for external parties to pay into the NY bank) include the state street branch nostro as the creditor account. These nostros are on Transact NY bank now. For converted client DDA accounts, on Transact Boston, we will update SSIs to external parties to pay to the client DDA (as the creditor / creditor account). The presence of the client DDA as the creditor account (which RTPS determines is on Transact Boston branch via the REL file) should invoke this interco settlement process. b. Or is #a not a valid case at all, and RTPS NY Bank will always receive Transact account? See above. There will be a multiple migration tranches of client DDAs to Transact Boston over approx 9 month period. So both scenarios will coexist during this time (NY bank settlement to the SSB branch nostro only for unconverted, and intercompany settlement for the converted Transact Bos accounts). If answer to #b is yes, then transact account can either reside in Boston or NY. If the Transact a/c resides in Boston branch then the ask from bank is to update the CHIPS settlement instructions to pay into the client DDA(in Boston) with intercompany posting applicable; and if Transact a/c resides in NY branch then the ask is to update the CHIPS settlement instructions to pay into the client DDA(in NY) as it is done today (settle in SS branch account) . Please confirm if the understanding is correct. Thanks c. Can there be a use-case where the Incoming USD payment received into RTPS NY Bank is for a client DDA which is on both Boston & NY branch? No
| 2026-12-08 | Amit sent answer to Phil | Hi Phil, Based on below response (highlighted in green in trailing email) from bank (Operations) looks like NY branch can also receive Hogan DDA a/c held at SSB, and as per them it should settle in Boston without Intercompany (cross bank ) accounting. Our POC for incoming goes for intercompany accounting irrespective of whether the incoming payment has Transact or Hogan creditor account. That means , the solution is not feasible in MTS and should be communicated to bank. Please advise if you think otherwise. Thanks, Amit
| 2026-12-09 | Amit sent Philp Answer to Matt | Good day Matt, Thanks for the clarification. Please find response to your email specific to this Incoming flow. For Incoming payments from clearing , in RTPS, the CROSS_BANK flag configuration in MTS will only allow interbank accounting when the credit account is not on NY and is found on BOS, regardless of presence of an indicator in REL file to indicate the account is Transact a/c or Hogan in BOS branch . In other words, specifically for incoming from clearing- RTPS does not determine the intercompany posting based on the indicator in REL file (Transact or Boston a/c). Simply, the logic is MTS will only allow interbank accounting when the credit account is not on NY and is found on BOS based on a CROSS_BANK flag. So, the posting entries would be as follows (when the credit account is not on NY and is found on BOS) • Debit NY bank clearing/settlement account • credit the Cross-bank accounts • Debit Cross bank account • credit Bos DDA Is your ask that the debit to be to the NY chips Clearing account and the Credit to the BOS Hogan account. Then no, to move money from one bank to the other requires cross bank accounting Please let us know. Thanks, Amit
| 2026-12-09 | Matt answer mail Amit | Thanks Amit. This is fine. We will control this with the SSI change on our side. Prior to the client migrating to Transact, the payments will come in as they do today with the SSB branch nostro account (on NY bank) as the creditor account. This will settle to NY only, as a debit NY CHIPS clearing and credit SSB branch nostro account (also on NY bank), as it does today. When the client migrates, we will update the SSIs so the creditor account is the client DDA on Transact (on the Bos bank). This will settle interbank as you noted. If you have additional follow-ups please feel free to send to me directly. Thanks, Matt
| 2026-12-12 | Amit sent to Mayjane draff solution document for signoff | Hi Mayjane, Please find attached draft cross bank solution document for bank sign-off. Let me know in case of any questions/concerns. Thanks!
| 2026-12-15 | Mayjane sent internal mail to bank for signoff
| 2026-12-15 | Matt send mail to Philp | Hello Phil, Just circling back on the table you shared for the cover/serial payment evaluation. I may need a quick discussion to understand the available fields which can be used to determine cover or serial. However, it may be simpler than that because when we are sending the pacs.008 payment instruction we know which we would like to pay via the cover method (the rest will be serial). Our upstream flows are designed to populate the Instructed Reimbursement Agent field (legacy MT tag 54a Receivers Correspondent) with a BIC when the payment should be processed via the cover method. The BIC/Agent in this field of course is the participant we should make the cover payment through (i.e. will be the receiver of the pacs.009cov). So for example, our pacs.008 instruction sent via Bank Adapter would look similar to the following (see below excerpt with instructed reimbursement agent BIC populated in the group header). <pacs:FIToFICstmrCdtTrf> <pacs:GrpHdr> <pacs:MsgId>25LHCGKBQLXFTA</pacs:MsgId> <pacs:CreDtTm>9999-12-31T00:00:00+00:00</pacs:CreDtTm> <pacs:NbOfTxs>1</pacs:NbOfTxs> <pacs:SttlmInf> <pacs:SttlmMtd>COVE</pacs:SttlmMtd> <pacs:InstgRmbrsmntAgt> <pacs:FinInstnId> <pacs:BICFI>SBOSUS33XXX</pacs:BICFI> </pacs:FinInstnId> </pacs:InstgRmbrsmntAgt> <pacs:InstdRmbrsmntAgt> <pacs:FinInstnId> <pacs:BICFI>IRVTUS3NXXX</pacs:BICFI> </pacs:FinInstnId> </pacs:InstdRmbrsmntAgt> </pacs:SttlmInf> </pacs:GrpHdr> Not sure whether we could configure based on the presence of instructed reimbursement agent BIC. If not, I’m sure we could use this as a trigger on our side to set one of the other fields from the evaluation table that can be used in the cover/serial determination. In other words, I’m sure we can achieve the desired result leveraging the table, we just may need some guidance on the best way to do that. Happy to have a quick off-line chat.
| 2026-12-15 | mayjane sent to amit test-cases
| 2026-12-16 | Venkata send signoff
| 2026-12-16 | Matt sent conditional signoff | Hello I approve with the following condition/update: • Please remove or reword the point in the Assumptions stating that cover payment processing is out of scope. It can be reworded to state that the details of the configuration/rules will be worked out and are not specified in the document, but the cover/serial logic must be enabled. Attached an email I sent yesterday (to Amit and Phil) stating that we just need to work with you to understand how we can work within the bounds of the ACI/RTPS evaluation table to drive serial vs cover. Again, we will look to do this within the bounds of configuring the table rules and not a custom solution (so perhaps that should be the point in the assumptions section)
| 2026-12-16 | Mark Coppola | High level doc approved.
| 2026-01-07 | Sizing commite | analize
| 2026-01-14 | Sizing commite | conclude
| 2026-01-15 | Jean H share estimation
| 2026-01-16 | Oscar Sent to bank the timelines | Hi Heidi / Mayjane Following receipt of the bank’s authorization and a review of the project timelines and capacity, we discussed the delivery schedule with ACI SMEs. It was jointly agreed that aligning this delivery with the March release would be the most appropriate option.